Program Title: Statewide Residential Single Family Energy Efficiency Rebates

- Program Overview

- The Single Family Energy Efficiency Rebates program is a statewide program, administered by the four California investor owned utilities, which provides rebates on various home improvement products, heating and cooling equipment, appliances, and residential pool equipment.

- Program Summary

- Total program budget = $2,880,965*

Expenditures to date = 2,918,001

*The program budget has been adjusted to reflect the October 10, 2003 Commission's approval regarding SoCalGas' Motion to replace funds inadvertently removed from SoCalGas’ PY 2003 statewide and local program budgets in D.03-04-055.

Additionally, the Commission approved SoCalGas’  request to increase the SFR program budget by  $1,200,000 to maintain incentive funding.

- Total net demand reduction and energy savings:

|  | Net Peak kW | Net kWh | Net therms |
| --- | --- | --- | --- |
| Program Target* | 758 | 2,675,121 | 952,328 |
| Actual | 528 | 2,547,919 | 896,805 |
| Committed | 0 | 0 | 0 |
| Total Actual and Committed (Recorded) | 528 | 2,547,919 | 896,805 |

*2003 targets were not set for the third quarter.

- Total number of customers served:

Projected: 	Projection of the number of customers to be served was not provided in the implementation plan.

Actual:  12,180 sites were completed during third quarter

- Projected and actual number of units:

Please refer to program activity tables in corresponding program workbook.

- Total rebate ($) paid: $2,232,920

Committed = $0

- Program Implementation Status

- Status of program delivery

- In compliance with Decision 03-04-055, Statewide utilities worked jointly to launch the Single Family Rebate program following Commission approval on April 17th, 2003.

- Customer Enrollment

- Sample copies of program applications were sent to the California Public Utilities Commission’s Energy Division.

- Workbook

- Please refer to the informational tables shown in the corresponding program workbook for details on program expenditures and activities.

- Training

- There was no statewide training during the third quarter.

- Marketing

- Coordinated marketing activities with the CPUC approved Direct Marketing Outreach Program.

- Updated web site information to show rebate funds availability.

- Conveyed information via SCG website to survey customers on methods of improving SCG Residential Rebates

- Hard to Reach

- Third Quarter Hard-To-Reach accomplishments will apply toward 2003 targets.

- The 2003 Hard-To-Reach target for Single Family Rebate is 23% of Single Family Rebate applications will be from Hard-To-Reach customers. Thru the third quarter of 2003, Single Family Rebate has 25% of applications from Hard-To-Reach customers.

- Program Accomplishments

Statewide Third Quarter Activities

- The statewide team worked jointly to continue aggressive implementation of the 2003 Single Family Rebate program.  Statewide activities included:

- The CA HVAC Initiative team met in July to begin planning for participation in several conferences scheduled for the remainder of 2003:  two with the Air-Conditioning and Refrigeration Institute (ARI) in Washington, DC and in Boston; a meeting with The Consortium For Energy Efficiency (CEE) in Waltham, MA; and one at the 2003 Energy Star HVAC Partner Meeting scheduled for late October in Portland, OR.

- Participated in the Energy Star Appliance Partners Meeting in Portland Oregon September 23 – 24.  Appliance manufacturers and major national retailers were well represented along with utilities from around the country. The IOUs met separately with Home Depot and Lowe’s to discuss plans for 2004-2005.

- Conducted extensive discussions with Leslie’s Poolmart, Inc. for the conduct of a pilot instant rebate program with this retailer's 106 California stores. A final agreement for each of the IOUs to incorporate is near completion.  This agreement would become effective with the 2004 program.

- The IOUs attended and participated in the CEE Program Conference in Waltham, Massachusetts September 8 - 10.  The conference focused on expanding HVAC partnerships with such industry interests as Energy Star, utilities, national distributors, HVAC manufacturers, PUC organizations, NATE, ACCA and other industry partners. These organizations discussed opportunities for collaboration and approaches needed to develop comprehensive national energy efficiency products and equipment installation standards.

- The IOUs agreed to co-fund an approach for the implementation of a more sophisticated and user-friendly web based list of qualifying models for the program’s HVAC measures.

- Participated in the Air-Conditioning and Refrigeration Institute (ARI) conferences held in Washington, DC and Boston.  These meetings addressed the continuing effort on behalf of the California utilities to persuade the trade organization to resume publication of EER data in the unitary product directory.

SCG Third Quarter Activities

- Coordinated marketing activities with the CPUC approved Direct Marketing Outreach Program.

- Updated web site information to show rebate funds availability.

- Implemented SCG website to survey customers on methods of improving SCG Residential Rebates

- Maintained Retailer Management effort with over 377 participating local retailers which included notifying retail manager of continuing rebate availability and details; replenishing rebate applications and information in multiple places in retail stores; explaining program changes and differences between SCG rebates and other marketplace rebates.

- Worked with Lowe’s and Home Depot to improve process for issuing in-store rebates.

- 5,000 additional rebate applications were printed and distributed to satisfy retail demand.

- Program Challenges

None.

- Customer Disputes

None.

- Compliance Items

- The following list itemizes the various regulatory compliance items issued by the California Public Utilities Commission directly relating to this program.

D. 03-04-055, Ordering Paragraph 3 states:

No party shall delay program commencement or preparation pending submission of or Commission action on these plans.

Response:

Program commencement and preparation were not delayed pending submission of or Commission action on these plans.

D. 03-04-055, Ordering Paragraph 6 states:

The utilities shall work together to market their statewide programs.  To the extent the utilities offer the same programs, they shall advertise them together.  Program Implementation Plans and quarterly reports shall describe utility efforts to coordinate programs.  Utilities shall focus all PGC-funded marketing for programs in this decision on energy efficiency messages.

Response:

SDG&E will work together with other utilities to market their statewide programs.  To the extent SDG&E offers the same programs SDG&E will advertise them together with the other utilities.  SDG&E’s Program Implementation Plans and quarterly reports describe utility efforts to coordinate programs.  Utilities shall focus all PGC-funded marketing for programs in this decision on energy efficiency messages.

Decision 03-04-055, states:

SDG&E proposes to reduce the requirements for pool pumps and motors to achieve statewide consistency.  Specifically, SDG&E proposes to eliminate the requirements of (1) peak shifting and (2) reduction of filtering time.

While statewide consistency is one program objective, it should not take precedence over goals relating to energy savings and cost-effectiveness.  For that reason, we will deny SDG&E’s proposal to eliminate its peak shifting and filtering time standards and instead require the other IOUs to adopt the standards used by SDG&E in 2002.

All IOUs shall maintain the unit goals proposed for PY2003.  Their future quarterly reports should include kW and kWh projections corrected for the increased standard.  The entries for those measures should be accompanied by an explanation of how the numbers were changed from the filed implementation plans.

Response:

SDG&E will apply 2002 shifting and filtering time standards to the 2003 program

Retracted Measures

Energy Star® 80% AFUE furnaces will be removed from the list of measures eligible for incentives due to low customer demand for the measure.

Response:

Effective 2003 -  Energy Star® 80% AFUE furnaces were removed from the list of  eligible measures.