| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Multifamily Energy Efficiency Rebates Redacted Version per G.O. 66-C and PUC Code Sec. 583 |
| IOU Service Area: | SCG |
| Program Number: | 1246-04 |
| Program Type: | IOU Statewide Program |
| Month | August-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Aug-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $2,865,628 | $141,009 | 5% | $625,509 | 22% |  |  | $625,509 | 22% | $2,240,119 |
| Admin | $422,750 | $10,510 | 2% | $99,948 | 24% |  |  | $99,948 | 24% | $322,802 |
| Marketing | $91,250 | $2,941 | 3% | $37,119 | 41% |  |  | $37,119 | 41% | $54,131 |
| DI | $2,280,550 | $127,558 | 6% | $488,442 | 21% |  |  | $488,442 | 21% | $1,792,108 |
| EM&V | $71,078 |  |  |  |  |  |  |  |  | $71,078 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

| Energy Effects | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 693 | 38 | 5% | 38 | 6% |  |  | 38 | 6% | 655 |
| Annual kWh | 9,659,430 | 337,092 | 3% | 1,908,242 | 20% |  |  | 1,908,242 | 20% | 7,751,188 |
| Lifecyc kWh | 119,776,653 | 4,257,205 | 4% | 23,106,367 | 19% |  |  | 23,106,367 | 19% | 96,670,287 |
| Annual Therms | 1,254,993 | 67,836 | 5% | 270,735 | 22% |  |  | 270,735 | 22% | 984,257 |
| Lifecyc Therms | 14,395,514 | 828,689 | 6% | 3,150,293 | 22% |  |  | 3,150,293 | 22% | 11,245,221 |

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Aug-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 29% of rebate applications come from HTR zip codes | 29% | 31% | 107% |  |  |  |  | 31% | 107% | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities:  continued re-fining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

    - Marketing

    - Marketing placed its full-page advertisement for the 2004 Energy Efficiency Program in four publications.  The ads were originally scheduled to run through June, but will run through the fourth quarter due to overwhelming response.

    - Continued referral and direct mailing of customer applications through its Customer Contact centers during the month.

    - Distributed marketing materials at the Orange County Fairgrounds – August 27-29.

    - Direct Implementation

      - For Audits and Site Surveys  - Not Applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization

- Total number of customers sites served, 62

- Summary of type and number of measures installed or repaired.

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 4 |
| Building Shell - Insulation | 15,392 |
| HVAC - Controls | 914 |
| Other | 32 |
| Water Heating - Systems | 69 |
| Water Heating - Controls | 2 |
| Grand Total | 16,413 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan (PIP) for this program on February 2, 2004.

- Coordination Activities 
In May, statewide IOUs (SDG&E, PG&E, SCE, and SCG) continued regular communication to discuss program progress and share marketing approaches, promotional plans, and market participation.  The Utilities also continue to provide review, recommendation and approval of reservation procedures.  Other coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing - 
None

- Additional items -None

Supporting Documentation

- Marketing Materials – 
Full page ad placed with four Apartment publications

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation- 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
There were no training activities this month

- Trade Shows and Public Event

Updated program information for SCG Multi Family Rebate as of October 7, 2004:

For the Multifamily Rebate program, a project is considered "Installed" when it has been paid. Similarly, a project is considered “Committed” when the application is in processing, but has not yet been approved for final payment.  For monthly reporting purposes, the Recorded Activities worksheet only includes projects, which have been installed, not those that are “committed”.

For purposes of projecting funding availability, and determining measure closures however, SCG considers both installed and committed categories in order to best assess remaining funding availability.  The following table reflects the total sums of both status categories, through October .7, 2004:

| Program | Incentive Budget | Status | Incentive $ | Gross kW | Gross kWh | Gross Therms | Net kW | Net kWh | Net Therms |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Multi-Family Rebate Program | $ 2,164,300 | Committed | $ 619,124.00 | 31 | 3,264,229 | 389,201 | 28 | 2,905,116 | 346,295 |
| Multi-Family Rebate Program | $ 2,164,300 | Installed | $ 656,429.90 | 68 | 2,943,483 | 405,736 | 60 | 2,619,683 | 360,879 |
| Total | $ 4,328,600 |  | $ 1,275,553.90 | 99 | 6,207,712 | 794,937 | 88 | 5,524,799 | 707,173 |
| 1 Commitments are applications that are currently in processing but have not yet been approved for payment. |