| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Multifamily Energy Efficiency Rebates |
| IOU Service Area: | SCG |
| Program Number: | 1246-04 |
| Program Type: | IOU Statewide Program |
| Month | May-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,624,768 | $171,539 | 4% | $2,977,619 | 64% |  |  | $2,977,619 | 64% | $1,647,149 |
| Admin | $522,750 | $5,425 | 1% | $226,057 | 43% |  |  | $226,057 | 43% | $296,693 |
| Marketing | $455,360 | $38,738 | 9% | $407,525 | 89% |  |  | $407,525 | 89% | $47,835 |
| DI | $3,575,580 | $127,376 | 4% | $2,344,037 | 66% |  |  | $2,344,037 | 66% | $1,231,543 |
| EM&V | $71,078 |  |  |  |  |  |  |  |  | $71,078 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 791 |  |  | 113 | 14% |  |  | 113 | 14% | 678 |
| Annual kWh | 13,141,337 | 681,383 | 5% | 11,036,250 | 84% |  |  | 11,036,250 | 84% | 2,105,087 |
| Lifecyc kWh | 162,081,837 | 8,175,758 | 5% | 133,059,870 | 82% |  |  | 133,059,870 | 82% | 29,021,967 |
| Annual Therms | 1,885,379 | 71,509 | 4% | 1,309,564 | 69% |  |  | 1,309,564 | 69% | 575,815 |
| Lifecyc Therms | 21,317,206 | 794,623 | 4% | 15,178,026 | 71% |  |  | 15,178,026 | 71% | 6,139,180 |

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 29% of rebate applications come from HTR zip codes | 29% | 30% | 103% |  |  |  |  | 30% | 103% | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

    - Regular monthly administrative activities include but are not limited to the following activities:

- Provided program status and applications to 78 customers requesting to be placed on waitlist.

- SCG’s website updated with information regarding Program closure; MF Rebate Application no longer available via internet.

- Multiple calls with CA statewide Multifamily Team to review budgets and program status.

- Completed ‘ride-along’ with Company’s Industrial Service Techs to observe high efficient water and space heating boilers and controllers.

    - Marketing

    - Completed fifth of six month advertising campaign of full-page ads promoting SCG MF Energy Efficiency rebates in 4 property owner industry publications.

    - Launched and distributed ad for MF Trends Magazine at the Pacific Coast Builder’s

    - Direct Implementation

      - For Audits and Site Surveys  - Not Applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization

- Total number of customers sites served

- Summary of type and number of measures installed or repaired.

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 15 |
| HVAC - Controls | 2,004 |
| Water Heating - Systems | 37 |
| Water Heating - Controls | 1 |
| Grand Total | 2,057 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities 
 Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing - 
None

- Additional Items - None

Supporting Documentation

- Marketing Materials – 
Full page ad placed with four Apartment publications

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation- 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
There were no training activities this month

- Trade Shows and Public Event

Pasadena Home and Garden Show