| Implementer Name: | Southern California Gas Company - SCG |
| --- | --- |
| Program Name: | IOU/UC/CSU Partnership for Energy Efficiency |
| IOU Service Area: | SCG |
| Program Number: | 1475-04 |
| Program Type: | IOU Partnership Program |
| Month | May-05 |

- Program Status

Program Description:

The University of California/California State University (UC/CSU) and Investor-Owned Utility (IOU) Energy Efficiency Partnership is a unique, statewide energy efficiency program that accomplishes immediate, long-term energy efficiency and demand savings, and establishes a permanent framework for a sustainable comprehensive energy management program at the thirty three (33) UC and CSU campuses served by California’s four large IOUs.  This program capitalizes on the vast resources and expertise of the UC/CSU and the California IOU’s to ensure a successful and cost effective program that meets all objectives of the California Public Utilities Commission (CPUC or Commission) as articulated in Decision 03-08-067. In lays the groundwork for not only a continued UC/CSU comprehensive energy efficiency program but also establishes a model for statewide partnership programs and will allow expansion of this program to California’s community colleges in the next funding cycle. The UC/CSU/IOU partnership program is comprised of three elements, which will operate on a statewide, integrated basis, providing immediate energy savings and setting the foundation for a long-term program focused on sustainability and best practices: Energy Efficiency Retrofits, Facility Retro-and Continuous Commissioning, and Energy Efficiency Education and Best Practices Development and Training.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $2,039,405 | $5,606 | 0% | $1,603,678 | 79% |  |  | $1,603,678 | 79% | $435,727 |
| Admin | $177,827 | $4,716 | 3% | $109,238 | 61% |  |  | $109,238 | 61% | $68,589 |
| Marketing |  | $318 | NA | $375,881 | NA |  | NA | $375,881 | NA | -$375,881 |
| DI | $1,800,828 | $572 | 0% | $1,118,559 | 62% |  |  | $1,118,559 | 62% | $682,269 |
| EM&V | $60,750 |  |  |  |  |  |  |  |  | $60,750 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

| Energy Effects | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 425,945 |  |  | 443,289 | 104% |  |  | 443,289 | 104% | -17,344 |
| Lifecyc Therms | 7,447,349 |  |  | 5,458,895 | 73% |  |  | 5,458,895 | 73% | 1,988,454 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

This program does not have performance goals.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Activities/Accomplishments –

- The Management Team approved a T-12 to T-8 lighting retrofit project at UC San Francisco’s Mission Center Building.

- The Management Team has authorized an additional $15,000 to further enhance the partnership website to include campus project scheduling capabilities.  The Management Team has also authorized $60,000 for the development of an MBCx Best Practices Report.  The report will document program components, execution, results, and lessons learned and be used to inform policy makers as well as future program implementers and participants.  Newcomb Anderson McCormick will lead the development effort.  Both of these projects are being funded from the engineering assistance budget available to the campuses.

- BOC classes were held on May 10, 11 and 12 in Sacramento, San Francisco and Tulare.  Scheduled sessions in Northridge were postponed due to low enrollment.  A Labs 21 course was held on May 17 in Fullerton.  All courses were well attended with approximately 40 people attending the three BOC sessions.

- The T&E Team issued a calendar of scheduled training sessions on the partnership website.  The calendar will be updated continually as new courses are scheduled.

    - Marketing

None

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable.

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served - None

- Summary of type and number of measures installed or repaired - None

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook  due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
None

- Coordination Activities

None

- Changes to Subcontractors or Staffing

Awad-Singer is no longer directly supporting the program as their role was absorbed into the work now being performed by Newcomb Anderson McCormick.  Awad-Singer’s final invoice was paid in May.

- Additional Items

None

Supporting Documentation

- Marketing Materials – 
None.

- Point of Purchase Program Documentation –
None

- Free Measure Distribution Documentation – 
None

- Upstream Incentive Documentation – 
None

- Training Documentation – 
None

- Trade Shows and Public Events – 
None

# Footnotes

The partnership has renamed this program element as “Monitoring Based Commissioning” (MBC) to better reflect the actual scope of the activity.  The program goals and overall approach remain the same.