| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | June-05 |

- Program Status

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,145,090 | $410,564 | 3% | $8,351,080 | 69% |  |  | $8,351,080 | 69% | $3,794,010 |
| Admin | $1,432,400 | $52,936 | 4% | $695,761 | 49% |  |  | $695,761 | 49% | $736,639 |
| Marketing | $2,174,790 | $43,595 | 2% | $1,654,467 | 76% |  |  | $1,654,467 | 76% | $520,323 |
| DI | $8,368,900 | $314,033 | 4% | $6,000,852 | 72% |  |  | $6,000,852 | 72% | $2,368,048 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Jun-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,250 | 149 | 3% | 2,448 | 58% |  |  | 2,448 | 58% | 1,801 |
| Annual kWh | 10,766,576 | 325,899 | 3% | 7,385,228 | 69% |  |  | 7,385,228 | 69% | 3,381,348 |
| Lifecyc kWh | 157,409,229 | 4,777,933 | 3% | 101,714,739 | 65% |  |  | 101,714,739 | 65% | 55,694,491 |
| Annual Therms | 4,736,076 | 163,363 | 3% | 3,543,964 | 75% |  |  | 3,543,964 | 75% | 1,192,112 |
| Lifecyc Therms | 63,299,167 | 2,127,645 | 3% | 44,691,517 | 71% |  |  | 44,691,517 | 71% | 18,607,650 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | June -05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 28% | 121% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative  - 
None.

    - Marketing

    - June/July newsletter article promoting SCG SF rebate program will be sent out to all customers in the June gas bill.

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 3,616 |
| Building Shell - Insulation | 414,161 |
| HVAC - Controls | 248 |
| HVAC - Heating Systems | 177 |
| Water Heating - Systems | 315 |
| Grand Total | 418,517 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing – Program Manager Assignment has changed

- Additional Items-None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month