| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Multifamily Energy Efficiency Rebates |
| IOU Service Area: | SCG |
| Program Number: | 1246-04 |
| Program Type: | IOU Statewide Program |
| Month | June-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,624,768 | $230,168 | 5% | $3,207,786 | 69% |  |  | $3,207,786 | 69% | $1,416,982 |
| Admin | $522,750 | $39,913 | 8% | $265,970 | 51% |  |  | $265,970 | 51% | $256,780 |
| Marketing | $455,360 | $24,475 | 5% | $432,000 | 95% |  |  | $432,000 | 95% | $23,360 |
| DI | $3,575,580 | $165,780 | 5% | $2,509,816 | 70% |  |  | $2,509,816 | 70% | $1,065,764 |
| EM&V | $71,078 |  |  |  |  |  |  |  |  | $71,078 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Jun-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 791 | 4 | 1% | 117 | 15% |  |  | 117 | 15% | 674 |
| Annual kWh | 13,141,337 | 512,037 | 4% | 11,548,287 | 88% |  |  | 11,548,287 | 88% | 1,593,050 |
| Lifecyc kWh | 162,081,837 | 6,158,873 | 4% | 139,218,742 | 86% |  |  | 139,218,742 | 86% | 22,863,095 |
| Annual Therms | 1,885,379 | 86,562 | 5% | 1,396,126 | 74% |  |  | 1,396,126 | 74% | 489,253 |
| Lifecyc Therms | 21,317,206 | 953,102 | 4% | 16,131,127 | 76% |  |  | 16,131,127 | 76% | 5,186,079 |

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | June-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 29% of rebate applications come from HTR zip codes | 29% | 29% | 100% |  |  |  |  | 30% | 103% | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

    - Regular monthly administrative activities include but are not limited to the following activities:

- Provided program status and applications to 101 customers requesting to be placed on waitlist.

- Attended HUD’s Affordable Housing; Green Building Conference

    - Marketing

    - Completed sixth of six month advertising campaign of full-page ads promoting SCG MF Energy Efficiency rebates in 4 property owner industry publications.

    - Direct Implementation

      - For Audits and Site Surveys  - Not Applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization

- Total number of customers sites served

- Summary of type and number of measures installed or repaired.

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 139 |
| Building Shell - Insulation | 6,899 |
| HVAC - Controls | 1,500 |
| Water Heating - Systems | 66 |
| Water Heating - Controls | 2 |
| Grand Total | 8,606 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities 
 Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing - 
None

- Additional Items - None

Supporting Documentation

- Marketing Materials – 
Full page ad placed with four Apartment publications

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation- 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
There were no training activities this month

- Trade Shows and Public Event

Pasadena Home and Garden Show