| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Crosscutting Education & Training |
| IOU Service Area: | SCG |
| Program Number: | 1258-04 |
| Program Type: | IOU Statewide Program |
| Month | June-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,672,314 | $151,194 | 4% | $2,654,291 | 72% |  |  | $2,654,291 | 72% | $1,018,023 |
| Admin | $731,664 | $116,684 | 16% | $899,389 | 123% |  |  | $899,389 | 123% | -$167,725 |
| Marketing | $277,000 | $34,510 | 12% | $368,361 | 133% |  |  | $368,361 | 133% | -$91,361 |
| DI | $2,574,650 |  |  | $1,386,541 | 54% |  |  | $1,386,541 | 54% | $1,188,109 |
| EM&V | $89,000 |  |  |  |  |  |  |  |  | $89,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder

| Performance Goal | Current Month’s Achievement | Cumulative Achievement | Remainder |
| --- | --- | --- | --- |
| 137 Seminars | 11 | 85 | 52 |
| 40 HTR Seminars | 9 | 66 | 0 |
| 35 Outreach Events | 2 | 25 | 10 |

| Equipment Demonstrations | # of Demonstrations | # of Attendees |
| --- | --- | --- |
| Food Service | 16 | 168 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include production and distribution of collateral, scheduling and holding classes and seminars, participating in community outreach events, planning for future classes and seminars, community and outreach events, managing of program budgets and expenditures and compiling data to prepare CPUC monthly reports.

    - Marketing

| Collateral | Description | Distribution | PDF File Name |
| --- | --- | --- | --- |
| IHACI – Preventing Compressor Failures/ Refrigeration Cycles (flier) (#13549/50) | Single sheet flier created to provide information on content, location, time, date, and availability for both seminars | 950 produced 750 direct mail (IHACI) 200 manually | 13549 13550 flier.pdf |
| Combustion Seminar - Oxnard (flier) (#13340) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 2,650 produced 2,131 direct mail 519 manually | 13340 flier.pdf |
| CHPS Professional Design Training (e-mail) (#13590) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 4,290 via e-mail | 13590 email.pdf |
| Energy-Efficient Chef: Pan Frying, Sautéing & Deep Frying (flier) (#12798) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 400 produced 400 manually | 12798 flier.pdf |
| Energy-Efficient Chef: Pan Frying, Sautéing & Deep Frying (e-mail) (#12798) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2,734 via e-mail | 12798 email.pdf |
| Exploring Cuisines of the South Pacific (flier) (#12801) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 2,450 produced 2,100 direct mail 350 manually | 12801 flier.pdf |
| Exploring Cuisines of the South Pacific (e-mail) (#12801) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2,734 via e-mail | 12801 email.pdf |
| Chain Accounts (e-mail) (#13576) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | Forwarded by Account Executives to select audience | 13576 STD.pdf |
| Chain Accounts (flier) (#13576) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 2,390 produced 1,560 direct mail 830 manually | 13576 flier.pdf |
| Chain Accounts (e-mail) (#13576) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2,734 via e-mail | 13576 email.pdf |
| IHACI – Preventing Compressor Failures/ Refrigeration Cycles (flier) (#13549/50) | Single sheet flier created to provide information on content, location, time, date, and availability for both seminars | 950 produced 750 direct mail (IHACI) 200 manually | 13549 13550 flier.pdf |
| Combustion Seminar - Oxnard (flier) (#13340) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 2,650 produced 2,131 direct mail 519 manually | 13340 flier.pdf |
| CHPS Professional Design Training (e-mail) (#13590) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 4,290 via e-mail | 13590 email.pdf |
| Energy-Efficient Chef: Pan Frying, Sautéing & Deep Frying (flier) (#12798) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 400 produced 400 manually | 12798 flier.pdf |
| Energy-Efficient Chef: Pan Frying, Sautéing & Deep Frying (e-mail) (#12798) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2,734 via e-mail | 12798 email.pdf |

    - Direct Implementation

The following classes were offered to train and inform the market actors in energy efficient methods and technologies:

| Date | Class Description | Attendees |
| --- | --- | --- |
| 06/07/05 | #12798 – FSEC Downey, CA The Energy Efficient Chef: Pan Frying, Sautéing & Deep Frying Understand the subtle differences between pan-frying, sautéing, and deep fat frying. Techniques discussed will highlight the use of energy-efficient, gas-fired equipment including fryers and ranges. Learn the features and benefits of Energy Star fryers to maximize food quality and increase savings. | 16 |
| 06/07/05 | #13549 – Chatsworth, CA Preventing Compressor Failures/Refrigeration Cycles (1 night class) The most expensive failure in an HVAC system is the compressor. Understanding what causes failures will help to prevent future failures. Proper "superheat" and "subcooling" refrigerant charging will be discussed to optimize system performance and energy efficiency. | 63 |
| 06/08/05 | #12801 – FSEC Downey, CA Exploring Cuisines of the South Pacific The exotic South Pacific is the source of cuisine that includes far more than tropical fruits and fresh seafood. Discover a wide variety of regional and national dishes that make the foods of island locations mouthwatering. Take part in this flavorful experience prepared in front of you on energy-efficient, gas-fired equipment. | 39 |
| 06/14/05 | # 13550 – ERC Downey, CA Preventing Compressor Failures/Refrigeration Cycles (1 night class) The most expensive failure in an HVAC system is the compressor. Understanding what causes failures will help to prevent future failures. Proper "superheat" and "subcooling" refrigerant charging will be discussed to optimize system performance and energy efficiency. | 115 |
| 06/21/05 | #13576 – FSEC Downey, CA Chain Account Expo: Trends of Tomorrow This half-day seminar and mini-expo is developed specifically for chain operators and provides customers an opportunity to view exhibits on the latest products and technologies that can increase energy efficiency and help save on labor costs. Learn about the SoCalGas rebate program for upgrading your operation to energy-efficient, gas-fired commercial food service equipment. | 36 |
| 06/220/05 | # 13340 – Oxnard, CA Combustion Seminar- (Two Day) This seminar provides basic knowledge of gas, gas equipment, combustion and air quality guidelines and the safe and efficient use of gas-fired equipment while focusing on energy efficiency and conservation. | 11 |
| 06/22/05 | # 14182 – Pomona, CA Hands-On HVAC Duct Testing and Sealing Training As a proactive response to the needs of HVAC professionals, The Gas Company is offering hands-on seminars to teach contractors, installers and service technicians how to self-test their work prior to undergoing third party verification for energy-efficient change-outs. These comprehensive one-night classes include an overview of rules and regulations for residential and nonresidential HVAC system change-outs, hands-on duct leakage test demonstrations, and relevant information on how to locate a HERS rater, what forms must be completed for the building department, and more. | 24 |
| 06/28/05/ | #13590 – ERC Downey, CA High Performance Schools: The CHPS Program The Collaborative for High Performance Schools program, or "CHPS", has a purpose to increase the energy efficiency of public schools in California by marketing information, service, and incentive programs directly to school districts and designers. | 53 |
| 06/29/05 | # 14182 – City of Industry, CA Hands-On HVAC Duct Testing and Sealing Training As a proactive response to the needs of HVAC professionals, The Gas Company is offering hands-on seminars to teach contractors, installers and service technicians how to self-test their work prior to undergoing third party verification for energy-efficient change-outs. These comprehensive one-night classes include an overview of rules and regulations for residential and nonresidential HVAC system change-outs, hands-on duct leakage test demonstrations, and relevant information on how to locate a HERS rater, what forms must be completed for the building department, and more. | 18 |

Outreach Events:

| Date | Organization | Event Description | Location |
| --- | --- | --- | --- |
| 06/27/05 | BOMA – Office Building Show | Darrell Brand attended BOMA Tradeshow exploring opportunities to collaborate on energy efficiency focused seminars | Anaheim, CA |
| 06/29/05 | Energy Management Congress | Darrell Brand attended Energy Management conference seeking information on efficiency-focused technologies | San Diego, CA |

      - Audits and Site Surveys  -

- Not applicable to this program

      - Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Not applicable to this program

      - Spending Variance

- No applicable to this program.

      - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
Revised program proposal and workbook filed on April 12, 2004 per the CPUC decision.

- Coordination Activities
Seminars and workshops focusing on commercial and residential new construction co-sponsored with SCG’s “Savings By Design” commercial new construction incentive program, Residential New Construction, and Building Operators Certification (BOC) program. Supporting the development of training and education of the UC/CSU/IOU Partnership program, South Bay Cities Council of Governments and the City of Ventura Resource Centers, and the California Energy Commission’s Best Practices education workshops.

- Changes to Subcontractors or Staffing
None.

- Additional Items 
None

Supporting Documentation

- Marketing Materials –

See 1.2.2

- Point of Purchase Program Documentation –

This program does not have point of purchase activities.

- Free Measure Distribution Documentation –

This program does not distribute free measures.

- Upstream Incentive Documentation –

This program is not an upstream incentive program.

- Training Documentation –

See 1.2.3

- Trade Shows and Public Events –

See 1.2.3