| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1404-04 |
| Month: | July 2005 |

- Program Status

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jul-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $793,490 | -$159 | 0% | $40,927 | 5% | $14,828 | 2% | $55,756 | 7% | $752,563 |
| Admin | $132,026 | -$159 | 0% | $13,030 | 10% | $14,828 | 11% | $27,859 | 21% | $118,996 |
| Marketing | $23,000 |  |  | $2,023 | 9% |  |  | $2,023 | 9% | $20,977 |
| DI | $604,675 |  |  | $25,874 | 4% |  |  | $25,874 | 4% | $578,801 |
| EM&V | $33,789 |  |  |  |  |  |  |  |  | $33,789 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | July-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 5 | 125% | 0 | 0% | 5 | 125% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 1 | 8% | 8 | 75% | 0 | 0% | 8 | 75% | 4 |
| Conduct at least 4 events for residential customers. | 4 | 4 | 100% | 24 | 650% | 0 | 0% | 24 | 650% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 0 | 0% | 26 | 216% | 0 | 0% | 26 | 216% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 15 | n/a | 52 | n/a | 0 | n/a | 52 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

- Team participated in meetings, conference calls and other communication with Partners regarding the existing program and planning for future program

- A new Environmental Deputy was hired during the reporting period

- Team met with IOU Partners to introduce new SBCCOG Environmental Deputy

- Executive staff met with SCE’s Director of Energy Efficiency.

    - Marketing –

SBESC:

- Prepared print ad and published in The Daily Breeze, (circulation 171, 560 households) to promote the July 21st workshop for religious facilities.  The event was also listed in the ‘Out and About’ Calendar section

- Prepared flyer for July 21 special workshops for religious facilities, and sent out personalized invitations to 175 local houses of worship.

- Prepared flyer for each of the three mobile home park trainings and delivered them a week prior to the training dates.

- Prepared articles for SBESC E-Newsletter and SBCCOG newsletter.  Published SBESC E-newsletter June 29.

- Met with Congresswoman Jane Harman’s Field Deputy at SBESC regarding the possibility of hosting an alternative energy expo on August 17

- July 13 Outreach to Torrance Chamber of Commerce Leadership Class of 2005, plus an outreach to the Lawndale Kiwanis.  A total of 32 information kits were given out at these two events.

- Program Manager attended Palos Verdes Peninsula Chamber Breakfast on July 27 to coordinate with West Basin Water District Sr. Engineer.  Met with SCE rep Scott Gobble re collaboration for Pump Training workshop scheduled for August 25.

- Contacted West Basin Water District Director to obtain list of South Bay pump owners for August 25 workshop as well as city representatives regarding possible invitees

- Program Manager was interviewed by Torrance Cable television re “What is SBESC” just prior to a televised residential training conducted by Carmen Oliver at the Tri-League of Women Voters.

- Continue to work with the community to identify outreach opportunities.

    - Direct Implementation

Training

SBESC delivered energy efficiency workshops for residential customers during the reporting period as follows:

    - July 5   - Royal Western Mobile Home Park (MHP), Gardena, CA

    - July 20 - Starlite Mobile Home Park, Torrance, CA

    - July 21 - Gardena Villa Mobile Home Park, Gardena, CA

    - July 28 - Tri-League of Women Voters,  Torrance, CA

The following business training was also delivered:

    - June 22 - Business –Energy Efficiency for Religious Facilities, Torrance, CA

Follow-up for training event included thank you letters and participation certificates. Most attendees rated the events good to excellent.

Energy Resource Center

Staff continues to process requests from telephone callers and visitors to the center in a timely manner.

Energy Efficiency Action Plan

The plan is currently being worked on and a first draft will be completed in time to be incorporated in current program.

      - Audits, Site Surveys and Partnerships - None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization – Not applicable

      - Calculated and Actual Payment Reconciliation - None

    - EM&V

Nothing this month.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

SBCCOG is collaborating with American Synergy Corporation, implementer of the direct install HTR Mobile Home Program to facilitate the mobile home park workshops. At these workshops, reservations are made for installation of energy efficiency measures by American Synergy.

- Changes to Subcontractors or Staffing
None

- Additional Items
None

Supporting Documentation

- Marketing Materials

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| Table E.1 – Training Documentation |
| --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees | Training |
|  |  |  | Type | Number | Date | Location |
| Residential EE Training | Workshop | EE Info | Residents | 57 | Various | Various |
| Religious Facilities Training | Workshop | EE Info | Business | 17 | 7/21/05 | Torrance |

| Table E.2 – Training Events Held |
| --- |
| Event Description | Event |
|  | Location | Date |
| Residential EE Training - Royal Western MHP | Gardena | 7/6/05 |
| Residential EE Training - Starlite MHP | Torrance | 7/20/05 |
| Residential EE Training - Gardena Villa MHP | Gardena | 7/21/05 |
| Residential EE Training - Tri-League of Women Voters | Torrance | 7/28/05 |
| Business EE Training – Religious Facilities | Torrance | 7/21/05 |

- Trade Show and Public Events

| Table F.2 - Trade Show and Public Events, Planned |
| --- |
| Event Description | Event |
|  | Location | Date |
| Torrance Kiwanis | Torrance | 8/2/05 |
| Hawthorne Community Fair | Hawthorne | 8/13/05 |
| Site Visit by The Gas Company | Torrance | 8/15/05 |
| Alternative Energy Expo | Torrance | 8/17/05 |
| Carson Unity Day | Carson | 8/21/05 |
| Pump Owners Workshop | Torrance | 8/25/05 |
| Gardena Jazz Festival | Gardena | 8/28/05 |
| Torrance Rotary | Torrance | 8/31/05 |