| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | September-05 |

- Program Status

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,145,090 | $301,116 | 2% | $9,407,583 | 77% |  |  | $9,407,583 | 77% | $2,737,507 |
| Admin | $1,432,400 | $555 | 0% | $948,656 | 66% |  |  | $948,656 | 66% | $483,744 |
| Marketing | $2,174,790 | $34,180 | 2% | $1,767,621 | 81% |  |  | $1,767,621 | 81% | $407,169 |
| DI | $8,368,900 | $266,381 | 3% | $6,691,306 | 80% |  |  | $6,691,306 | 80% | $1,677,594 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Sep-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,250 | 130 | 3% | 2,988 | 70% |  |  | 2,988 | 70% | 1,262 |
| Annual kWh | 10,766,576 | 280,131 | 3% | 8,509,231 | 79% |  |  | 8,509,231 | 79% | 2,257,345 |
| Lifecyc kWh | 157,409,229 | 4,127,457 | 3% | 118,438,259 | 75% |  |  | 118,438,259 | 75% | 38,970,970 |
| Annual Therms | 4,736,076 | 138,529 | 3% | 4,096,771 | 87% |  |  | 4,096,771 | 87% | 639,305 |
| Lifecyc Therms | 63,299,167 | 1,799,862 | 3% | 51,943,485 | 82% |  |  | 51,943,485 | 82% | 11,355,682 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | September -05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 28% | 121% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative- 
None.

    - Marketing –

- Notification sent out to 351 retailers in SCG’s service territory announcing the re-opening of the 2005 SF rebate program.

- New applications to be re-printed and distributed early October.

- Participated in the 2005 Energy Star Partners Conference in Saratoga Springs, NY.  Met with Energy Star manufacturers and retailers to discuss potential coop opportunities for 2006.

- Met with Viewtech Financial Services to discuss opportunities to provide online rebates for SCG in 2006 none this month.

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 3,132 |
| Building Shell - Insulation | 360,852 |
| HVAC - Controls | 189 |
| HVAC - Heating Systems | 128 |
| Water Heating - Systems | 184 |
| Grand Total | 364,485 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing – Program Manager Assignment has changed

- Additional Items-None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month