| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Single Family Home Energy Efficiency Rebate |
| IOU Service Area: | SCG |
| Program Number: | 1220-04 |
| Program Type: | IOU Statewide Program |
| Month | December-04 |

- Program Status

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $12,314,090 | $368,859 | 3% | $4,451,630 | 36% |  |  | $4,451,630 | 36% | $7,862,460 |
| Admin | $1,432,400 | $62,136 | 4% | $395,727 | 28% |  |  | $395,727 | 28% | $1,036,673 |
| Marketing | $2,174,790 | $19,417 | 1% | $280,817 | 13% |  |  | $280,817 | 13% | $1,893,973 |
| DI | $8,537,900 | $287,306 | 3% | $3,775,086 | 44% |  |  | $3,775,086 | 44% | $4,762,814 |
| EM&V | $169,000 |  |  |  |  |  |  |  |  | $169,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 3,073 | 57 | 2% | 895 | 29% |  |  | 895 | 29% | 2,178 |
| Annual kWh | 9,518,688 | 1,009,474 | 11% | 3,981,433 | 42% |  |  | 3,981,433 | 42% | 5,537,255 |
| Lifecyc kWh | 132,451,464 | 11,577,100 | 9% | 50,824,964 | 38% |  |  | 50,824,964 | 38% | 81,626,500 |
| Annual Therms | 4,453,873 | 534,900 | 12% | 2,012,332 | 45% |  |  | 2,012,332 | 45% | 2,441,541 |
| Lifecyc Therms | 57,655,114 | 6,008,625 | 10% | 23,973,262 | 42% |  |  | 23,973,262 | 42% | 33,681,852 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | December -04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 23% of rebate applications come from HTR zip codes | 23% | 28% | 121% |  |  |  |  | 28% | 121% |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative  - 
Regular monthly administrative activities include but are not limited to the following activities:  three calls with CA statewide Single Family team to revise the customer application for 2005.  Internally developed talking points addressing year-end transition to address customer submitted applications.  Conducting year-end program budgets and expenditure review and reconciliation.

    - Marketing

    - No new marketing to report.

    - Direct Implementation

      - For Audits and Site Surveys :N/A

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Total number of customers sites served, 1,522

- Summary of type and number of measures installed or repaired

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 1,555 |
| Building Shell - Insulation | 151,919 |
| HVAC - Controls | 5,949 |
| HVAC - Heating Systems | 77 |
| Water Heating - Systems | 100 |
| Grand Total | 159,600 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance - SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing - 
None

Additional Items -  For monthly reporting purposes, the Recorded Activities worksheet only includes projects, which have been installed, not those that are “committed”. For purposes of projecting funding availability, and determining measure closures however, SoCalGas considers both installed and committed categories in order to best assess remaining funding availability

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
None this month

- Free Measure Distribution Documentation-  
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
None this month

- Trade Shows and Public Events – 
None this month