| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential New Construction Savings By Design |
| IOU Service Area: | SCG |
| Program Number: | 1249-04 |
| Program Type: | IOU Statewide Program |
| Month | March-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Mar-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,621,150 | $78,305 | 2% | $3,051,911 | 66% |  |  | $3,051,911 | 66% | $1,569,240 |
| Admin | $600,433 | $21,670 | 4% | $392,910 | 65% |  |  | $392,910 | 65% | $207,523 |
| Marketing | $302,772 | $8,964 | 3% | $234,994 | 78% |  |  | $234,994 | 78% | $67,778 |
| DI | $3,564,795 | $47,671 | 1% | $2,424,007 | 68% |  |  | $2,424,007 | 68% | $1,140,789 |
| EM&V | $153,150 |  |  |  |  |  |  |  |  | $153,150 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Mar-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,367 | 60 | 1% | 2,804 | 64% |  |  | 2,804 | 64% | 1,563 |
| Annual kWh | 22,628,534 | 692,644 | 3% | 13,406,219 | 59% |  |  | 13,406,219 | 59% | 9,222,316 |
| Lifecyc kWh | 339,428,011 | 10,389,662 | 3% | 201,093,278 | 59% |  |  | 201,093,278 | 59% | 138,334,733 |
| Annual Therms | 296,194 | 2,809 | 1% | 182,465 | 62% |  |  | 182,465 | 62% | 113,729 |
| Lifecyc Therms | 4,442,904 | 42,140 | 1% | 2,736,971 | 62% |  |  | 2,736,971 | 62% | 1,705,933 |

Currently, the formulas in the workbook do not allow us to accurately portray activity.  The savings will be updated once the formulas have been corrected.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

- Participated in the Building Evaluation Assessment (BEA) conference call where the New Construction Potential Study and baseline analysis was discussed with a consultant and the Statewide Savings By Design (SBD) Team.

- Attended the SoCalGas HRAC (Heating Refrigeration Air Compression) team meeting to discuss closer coordination between Savings By Design and the Major Markets group.

- Met with Quantum Consultants to discuss a strategy and approach for wastewater treatment projects in both the Edison territory as well as the municipal electric utility territories.

- Attended a Major Markets staff meeting to discuss a strategy for getting more industrial projects into the Savings By Design program.

    - Marketing

- Made a presentation and represented Savings By Design at ERC seminar; “Cool Roofs.”

- Participated in various CHPS (Collaborative for High Performance Schools) meetings including the Finance Committee conference call to discuss the upcoming program plan and budget.  Began reviewing the updated CHPS Best Practices Manuals.

    - Direct Implementation

- Continued to coordinate and give direction to the Commissioning consultant regarding the LAUSD Cahuenga Elementary School.

- Attended the LACCD/LAUSD/City of LA Sustainability Collaborative.  Topic of discussion was sustainability in historical renovation projects.  The speaker was, John Lesak, Senior Associate with WJE Architects and Engineers, Co-Chair of the Association for Preservation Technology's technical committee on Historic Preservation and Sustainability.

- Attended the CA Manufacturing Technology Consulting Energy Savings Strategies seminar and met with customers who are interested in making their manufacturing processes more energy efficient.

- Met with David Mora of Mayor Hahn’s office.  Discussed projects that the mayor’s office is working on and introduced staff there to Savings By Design and what we have to offer for their projects.

- Attended HVAC Design and Procurement for Energy Efficiency seminar.  This seminar was sponsored by the UC/CSU/IOU Partnership; discussed energy efficient HVAC design for campus facilities staff.

- Met with Fatburger Corporate to discuss what Savings By Design can offer.  Discussed how VAV kitchen hoods can optimize energy efficiency in their commercial kitchens.

Training Documentation

| Training Description | Location – City | Audience | # of Attendees | SBD Presentation? Y or N | Materials Disseminated |
| --- | --- | --- | --- | --- | --- |
| Schools – CHPS presentation | Los Angeles | ASHRAE SoCal Chapter | 50 | Y | 50 Brochures |
| Commercial Kitchen Ventilation | Downey | ERC Seminar | 35 | N | 28 Brochures |
| CA Manufacturing Technology Consulting Energy Savings Strategies Seminar | Garden Grove | Industry seminar | 25 | Y | 25 Brochures 25 1-pagers |
| HVAC Design and Procurement for Energy Efficiency | Irvine | UC/CSU/IOU Partnership | 25 | Y | 30 Brochures |
| Kitchen energy efficiency for Fatburger facilities | Santa Monica | Fatburger | 4 | Y | 4 Brochures 4 1-pagers |
| Projects with Mayor Hahn’s Office of Economic Development | Los Angeles | Mayor Hahn’s Office | 10 | Y | 10 |

Trade Show and/or Public Events

- Made a presentation on CHPS (Collaborative for High Performance Schools) and Savings By Design as the main speaker for the March monthly Southern California Chapter of the ASHRAE meeting.  The presentation included the proposed changes that the CHPS Technical Subcommittee is proposing.

      - Audits and Site Surveys

Not applicable to this program

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable to this program

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SDG&E pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
None

- Coordination Activities
Cooperated and coordinated efforts for promoting various energy efficiency programs provided by SoCalGas.

- Changes to Subcontractors or Staffing

None

- Additional Items

Updated Tab 7 to reflect subcontractor costs incurred in previous months.

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
No training seminars were held this month.

- Trade Shows and Public Events – 
None this month.