| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Crosscutting Education & Training |
| IOU Service Area: | SCG |
| Program Number: | 1258-04 |
| Program Type: | IOU Statewide Program |
| Month | January-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,672,314 | $142,356 | 4% | $1,872,102 | 51% |  |  | $1,872,102 | 51% | $1,800,212 |
| Admin | $731,664 | $41,954 | 6% | $564,727 | 77% |  |  | $564,727 | 77% | $166,937 |
| Marketing | $277,000 | $29,621 | 11% | $249,421 | 90% |  |  | $249,421 | 90% | $27,579 |
| DI | $2,574,650 | $70,781 | 3% | $1,057,954 | 41% |  |  | $1,057,954 | 41% | $1,516,696 |
| EM&V | $89,000 |  |  |  |  |  |  |  |  | $89,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goal | Current Month’s Achievement | Cumulative Achievement | Remainder |
| --- | --- | --- | --- |
| 137 Seminars | 16 | 16 | 121 |
| 40 HTR Seminars | 13 | 13 | 27 |
| 35 Outreach Events | 1 | 1 | 34 |

| Equipment Demonstrations | # of Demonstrations | # of Attendees |
| --- | --- | --- |
| Food Service | 12 | 68 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include production and distribution of collateral, scheduling and holding classes and seminars, participating in community outreach events, planning for future classes and seminars, community and outreach events, managing of program budgets and expenditures and compiling data to prepare CPUC monthly reports.

This month, additional activities included:

- Program Managers attended meetings to review and understand CPUC reporting requirements for 2004.

- Complied data to prepare monthly reporting to CPUC

    - Marketing

| Collateral | Description | Distribution | PDF File Name |
| --- | --- | --- | --- |
| FSEC 2005 Calendar | 11X17 two-sided, calendar created to provide information on annual seminar content, time, date, and location | 30,000 produced 21,835 via direct mail 594 manually | 2005 FSEC Calendar.pdf |
| FSEC 2005 Calendar – Joint Energy Center Events | Single sheet calendar created to provide information on seminar content, time, date, and location | 500 produced 500 manually | 2005 JEC Food Service Calendar.pdf |
| ERC 1st Quarter 2005 Calendar | 11X17 two-sided, calendar created to provide information on 1st Quarter seminar content, time, date, and location | 12,000 produced 7,048 via direct mail 2,952 manually | SCG 2005 1st Qtr Calendar.pdf |
| Title 24 Calendar – Winter/Spring | 11X17 folding calendar created to provide information on Winter/Spring seminar content, time, date, and location | 11,925 produced 10,075 via direct mail 1,850 manually | SCG 2005 T24 Winter Spring Calendar.pdf |
| IHACI – Installation Best Practices – Parts I & II (#13069/70/71/72) | Single sheet flier created to provide information on seminar content, time, date, location, and availability for all seminars | 900 produced 750 direct mail (IHACI) 150 manually | 13069 13070 13071 13072 flier.pdf |
| Lighting the Electronic Office (flier) (#12975) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 900 produced 652 direct mail 248 manually | 12975 flier.pdf |
| Non-Res Fenestration – Architects & Specifiers / Glazing Contractors (flier) (#10362/63/64/64) | Single sheet flier created to provide information on seminar content, time, date, location, and availability for both seminars | 925 produced 776 direct mail 149 manually | 13062 13063 13064 13065 flier.pdf |
| (JEC) Equipment Selection for Savings & Success (flier) (#12767) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 3,750 produced 3,553 direct mail 197 manually | 12767 flier.pdf |
| (JEC) Equipment Selection for Savings & Success (e-mail) (#12767) | Electronic-mail campaign created to link to website, providing information on seminar content, time, date, location and availability | 2,744 via e-mail | Link to web registration only |
| Boost Your Profits in 2005 (flier) (#12768) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 3,750 produced 3,553 direct mail 197 manually | 12768 flier.pdf |
| Boost Your Profits in 2005 (e-mail) (#12768) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 3,224 via e-mail | 12768 email.pdf |
| Indoor Comfort News – IHACI Seminar Ad | Full-page advertisement in HVAC industry-focused monthly periodical, created to provide information on seminar content, time, date, location | Insert in publication | January 2005 ICN Ad.pdf |

    - Direct Implementation

The following classes were offered to train and inform the market actors in energy efficient methods and technologies:

| Date | Class Description | Attendees |
| --- | --- | --- |
| 01/04/05 | #13069 – Chatsworth, CA Installation Best Practices (Part I) This two-part seminar explains how the simple approach can often be the best course of action. Discussion will cover timesaving tips, cost control and energy-efficient techniques and technologies, and even ways to best work with consumers. Emphasis: Equipment Selection and Installation | 31 |
| 01/06/05 | # 13070– Chatsworth, CA Installation Best Practices (Part II) Note: Attendance of Part I is a prerequisite for attending Part II. This two-part seminar explains how the simple approach can often be the best course of action. Discussion will cover timesaving tips, cost control and energy-efficient techniques and technologies, and even ways to best work with consumers. Emphasis: Tight Ducts, Air Filtration Systems, Proper Sealing and Accessories | 18 |
| 01/11/05 | # 13071– ERC Downey, CA IHACI - Installation Best Practices (Part I) This two-part seminar explains how the simple approach can often be the best course of action. Discussion will cover timesaving tips, cost control and energy-efficient techniques and technologies, and even ways to best work with consumers. Emphasis: Equipment Selection and Installation | 77 |
| 01/12/05 | # 12975 – ERC Downey, CA Lighting the Electronic Office A half-day, intermediate level, interactive workshop designed to explore "Ergonomic Lighting", or lighting that is not only energy-efficient, but also considers the physical and psychological needs of people working in office buildings. This workshop also addresses the added lighting complexities associated with the implementation of electronic presentations and video conferencing. | 13 |
| 01/12/05 | # 13347 – Bakersfield, CA Combustion Seminar for Residential Appliances, Housing Authority, HIA This is a residential appliance seminar for the Bakersfield Housing Authorities' maintenance group. The seminar is an overview of combustion safety, equipment maintenance and energy efficiency issues regarding gas appliances found in single family homes or multi-family dwellings. | 33 |
| 01/13/05 | # 13072 – ERC Downey, CA Installation Best Practices (Part II) Note: Attendance of Part I is a prerequisite for attending Part II. This two-part seminar explains how the simple approach can often be the best course of action. Discussion will cover timesaving tips, cost control and energy-efficient techniques and technologies, and even ways to best work with consumers. Emphasis: Tight Ducts, Air Filtration Systems, Proper Sealing and Accessories | 64 |
| 01/13/05 | # 13346 – Wasco, CA Boiler and Dryer Seminar, California State Prison Authority This is a boiler and commercial dryer seminar for the California State Prison System's maintenance group at Wasco. The seminar is a overview of combustion safety, equipment maintenance and energy efficiency issues. | 19 |
| 01/13/05 | #13035 – FSEC Downey, CA CaptiveAire Ventilation Systems This seminar will point out the importance of selecting the appropriate ventilation equipment for food service operations. Doug Horton, from CaptiveAire Systems, Inc, will point out features to consider when choosing a system, such as: flow rates, make-up air source and controls, price vs. operating costs over time, clearance guidelines, etc.. Included will be a demonstration of a CaptiveAire ventilation system installed in the FSEC Ventilation and Bake Lab. | 64 |
| 01/19/05 | # 13047 – Redlands, CA ACCA Manual J - Introduction Overview of changes to the Residential Energy Standards in order to optimize energy efficiency performance. Class covers GRI guidelines for sizing and installing combo systems, duct system testing and radiant barrier roof sheathing | 22 |
| 01/20/05 | # 12767 FSEC Downey, CA Equipment Selection for Savings & Success (JEC) When buying new or replacing commercial kitchen gas equipment, your decisions can make a huge impact on the success of the operation. Does investing a bit more up front for energy-efficient equipment really pay off in the long run? Get the facts at this informative seminar. | 48 |
| 01/20/05 | # 13053 – Redlands, CA ACCA Manual D Introduction Focus will be on designing residential duct systems according to ACCA Manual D specifications to optimize HVAC system energy-efficient performance. | 19 |
| 01/20/05 | # 13062 – ERC Downey, CA Non-Residential Fenestration Certification (NFCI) – Architects/Specifiers Architects will be provided with the technical expertise needed to comply with the new 2005 Title 24 energy efficiency standard requirements for NFRC labeling of site-built fenestration products. | 10 |
| 01/20/05 | # 13063 – ERC Downey, CA Non-Residential Fenestration Certification (NFCI) - Glazing Contractors When the owner and architect is not the "responsible party" for a particular building project, C-17 contractors are responsible for the NFRC site-built certification glazing systems. This session offers C-17 contractors the knowledge and technical skill set necessary to become a "responsible party", and comply with the new 2005 Title 24 energy efficiency standard requirements for NFRC labeling of site-built fenestration products. | 2 |
| 01/21/05 | # 13108 – Redlands, CA 2005 Energy Standards Update/High Performance Ducts Oriented toward builders, HVAC contractors and engineers, this section will review current and 2005 changes to the Residential Energy Standards. Class topics will also include: High performance glazing, radiant barrier roof sheathing, "Hands-on" duct testing and demonstration, and Home Energy Rating System (HERS) verification process. | 27 |
| 01/25/05 | # 12908 - ERC Downey, CA Department Of Energy (DOE) Steam Specialist Training The DOE Steam Software Specialist, Department of Energy Steam Assessment Software Training. This three-day training and exam is co-sponsored by the California Energy Commission, the US Government Department of Energy (DOE), and The Gas Company. The operation of typical boiler steam systems, methods of system assessment, and efficiency improvement will be covered in this class. This information can also be very valuable to industrial and institutional plant personnel such as energy managers, supervisors, engineers, and equipment operators. | 18 |
| 01/26/05 | # 12768 FSEC Downey, CA Boost Your Profits in 2005 This engaging seminar will be jam-packed with refreshing new concepts to kick off the New Year! Gain essential tips from Dr. A. Elizabeth Sloan, our dynamic keynote speaker, plus three more great presentations on performance coaching, profitable menus and energy efficiency, and state-of-the-art temperature control. | 51 |

Outreach Events:

| Date | Organization | Event Description | Location |
| --- | --- | --- | --- |
| 01/12/05 | Southern California Section - Institute of Food Technologists | Executive Chef Jill Bosich judged student competition at the SCIFTS 18th Annual Southern California Food Industry Conference, “Functional Foods & Dysfunctional Promises: A Critical Look” | Chapman College, Orange, CA |
| 02/08/05-02/10/05 | World AG Show, LJB | This organized, centrally located show will provide an opportunity to display energy efficiency-focused agriculture products, services, and equipment to an interested audience of farmers - serious, potential buyers. Attendees will view the latest technology, and agricultural equipment including the latest energy efficient water pumping and food processing equipment and services. | Tulare, CA |
| 02/25/05 | Los Angeles Mission College | Food Service Equipment Center Supervisor Melisa Marks will appear as an invited speaker and panel discussion member before “New Happenings in Tech Prep”, a seminar by the college’s Culinary Arts Department. | Los Angeles Mission College, Sylmar, CA |

      - Audits and Site Surveys: Not applicable

      - Direct Installations, Rebates, Equipment Maintenance and Optimization: Not applicable

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons: Not applicable

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
Revised program proposal and workbook filed on April 12, 2004 per the CPUC decision.

- Coordination Activities
Seminars and workshops focusing on commercial and residential new construction co-sponsored with SCG’s “Savings By Design” commercial new construction incentive program and Residential New Construction. Supporting the development of training and education of the UC/CSU/IOU Partnership program, South Bay Cities Council of Governments and the City of Ventura Resource Centers, and the California Energy Commission’s Best Practices education workshops.

- Changes to Subcontractors or Staffing
None.

- Additional Items 
None

Supporting Documentation

- Marketing Materials –

See 1.2.2

- Point of Purchase Program Documentation –

This program does not have point of purchase activities.

- Free Measure Distribution Documentation –

This program does not distribute free measures.

- Upstream Incentive Documentation –

This program is not an upstream incentive program.

- Training Documentation –

See 1.2.3

- Trade Shows and Public Events –

See 1.2.3