| Program Name: | Multi Family Energy Efficiency Retrofit Program |
| --- | --- |
| Program Number: | SCG3510 |
| Quarter: | Second Quarter 2006 |

- Program description:

The Multi Family Energy Efficiency Retrofit (MFEER) Program is a statewide program that targets property owners and managers of multifamily residential dwellings, homeowner’s associations and mobile home park associations.  The program encourages property owners and managers to install qualifying energy efficiency products in common areas for residential apartments, mobile home parks and condominium complexes.  The program is designed for flexibility; it offers agreed upon statewide measures for coordinated implementation, but is designed to easily adapt to market changes, including adding new measures that may emerge as cost effective opportunities in the SoCalGas local service area.

- Administrative activities:

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.  In addition:

- Printed 2006 Multifamily Rebate applications as necessary.

- Updated SoCalGas’ 2006 Multifamily rebate web page to remove information and quick link to registration for 6/6/06 Seminar and Expo.

- Ongoing communication with Processing and Inspection group to ensure correct application of 2006 program procedures.

- Attended EE Replacement Demo for online rebate application and processing system.

- Continued participation and review of scope of work for joint 3rd Party Program with SCE, for Coin Op Laundry program.

- Continued participation in weekly Statewide IOU Multifamily Rebate Team conference calls.

- Statewide Team members held two Contractors Meetings; San Francisco, 4/24/06 and Downey on 5/8/06.  Meeting agenda focused on educating contractors that participate in SW MF Rebate Programs on issues relating to program status, processing and customer satisfaction related with products and services provided by contractors.

- Onsite meeting with boiler manufacturer representatives to review large installation project.

- Provided training to SCG’s Customer Services Field Operations group regarding Residential Customer Programs, with an emphasis on Multifamily Rebate Program on June 15, 2006.

- Marketing activities:

- 2006 Multifamily Rebate Application and information posted to SoCalGas’ web site in English and Spanish languages.

- Application may be downloaded via the web site or requested via SCG Residential Marketing Department.

- Produced Energy Efficiency Seminar and Expo 6/6/06: ‘Hot Water Solutions for Multifamily Properties’ attended by nearly 100 participants and vendors.  Keynote speaker from the California Energy Commission and speakers from equipment manufacturers provided customers with pertinent information on saving energy on their hot water distribution systems.

- Internal communication piece in Sempra Energy Daily News article highlighted 6/6/06 Seminar and Expo.

- Participated in the Apartment Owners Association of California Million Dollar Tradeshow, 5/18/06; was attended by approximately 800 people.

- Distributed multifamily applications, tri-fold program description brochures, and June 6th seminar/expo invitations during the AOA of CA Million Dollar Tradeshow, 5/18/06.

- Attended the Affordable Housing Management Association Expo 5/22/06, networking with industry professionals.

- Collaborated with SCG Outreach Advisor to target marketing efforts at two partnership programs:  Ventura County Regional Energy Alliance and South Bay Cities Council of Governments.  1000 MF Program Brochures detailing program description, eligible measures and instructions for customer participation were distributed.

- Residential Rebate Brochure, detailing rebate and home energy survey programs was created for future distribution at outreach events.

- Direct implementation activities:

- California’s ‘Flex Your Power’ e-Newswire promoted the Hot Water Solutions for Multifamily Properties seminar and expo in the 4/18/06 edition.

- Launched a Direct Mail campaign to approximately 3000 owners of multifamily properties to attend the 6/6/06 Seminar and Expo.

- Approximately 1000 Hot Water Solutions Seminar fliers were delivered to customers in SoCalGas service territory via tradeshow and outreach participation during second quarter.

- Ongoing random inspections of installed rebate measures as required per program specifications.

- Attended 5th Annual Green Building Conference; 4/20/06

- Attended Multifamily Buildings 2006 Conference, New York 6/25/06 -6/28/06, making key contacts with industry professionals.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

379 requests for reservations have been received for 2006 Multifamily Rebate Program through June 30, 2006.  47% of the incentive goal as been reserved, committed or paid, and the program has achieved 45% of therm goal.  Currently, program is on target.

- Program achievements (non-resource programs only):

- N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- Continued marketing strategy with emphasis on attending Apartment Association Tradeshows 1st and 2nd quarter and cultivating relationships in the industry.

- Continued to work with controller contractors to encourage installation of controls in older, pre 1970 multifamily buildings.

- Will investigate potential to market SCG MF Rebate program to U.S. Department of Housing and Urban Development.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

Program Manager will continue to provide internal training to SCG Customer Service Field Supervisors and will investigate potential pilot program for Residential Energy Efficiency education rollout to field personnel.

Program Manager will attend Apartment Association meetings and develop associations with key contacts.

Will continue to attend Multifamily Tradeshows as necessary.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts,

- None, Contact is Joy Yamagata

- Changes to contractors and contractor responsibilities, if any

- N/A

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.