| Program Name: | Single Family Energy Efficiency Retrofit program |
| --- | --- |
| Program Number: | SCG3517 |
| Quarter: | Second Quarter 2006 |

- Program description

The Single Family Energy Efficiency Retrofit (SF) program is an existing statewide program designed to help Southern California Gas Company (SoCalGas) residential customers reduce their natural gas energy usage by replacing inefficient appliances with new energy-efficient appliances and weatherizing their homes.  The program contains elements such as traditional customer incentives, point of sale (POS) rebates, customer information and education and marketing and outreach, using trade allies, manufacturers, retailers and distributors to deliver information, measures and rebates.  It offers agreed upon statewide measures with coordinated implementation, and is designed to be able to segregate, and add new measures for tailoring to a specific market opportunity that emerges in the SoCalGas local service area.

- Administrative activities

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.  In addition:

- Coordinated development and printing of the single family rebate applications

- Updated SoCalGas’ 2006 Single Family rebate web page

- Coordinated communications to retailers related to updates associated with the single family rebate program.

- Coordinated translation of rebate materials into Spanish

- Updated processing procedures to reflect changes to the rebate program.

- Met with Processing group, Energy Information Center group and Inspections group to review 2006 program measures and changes.

- Participated in meetings with local and chain retailers to discuss point of sale opportunities at their locations.

- Updated customer disqualified and customer incomplete letters for the 2006 rebate program.

- Updated processing procedures to reflect participation and qualification criteria.

- Drafted a point-of-sale agreement for retailers and coordinated legal department review and approval.

- Sent invitation for retailers to participate in SoCalGas’ point-of-sale instate rebates to over 300 appliance retailers in SoCalGas’ service territory.

- Participated in drafting a scope of work for online rebate application and processing.  Participated in the review process until a finished product is available for launch.

- Reviewed program information provided to Flex You Power for their web posting.

- Marketing activities

- 2006 Single Family rebate information updated on SoCalGas’ web site.  2006 SF application also available on SoCalGas’ web site and by request through our Energy Information Center.

- June/July issue of the Gas Company newsletter had an article promoting the 2006 SF rebate program

- 2006 Single Family rebates and Home Energy Upgrade Finance program funded by Fannie Mae mention and advertised in the April edition of California Homeowner Magazine distributed to the League of American Homeowner’s 20,000 members.

- 2006 single family signage and point of sale instant rebate signage was developed for distribution to all participating retailers.

- SoCalGas’ outreach group participated in events such as Earth Day at the LA Zoo, Hawthorne Earth Day Festival, Boeing Earth Day Festival, Raytheon event handing out 2006 SoCalGas single family rebate applications.

- Direct implementation activities

- 2006 SF rebate applications and signage were delivered to over 300 retailers in SoCalGas’ service territory thorough our contractor field representative.

- With the help from SDG&E, planned a joint RFP seeking an outside vendor to provide rebate application processing and online rebate application services.

- 6 local retailers are participating in the point of sale instant rebate campaign providing SoCalGas customers with an instant rebate on qualifying clothes washers, dishwashers or natural gas water heaters.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain

15,161 rebate applications have been received through June 30, 2006. 28% of incentive budget has been spent and program is at 18% of therm goal.  Although the second quarter has been slow, the upcoming seasonal summer promotions and point of sale instant rebates should boost participation.

- Program achievements (non-resource programs only):

- None

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- Expanded point of sale rebates on high efficiency clothes washers, high efficiency dishwashers and natural gas water heaters offered to local retailers.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Point of sale participation for retailers selling high efficiency clothes washers, high efficiency dishwashers and natural gas water heaters expected to increase.  SoCalGas is in discussions with big box retailers that may participate.

- Changes to staffing and staff responsibilities, if any

- N/A

- Changes to contracts,

- None, Contact is Joy Yamagata

- Changes to contractors and contractor responsibilities, if any

- None

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.