| Program Name: | Single Family Energy Efficiency Retrofit program |
| --- | --- |
| Program Number: | SCG3517 |
| Quarter: | Fourth Quarter 2006 |

- Program description:

The Single Family Energy Efficiency Retrofit (SF) Program is an existing statewide program designed to help Southern California Gas Company (SoCalGas) residential customers reduce their natural gas energy usage by replacing inefficient appliances with new energy-efficient appliances and weatherizing their homes.  The program contains elements such as traditional customer incentives, point of sale (POS) rebates, customer information and education and marketing and outreach, using trade allies, manufacturers, retailers and distributors to deliver information, measures and rebates.  It offers agreed upon statewide measures with coordinated implementation, and is designed to be able to segregate, and add new measures for tailoring to a specific market opportunity that emerges in the SoCalGas local service area.

- Administrative activities:

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.  In addition:

- Continued communications to retailers related to updates associated with the single family rebate program.

- Updated processing procedures to reflect changes to the point of sale instant rebate program.

- Continued discussions with local and chain retailers to recruit new point of sale retailers.

- Coordinated statewide meeting to discuss changes and new measures for the 2007 residential program.

- Continued talks with an outside vendor for online rebate application and processing for 2007.  Participated in the review process until a finished product is available for launch.

- Reviewed and provided feedback on preliminary work for online rebate application.

- Continued discussions with Costco and Best Buy retailers to discuss the possibility of offering a point of sale instant rebate on qualified appliances.

- Participated in conference calls with CEE appliance committees.

- Provided Energy Star and CEE with program summaries for their upcoming partner meetings.

- Attended ‘Program Builder’ demonstration and training.

- Attended various meetings with marketing and outreach to discuss advertising opportunities for the rebate program.

- Evaluated program progress year-to-date to assess needs for 2007.

- Marketing activities:

- Continued discussions with members of Energy Star to discuss possibilities of a targeted Energy Star dishwasher campaign to the Hispanic market and non-dishwasher users in our service territory.

- Continued discussions with Lowe’s to discuss potential opportunities for point of sale participation in 2007.

- Met with LADWP to discuss potential opportunities for cross-promotion between both utilities.

- Continued Home Depot promotion related to the point of sale instant rebates on qualified clothes washer, dishwasher, or natural gas water heater.  Customers can participate to win a monthly Home Depot gift card.

- Met with tankless water heater manufacturers to discuss the possibility of offering a residential retrofit tankless water heater rebate for 2007.

- Met with Energy Star to discuss the possibilities of creating a pilot program focusing on high end Energy Star efficient appliances.

- Direct implementation activities:

- In collaboration with SDG&E, continued discussions with an outside vendor to provide rebate application processing and online rebate application services for 2007.

- Continued recruiting efforts of local retailers to participate in the point of sale instant rebate campaign providing SoCalGas customers with an instant rebate on qualifying clothes washers, dishwashers or natural gas water heaters.

- Updated processing procedures to reflect changes and additional measures for the 2007 residential rebate program.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

37,375 rebate applications have been received through December 31, 2006.  77% of incentive budget has been spent and program is at 41% of therm goal.  .  Applications received from the 2006 program is lower compared to the previous year’s programs.

- Program achievements (non-resource programs only):

None

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- Discontinue rebates on 90% AFUE natural gas furnaces.

- Addition of new measures which include faucet aerators, low flow showerheads and pipe wrap for 2007.

- Addition of tankless water heater rebate (via the manufacturers) for 2007.

- Expanded point of sale rebates on high efficiency clothes washers, high efficiency dishwashers and natural gas water heaters offered to local retailers.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Increase point of sale participation for retailers selling high efficiency clothes washers, high efficiency dishwashers and natural gas water heaters.  Continue discussions with non-participating big box retailers to offer point of sale instant rebates.

- Focus promotions on faucet aerators, low flow shower heads, pipe wrap and residential retrofit tankless water heaters.

- Minimize application processing time by focusing on point of sale instant rebates and online applications.

- Work with contractors on offering point of sale instant rebates on insulation, tankless water heaters and other contractor installed measures.

- Partner with municipalities and local water utilities to cross promote residential rebate program for 2007.

- Changes to staffing and staff responsibilities, if any:

None

- Changes to contracts:

None

- Changes to contractors and contractor responsibilities, if any:

None

- Number of customer complaints received:

None

- Revisions to program theory and logic model, if any:

None