| Program Name: | Coin Op Laundry Program |
| --- | --- |
| Program Number: | SCG3540 |
| Quarter: | Fourth Quarter 2006 |

- Program Description:

The primary goal of the program is to promote the installation of Energy Star equivalent standards for commercial-grade clothes washers to replace inefficient commercial clothes washer’s as served by gas or electric water heaters in high-usage Laundromats, institutions and multifamily facilities.

The energy savings will be achieved by providing appropriate rebates and education on overall energy and water savings to property managers and owners, equipment manufacturers and residential and small commercial leasing companies to facilitate the replacement and early retirement of existing leased or company owned equipment. Additional energy savings will be achieved concurrently by installing pipe wrap and lighting measures.  The program shall market and provide outreach approaches to bring multiple decision makers and stakeholders together to facilitate energy efficiency actions in the commercial washer industry. The primary decision makers and stakeholders this program will include the following types of customers:

- Owners or Leasers of commercial clothes washers at Laundromat, institutions and multi family property managers and owners;

- Commercial washer leasing companies; distributors and route operators;

- Commercial washer equipment manufacturers; and

- Water agencies, municipalities and companies serving Southern California Gas Company (SCG) & Southern California Edison (SCE)

- Administrative Activities

During the 4th Quarter 2006, the Commercial Laundry Administrative Team continued their meetings with the companies who lease or finance commercial washers to the end-use customers. In addition, we continued to meet with the many water agencies and water districts within the SCG-SCE service area. Thanks to SCG for hosting a November 28 kickoff meeting involving all principal utilities (SCG, SCE and Metropolitan Water District (MWD). The focus of the meeting was how best to achieve program goals through collaboration and communications. This meeting was also attended by Honeywell and many member of the Commercial Laundry Team.

During the 4th quarter, SCG and UCONS executed a final protocol and agreement to conduct an evaluation of energy savings of commercial washers at a number of end-user site locations. The evaluation will be conducted by an independent national lab, Battelle PNNL. The schedule for initiating the evaluation activities may be delayed a few weeks as the commercial washers to be evaluated under this program will not be installed to allow sufficient time to complete the early phase of evaluations by April.

There are many separate steps required to qualify a customer for the separate rebates and to get the rebate payments sent to the qualifying customer. Systems and database systems have been developed to meet the separate requirements of the customers and the multiple utilities. Our team has been active in developing protocols, data systems, process flow, marketing materials and putting people in place to address these requirements.

Team members continued to meet and conference on a regular basis to review issues, identify problems and solutions, to review goals and report accomplishments.

- Marketing Activities

Marketing activities were reviewed during the 4th quarter in recognition of the significant changes in CEE Tier MEF requirements for 2007. The Commercial Laundry Outreach Team members continued to work diligently with distributors and route operators to establish in house sales training meetings.  These activities will be continued in 2007, but marketing efforts will be expanded in 2007 to include the following activities:

  - training and education of property managers and property management associations

  - working collaboratively with current utility programs (and third party programs) to promote program benefits to all customer sectors

Concluded a contract with Honeywell to enable the SCG-SCE Coin-Op Laundry Program (CLP) to interface with the MWD “Save Water Save a Buck” rebate program. This activity will enhance bringing water and energy rebates together.  MWD will be contacting all of their qualified customers to let them know that energy rebates are available as well.

The CLP website was maintained and updated for the purpose of marketing the program.  On the website a customer will find all the information they will need to participate, and they will be able to apply online for washer rebates.

- Direct Implementation Activities

As of Dec 31, 2006 the CLP completed the application process and 100% inspection of 290 sites with 1375 efficient commercial washers (gas water heating) and 12 efficient washers (with electric water heating).  This represents a very quick start to the program having officially started near the end of August.

- Program Performance/Program Status

As of December 31, 2006 the CLP has received a total of 614 applications for a total number of 3738 high efficient washers (gas water heating) and 15 applications representing 51 commercial washers (electric water heating). SCE has provided a targeted list of potential (electric water heating applications) which will be used to increase the number of commercial washers going into electric water heating facilities.

- Program Achievements

During the 4th Quarter of 2006 we had a large number of applications submitted and successfully achieved meeting with the major water agencies to meet program goals for combining water and energy program benefits. We were also to meet with all major route operators and distributors who deliver and service commercial washers in the commercial laundry market.

We have brought water and energy together by combining rebates with Metropolitan Water District and the Save-A-Buck program.

- Changes in program emphasis, if any, from previous quarter. (New program elements, less or more emphasis on a particular delivery source, program elements discontinued, measure discontinued, budget changes, etc.)

The third quarter focused on rolling-out the program and getting program elements in place. The 4th quarter initiated a ramp-up into a full-scale production mode.

- Discussion of near-term plans for the program over the coming months (marketing, outreach efforts that are expected to significantly increase participation in the program).

The 4th quarter saw continued growth in CLP participation as the marketing efforts reached a wider range of customers. However, program participation in the early months of 2007 is expected to decrease (as only Energy Star front load washers will qualify under this program). To mitigate this projected slowdown, the program will expand marketing efforts to include direct marketing to end use tenant customers and multi family property managers of SCG-SCE. This will require close coordination with the separate multi family program of SCG-SCE.

Ramped up to make a significant contribution to the number of CFL, T8 Retrofits and Pipe Wrap in the Fourth Quarter.

- Changes to staffing and staff responsibilities, if any.   None

- Changes to the contract, if any.   None.

- Changes to contractors and contractor responsibilities, if any.  None.

- Number of customer complaints received.   No customer complaints were received during this quarter

- Revisions to program theory and logic model, if any.  There were no changes in program theory and logic models.

- Concluding Comments.

The level of cooperation by each of the many several utilities (gas, electric and water) has been outstanding. There are different ideas on “the best way” to implement a commercial laundry program and there continue to be barriers to collaboration with other utility energy efficiency programs. But on every occasion where a problem or issue arises that requires feedback or assistance by SCG and SCE, the response has been prompt and very helpful.