| Program Name: | Portfolio of the Future |
| --- | --- |
| Program Number: | SCG3530 |
| Quarter: | First Quarter 2007 |

- Program description

The Portfolio of the Future Program is comprised of multiple diverse activities designed to help SoCalGas identify and evaluate promising emerging natural gas efficiency technologies.  The Portfolio Program starts with a comprehensive scan of technologies and an evaluation of their readiness for commercialization.  The inventory of technology opportunities will then be prioritized in accordance with criteria to be established with SoCalGas.  From this ranked inventory, a portfolio of studies and activities, including pilot demonstration projects and testing of new business models, will be implemented.  The overarching goal of this program is to advance development of promising technologies for possible inclusion in SoCalGas’ energy efficiency programs.

- Administrative activities

- Conducted project management and accounting activities, including monthly budget variance reports, work planning, staffing and scheduling.

- Performed monthly billing and reporting, including updating Sempra Utilities’ DBE (Diverse Business Enterprises) compliance reporting database.

- Modified monthly reporting and invoicing procedures as requested by Sempra Utilities’ contract administrator.

- Reviewed “flat file” instructions with Sempra Utilities’ contract administrator and IT staff (submission of flat files on hold pending resolution of implementation issues).

- Updated subcontracting plan, including identification and timing of needed skill sets.

- Attended quarterly contractors’ meeting in Downey.

- Marketing activities

- None

- Direct implementation activities

- Compiled results of initial screening and ranking of natural gas emerging technologies, all sectors (residential, commercial, industrial).

- Reviewed highest ranked options with SoCalGas to determine whether and how these measures “fit” into SoCalGas’ existing and planned energy efficiency portfolio.

- Commenced development of pilot project concepts for priority technologies.

- Refined technologies database and portfolio evaluation tool to prepare for hand-off to SoCalGas.

- Completed compilation and organization of natural gas energy efficiency technologies database.  Final database was submitted to SoCalGas on Feb. 28, 2007.

- Obtained authorization from SoCalGas to proceed with scoping market studies, pilot programs and other technical assistance to advance four technologies identified as “high potential”.

- Commenced additional research needed to make decisions on other technologies that appear to have significant potential.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

- Completed evaluation and prioritization of candidate natural gas efficiency emerging technologies; reviewed with SoCalGas.

- Identified 4 high priority natural gas efficiency technologies for development: Improved Heat Transfer; Commercial Laundry Wastewater Recycling; Improved Commercial Dishwashers; and Solar Water Heating.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Meet with SoCalGas emerging technology and program/account management staff for the joint purposes of (a) reviewing relative ranking of natural gas efficiency technonlogy options, and (b) continuing discussions about priority measures and goals/objectives for the pilot portion of the Alliance program.  Recommended studies, pilots, demonstration projects, and new business models will be reviewed at that time.  Specific pilot and other activities will commence upon SoCalGas’ approval.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts

- None

- Changes to contractors and contractor responsibilities, if any

DBE Subcontractors

- Correction to subcontractor hired in Q3 2006:  Strategic Energy Innovations, a DBE non-profit corporation, is dually certified as both a WBE and MBE.

- Engaged a WBE firm, LKM Associates, LLC, to assist in developing and implementing the Portfolio’s marketing and outreach program.

Grantees

A grant agreement was issued to The Public Sustainability Partnership (PSP), a newly formed non-profit corporation, on February 1, 2007.

At the time of the proposal (November 2005), The Public Sustainability Partnership (PSP) was identified as a "soon to be formed non-profit" participant in the Alliance and Portfolio Programs.  The PSP was incorporated on January 13, 2006 by Laurie Park, NCI's Program Manager for both the Alliance and the Portfolio, on behalf of multiple public and private parties who are working together to collaboratively develop and implement sustainability programs.  The PSP has received confirmation from the IRS that its 501(c)(3) application is approved as of the date of incorporation.  Ms. Park serves as President of the PSP.  Ron Nichols, a Managing Director with NCI, serves on PSP's Board of Directors.  Neither Ms. Park nor Mr. Nichols receives any compensation for their service to PSP; nor will they be providing services under this grant agreement with PSP.

Given the natural synergies between the PSP's mission and the goals of the Alliance and Portfolio Programs, and consistent with the Alliance and Portfolio goals of leveraging existing resources, assets, relationships and access channels, PSP’s primary role in the Alliance and the Portfolio is to help develop the sustainability value proposition and to build partnerships among diverse public and private entities.

The following individuals associated with PSP may provide services to the Alliance and/or Portfolio Programs under this grant agreement.

Board of Directors:

- Craig Sheehy, Director of Property Management for Thomas Properties Group, Vice Chair of the Governor's Real Estate Industry Leadership Council, and past-Chair/President of BOMA-CAL, National BOMA and International BOMA.

- William Becker, Executive Director of the Presidential Climate Action Project, co-founder of the Global Energy Center for Sustainable Communities, and former Western Regional Manager of U.S. Department of Energy.

Advisory Board:

- Christine Ervin, Principal of Christine Ervin Company, former President and CEO of the U.S. Green Building Council, and former Assistant Secretary of U.S. Department of Energy's Office of Energy Efficiency and Renewable Energy (EERE).

Officers:

- George Burmeister, Vice President of the PSP, President of Colorado Energy Group, and former Special Advisor to U.S. DOE EERE.

Program Advisors:

- Paul Johnson, former Senior Manager of the U.S. Department of Energy's Regional Office in Seattle and Regional Program Manager for Rebuild America.

- Dr. Bob Wilkinson, a Lecturer in the Environmental Studies Program, and the Donald Bren School of Environmental Science and Management, at the University of California, Santa Barbara, on water policy, climate change, and environmental policy issues.

Other PSP resources may be brought into the Alliance and/or Portfolio Programs via this grant agreement as additional needs are identified.

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

# Provided in February 1, 2006 concept paper.

- None