| Program Name: | Mobile/Manufactured Home Innovative Outreach and Measure Program |
| --- | --- |
| Program Number: | SCG3539 |
| Quarter: | First Quarter 2007 |

- Program Description

The Mobile/Manufactured Home Innovative Outreach and Measure Program has been designed to provide gas measures on a comprehensive basis to 14,500 mobile home customers in the SCG service territory.

- Administrative Activities

The 1st Quarter showed a strong acceleration of production in the Manufactured-Mobile Home Program and the program is gaining traction. We are consistently working on organizing our systems and structures to consistently work through our finding, scheduling, installation and inspection processes to consistently increase production.

During the quarter, on March 23, a Synergy representative attended the Southern California Gas sponsored Quarterly Contractors meeting in Downey, CA.  A representative from Synergy  also attended the PAG meetings for SCE-SCG in April, reporting on 3rd party programs.

On March 23 and 24, Synergy sponsored a two-day hardwire and T-8 retrofit installation and safety course for lighting with our key managers and associates.  This was a very productive training workshop.

- Marketing Activities

Our marketing and outreach staff has worked toward supporting our business plan by personally distributing flyers in several parks to increase interest and attendance at follow-up neighborhood meetings.

Our marketing and outreach personnel have held 29 neighborhood meetings with 875 guests in attendance for the quarter, with 2,519 guests visited or contacted program to date.  During these meetings a program overview was presented to possible Mobile Home clients.  Sample of the measures to be performed were demonstrated and potential clients and program participants were able to ask questions.  It was felt that these neighborhood meetings were quite productive.  Many customers are able to schedule their appointments for installation directly from these meetings.

Locations and numbers where a number of the neighborhood meetings were held are included as follows to give you a sampling of the types of meetings held:

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| January | Jackson MHP | Hemet | 12 |
|  | Casa Del Rey | Hemet | 6 |
|  | Parkview | Palm Springs | 32 |
|  | Heritage MHP | San Jacinto | 52 |
|  | Rancho Mirage Park | Rancho Mirage | 31 |
|  | Sands RV | Desert Hot Springs | 9 |
|  | Avalon | Yucaipa | 20 |
|  | Joshua Springs | Desert Hot Springs | 7 |
|  | The Colony | Rancho Mirage | 50 |
|  | Mountain View | Desert Hot Springs | 17 |
|  | Desert Palms | Desert Hot Springs | 4 |
|  | Jurupa Hills | Riverside | 29 |
|  | Highland Palams | Homeland | 28 |
| Total Jan | 13 |  | 297 |
| Total | Program-To-Date |  | 1941 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| February | Jurupa Hills | Riverside | 45 |
|  | Palm Villa | Hemet | 25 |
|  | PARK ESTATES | Hemet | 10 |
|  | Canyon Hills | Wildomar | 30 |
|  | Panorama Cove | Hemet | 20 |
|  | Casa Del Rey | Hemet | 100 |
|  | Friendly Village | Long Beach | 50 |
|  | Caliente | Desert Hot Springs | 90 |
| Total Feb | 8 |  | 370 |
| Total | Program-To-Date |  | 2,311 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| March | Almar Acres | Desert Hot Springs | 60 |
|  | Miracle Acres | Desert Hot Springs | 20 |
|  | Country Lakes | San Jancinto | 30 |
|  | The Farm | Wildomar | 30 |
|  | Sparkling Waters | Desert Hot Springs | 30 |
|  | Vista Grande | Desert Hot Springs | 25 |
|  | Swan Lake MHP | Mira Loma | 10 |
|  | Simpson Center | Hemet | 3 |
| Total Mar | 8 |  | 208 |
| Total | Program-To-Date |  | 2,519 |

- Direct Implementation Activities

- Synergy continues to monitor ways to improve direct implementation process and procedures and is pleased that production levels are on track and ahead of schedule.

Program Performance/Program Status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program Achievements (non-resource programs only):

SCG Budget Report and Energy Savings

| Budget and Expenditures | Budget | Cumulative | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- |
| Total | $4,572,000 | $943,850.56 | 20.64% | $3,628,149.45 |
| Admin | $411,065 | $85,238.67 |  | $325,826.33 |
| Marketing | $300,000 | $62,096.00 |  | $237,904.00 |
| DI-Labor | $2,223,156 | $460,537.46 |  | $1,762,618.54 |
| DI-Materials | $1,634,779 | $335,978.43 |  | $1,298,800.58 |
| SCG GAS | Goals | Cumulative | % of Goals | Goals Minus Cumulative |
| Energy Effects |  |  |  |  |
| Annual Therms | 854,278 | 184,640.98 | 21.61% | 669,637 |

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a partic delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None, other than working to increase production and complete all work, where possible in 2007.  We will then work with the program manager in June/July to explore supplemental funding for 2008 to gain additional energy savings.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Synergy is also working on adding additional technicians and crews to increase production throughout the summer months.  Not only will these individuals help during this period, but throughout 2007.

- Changes to staffing and staff responsibilities, if any.

- None

- Changes to contracts, if any.

None

- Changes to contractors and contractor responsibilities, if any.

None

- Number of customer complaints received.

- There were 13 Customer complaints received in the first quarter of 2007, most having to do with scheduling. These complaints were immediately resolved to the customer’s satisfaction. There are no outstanding issues.  There were also hundreds of customer satisfaction calls or cards.  Customers are generally most grateful for this program and are very satisfied with the service.

- Revisions to program theory and logic model, if any.

- Provided in February 1, 2006 concept paper.

- None