| Program Name: | California Urban Water Council Program |
| --- | --- |
| Program Number: | SCG3526 |
| Quarter: | Second Quarter 2007 |

- Program description

This is the third phase of this direct-install incentive-based program that replaces high energy and water use pre-rinse spray valves with more efficient models at food service facilities: restaurants, cafeterias, institutional kitchens and food preparation companies.  There is no cost to the participants and water utilities throughout the state are contributing a portion of the funds for program implementation.  This program targets hard-to-reach food service operators.

- Administrative activities

For the second quarter of 2007 SCG continued to work with CUWCC to evaluate the feasibility for continuing the program.  CUWCC is working with A&N Technical services to assist in the evaluation of the program.

- Marketing activities (describe)

None for Q2 2007

- Program performance/program status (describe)

Program is on target

Program is exceeding expectations

Program is falling short of expectations

# Explain:

# Allowable therm savings per unit is still in debate.

# In addition, as mentioned in 4Q 2006 report there are two other reasons for production falling:

# The program started up several months later than expected.  We continue to track at the average monthly production from phase 1 and 2 during start up months.

# The program to date response rate is tracking at 20%, well below the previous phases’ rate of 50%.  This is due to two main factors: saturation and no spray valve set up.

# Saturation:  As would be expected saturation has increased since Phase 1 of the program.  It is becoming much harder to cost effectively outreach to food service facilities in a door-to-door style because on any given street many of the  sites have been done and therefore the field reps canvass area is not as concentrated.

# No Spray Valve Set Up: Many of the outlying communities that were not hit in previous phases that are being targeted in Phase 3 are older communities and most of the food service facilities in those areas do not have a valve set up.  This has reduced our response rate significantly.

- Program achievements (non-resource programs only):

NA

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

There are no changes to the program.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

The program is currently being reviewed to determine the feasibility for continuing the program.

- Changes to staffing and staff responsibilities, if any

There are no changes to staffing or staff responsibilities.

- Changes to contacts,

There are no changes to the contact.

- Changes to contractors and contractor responsibilities, if any

There are no changes to contractors or their responsibilities.

- Number of customer complaints received

No customer complaints were received.

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.

There are no changes to the theory and logic model.