# Program Name:	Mobile/Manufactured Home Innovative Outreach and Measure Program

Program Number:	SCG3539

Quarter:		Second Quarter, 2007

- Program Description
The Mobile/Manufactured Home Innovative Outreach and Measure Program has been designed to provide gas measures on a comprehensive basis to 14,500 mobile home customers in the SCG service territory.

- Administrative Activities
Throughout the second quarter, we met with Southern California Edison’s (SCE) Program Manager to review all invoices and to look at ways to strengthen the entire acquisition, installation and billing process. As a result, Synergy is applying a number of excellent checks and balances to assure that the measure forms match the invoices perfectly. We have also set up a control sheet to provide a check and balance for each invoice.  These measures will help strengthen the audit trail for the program. Not only did Synergy apply these processes to this quarter’s invoices, but has also gone back through each pervious invoice to apply these improved standards and make the appropriate adjustments and reconciliations.

Although we slowed production a bit during some moths of the quarter to be sure these standards are in place, we experienced the best combined (SCE-SCG) month of production that we have had for the program in June and we also experienced the strongest quarter yet for production. 

We attended a number of Program Advisory Group (PAG) meetings during the month and were pleased to see that the Mobile Home program is one of the most successful programs of the utilities.

We have been working on organizing our systems and structures to consistently work through our finding, scheduling, installation and inspection processes to consistently increase production in an effort to hit program targets 6-12 months ahead of schedule. We have been working on increasing the numbers of technicians in the field, which will provide us with added production capability.

- Marketing Activities
Our marketing and outreach staff has worked toward supporting our business plan by personally distributing flyers in several parks to increase interest and attendance at follow-up neighborhood meetings.

Our marketing and outreach personnel have held 38 neighborhood meetings with 900 guests in attendance during the second quarter.  During these meetings a program overview was presented to possible Mobile Home clients. Samples of the measures to be performed were demonstrated and potential clients and program participants were able to ask questions.  It was felt that these neighborhood meetings were quite productive.  Many customers are able to schedule their appointments for installation directly from these meetings.

Locations and numbers where neighborhood meetings were held are included as follows:

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| April | Groves | Irvine | 210 |
|  | Patrician | Yucaipa | 10 |
|  | Royal Holiday | Hemet | 10 |
|  | Avalon | Riverside | 10 |
|  | FH Village | Pomona | 20 |
|  | Royal Holiday | Hemet | 30 |
|  | Star Lite | Torrance | 10 |
| Total April | 7 |  | 300 |
| Total | Program-To-Date |  | 2,819 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| May | Yucaipa Village | Yucaipa | 20 |
|  | Wildwood Canyon | Yucaipa | 20 |
|  | Horizon | Palm Springs | 10 |
|  | Valley View | Yucaipa | 15 |
|  | Banning Est | Banning | 55 |
|  | Mountain Springs | Banning | 15 |
|  | Fernwood | Ontario | 15 |
|  | Northview | Yucaipa | 30 |
|  | American Village | San Jacinto | 45 |
|  | Rancho Caballaro | Riverside | 35 |
|  | Pomona Islander | Pomona | 35 |
|  | Wishing Well | Yucaipa | 15 |
|  | Mission Valley | Yucaipa | 15 |
|  | Palm Canyon Mobile | Palm Springs | 10 |
|  | Linda Vista | Banning | 20 |
| Total May | 15 |  | 355 |
| Total | Program-To-Date |  | 3,174 |

| Month | Mobile Home Park | City | Number Attending |
| --- | --- | --- | --- |
| June | Executive | Yucaipa | 15 |
|  | Redlands CMH | Redlands | 15 |
|  | Fairway | Highland | 15 |
|  | Mirage | Hemet | 20 |
|  | Las Casitas | Yucaipa | 20 |
|  | Grandview East | Yucaipa | 5 |
|  | Grandview West | Yucaipa | 5 |
|  | Park Terrace | Yucaipa | 15 |
|  | Aladdin | Yucaipa | 15 |
|  | Avalon | Riverside | 15 |
|  | Caravan | Yucaipa | 5 |
|  | Sun Valley | Hemet | 30 |
|  | Yucaipa | Yucaipa | 20 |
|  | Rancho Del Sol | Yucaipa | 5 |
|  | Silver Creek | Highland | 25 |
|  | Mountain View | San Bernardino | 20 |
| Total June | 16 |  | 245 |
| Total | Program-To-Date |  | 3,419 |

- Direct Implementation Activities
Synergy continues to monitor ways to improve direct implementation processes and procedures and is pleased that production levels are on track and ahead of schedule.

- Program Performance/Program Status
(	Program is on target
(	Program is exceeding expectations
(	Program is falling short of expectations

- Program Achievements (Non-Resource Programs Only)
SCG Budget and Energy Savings Report

| Budget and Expenditures | Budget | Cumulative | % of Budget | Unspent |
| --- | --- | --- | --- | --- |
| Total | $4,572,000 | $1,305,313 | 28.55% | $3,263,687 |
| Admin | $414,065 | $118,216 |  | $292,849 |
| Marketing | $300,000 | $85,650 |  | $214,350 |
| DI-Labor | $2,223,156 | $634,715 |  | $1,588,441 |
| DI-Materials | $1,634,779 | $466,732 |  | $1,168,047 |
| Energy Effects | Goals | Cumulative | % of Goals | Goals Minus Cumulative |
| Annual Therms | 854,278 | 256,257 | 30.00% | 598,021 |

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measures discontinued, budget changes, etc.).
None, other than working to increase production and complete all work, where possible in 2007.  We will then work with the program manager to explore supplemental funding for 2008 to gain additional energy savings.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.).
Synergy has added additional technicians and crews to increase production throughout the summer months. Not only will these individuals help during the summer period, but throughout 2007.

- Changes to staffing and staff responsibilities, if any.
None

- Changes to contracts, if any.
None

- Changes to contractors and contractor responsibilities, if any.
None

- Number of customer complaints received.
During the second quarter of 2007 there were 15 customer complaints. All have been resolved. Some had to do with technicians being late on an appointment or having missed an appointment, a few had to do with HVAC operational issues during hot weather, one had to do with the level of communication from the technician and all were successfully resolved to the customers satisfaction. We are working with the technicians to follow-through carefully with each customer and confirm that each measure is properly functioning before leaving the site and to be more social and communicative. Synergy received 649 complimentary customer satisfaction calls and cards in the second quarter of 2007. Customers seem to be very satisfied for the services rendered and for the program in general.

- Revisions to program theory and logic model, if any.
None. Provided in February 1, 2006 concept paper.