| Program Name: | SCG Statewide Crosscutting Codes and Standards |
| --- | --- |
| Program Number: | SCG3501 |
| Quarter: | Fourth Quarter 2007 |

- Program description:

Codes and Standards (C&S) is an existing statewide program that promotes upgrades and enhancements in energy efficiency standards and codes.  Codes and Standards Enhancement (CASE) studies are performed for promising design practices and technologies.  The studies’ results are presented to standards and code-setting bodies to encourage adoption of energy efficiency measures. In addition, C&S develops and conducts training seminars to inform the building community regarding applicable codes and prepare them for upcoming code changes.

- Administrative activities:

- Routine monthly administrative activities include but are not limited to the following activities:  Project tracking and review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, and managing of program budgets and expenditures.  Supporting CPUC’s impact evaluation contractor Quantec’s requests regarding pre-2006 codes and standards advocacy efforts.

- Marketing activities:

- None

- Direct implementation activities:

- Continued monitoring and providing support to the CEC on the 2008 Title 24 workshops on building standards. Attended Title 24 workshop for 45 day language conducted by the CEC on December 17, 2007.

- Participated in Title 20 planning workshop at the CEC on December 12, 2007

- Continued activities for the following CASE studies:

  - Hotel Card Key Control

  - Multifamily Central DHW systems

  - Improved Res Water Heating Distribution System Design

  - Commercial Gas Clothes Dryers

  - Evaporative Cooling

- Continued evaluation of potential CASE studies.

- Selected following CASE studies for further evaluation:

  - Gas Convection Oven

  - Solar Thermal Pool Heating

  - Radiant Heaters

  - Domestic Hot Water - Prevent showers with multiple heads

- Held statewide planning and coordination meeting on October 19, 2007 and participated in the one on November 27, 2007.

- Participated in workshop with CEC and consultants on project to develop Title-24 compliance software workshop.  Provided cofunding to CEC for workshops..

- Participated in USGBC’s Greenbuild 2007.

- Participated in ASHRAE Standard 90.1, TC 6.6- Service Water Heating and 62.2 Indoor Air Quality  meetings

- Continued to look at the opportunity for locally adopted energy standards which local governments could adopt that exceed Title 24 standards.

- Continued monitoring and participating in USDOE rulemaking activities including residential water heating and direct heating equipment.

- Participated in Future Comfort Controls in California Homes workshop at LBNL

- Participated in sectoral workshops on residential and commercial for the 2009-2020 Strategic Plan

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

# The program is on target.  Potential CASE studies are being planned.

- Program achievements (non-resource programs only):

# Continued development of CASE studies.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

# None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

# Will continue as per 1st Quarter 2006.

- Changes to staffing and staff responsibilities, if any:

# None.

- Changes to contracts:

# None.

- Changes to contractors and contractor responsibilities, if any:

# None.

- Number of customer complaints received

# None.

- Revisions to program theory and logic model, if any

None.