| Program Name: | SoCalGas On-Bill Financing |
| --- | --- |
| Program Number: | SCG3514 |
| Quarter: | Fourth Quarter 2007 |

- Program description:

The Southern California Gas Company (SoCalGas) On-Bill Financing (OBF) Program is a local program designed to facilitate the purchase and installation of qualified energy efficiency measures by customers who might otherwise not be able to act given capital constraints and administrative and time burdens to participation.

- Administrative activities:

- Various internal presentations to provide an overview of the 2006-2008 On-Bill Financing Program and the support the program provides to energy efficiency rebate/incentive programs.

- Participated in discussions and meetings with the Statewide IOUs to discuss our approaches for Financing programs for the 2006-2008 program cycle.

- Marketing activities:

The OBF program sought select customers to participate in program as "beta" sites for testing purposes.

- Direct implementation activities:

Phase II Business Requirements to fully automate the billing system for processing monthly loan charges was completed.  This process integrates SoCalGas’ billing system with a SAP loan module to provide accurate and systematic procedures to streamline loan and payment processing.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

Milestone 1 stated that SoCalGas would have a manual billing system in place and loans available to customers by end of first quarter 2006.  At the end of the first quarter 2006, the manual billing system was in place.

Milestone 2, the billing system automation project (Phase II) has completed and operational at the end of the third quarter 2007.

Program participation is substantially lower than the average 300 loans per year projected in the Program Concept paper filed on 2/1/06.  This is primarily due to the difficulty that most current natural gas measures that qualify for EE rebates to also qualify for OBF (e.g., project payback periods exceed the 5-year maximum).

While it is understood that the challenge for a gas-only OBF program is tremendous and the progress will likely be very slow, nevertheless, SoCalGas will continue to explore ways to outreach to customers who can benefit from the program and to adjust the program to make it more accessible to more customers.

- Program achievements (non-resource programs only):

- At year end 2007, there were seven (7) projects signed up to participate in the program for a total of about $231,000 in loans dollars.

- Distributed OBF fact sheet at various outreach events

- Continued to assess OBF and review gas-only OBF market potential in SCG’s service territory.  We are investigating program re-design options for the 2009 cycle, as well as how to best market to the currently identified niche opportunities.

- Conducted three focus group discussions to better understand key factors small business customers consider when making decisions regarding financing energy efficiency projects.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

- Work with Partnership programs to recruit potential OBF customers

- Target vendors and/or manufacturers whose energy efficient equipment qualify for OBF

- Changes to staffing and staff responsibilities, if any:

None.

- Changes to contracts:

None.

- Changes to contractors and contractor responsibilities, if any:

None.

- Number of customer complaints received:

None.

- Revisions to program theory and logic model, if any:

None.