| Program Name: | Portfolio of the Future |
| --- | --- |
| Program Number: | SCG3530 |
| Quarter: | Fourth Quarter 2007 |

- Program description

The Portfolio of the Future Program is comprised of multiple diverse activities designed to help SoCalGas identify and evaluate promising emerging natural gas efficiency technologies.  The Portfolio Program starts with a comprehensive scan of technologies and an evaluation of their readiness for commercialization.  The inventory of technology opportunities is then prioritized in accordance with criteria established with SoCalGas.  From this ranked inventory, a portfolio of studies and activities, including pilot demonstration projects and testing of new business models, is implemented.  The overarching goal of this program is to advance development of promising technologies for possible inclusion in SoCalGas’ energy efficiency programs.

- Administrative activities

- Conducted project management and accounting activities, including monthly budget variance reports, work planning, staffing and scheduling.

- Performed monthly billing and reporting, including updating Sempra Utilities’ DBE (Diverse Business Enterprises) compliance reporting database.

- Maintained the SMART system.

- Marketing activities

- Commenced development of website template and content for selected emerging technologies.

- Direct implementation activities

- Continued to identify manufacturers, customers and other strategic partners for participation in energy efficiency demonstration projects; pursued partnerships to implement already approved pilots.

- Continued refining work plans for top measures selected for pilot studies.

- Continued providing requested materials to EM&V contractor.

- Researched and pursued potential technologies and manufacturers for participation in energy efficiency demonstration projects.

- Updated sweep for, and evaluation of, promising emerging technologies (identified alternative dry cleaning and membrane filtration technologies).

- Commenced development of detailed workpapers.

Pilot A – SpyrcorTM.  Identified potential demonstration sites, developed plan for emissions test at Spinworks test facility, established data requirements for a successful demonstration at a customer facility, identified data needed to refine market forecast, and reviewed plan for emissions testing of the SpyroCorTM inserts developed by Spinworks.

Pilot B – Laundry Wastewater Recycle.  Completed market research and analysis, including review of competitive commercial laundry technologies.  Prepared presentation summarizing findings and recommendations, and reviewed spreadsheet model estimating energy savings potential.

Pilot C – Commercial Dishwashers.  Completed Phase 1 market study that included survey interviews of fast food restaurants, food stores, schools, colleges, hotels, hospitals and prisons.  Also conducted surveys for casual concept/independent restaurants, and additional surveys to cover an expanded definition of “cafeterias” that included buffets and casinos.

Pilot D – Solar Water Heaters.  Conducted market research to assess costs and market barriers.  Conducted interviews of installers, manufacturers, distributors and a CPUC representative and conducted a brainstorming session on potential business models.  Began development of a market study and evaluation of business model options.  Discussed potential partnership between SCG and MMA Renewables.

Pilot E – Steam Traps.  Continued working with Armstrong and its representative in Southern California to plan for a field demonstration of the savings potential at a Coca-Cola Bottling Plant.  In cooperation with Armstrong, revised a preliminary spreadsheet-based model for analyzing energy savings and financial attractiveness of the SteamEye system under different scenarios to obtain a more accurate estimate of the market penetration and energy savings potential in SCG territory.  Worked with Armstrong International to finalize details of the installation scheduled to occur by end January 2008.

Pilot F – Cold Water (Enzymatic) Detergents.  By request of SCG, developed proposal for PG&E participation in the market assessment and participated in discussions among SCG, PG&E and the project team regarding PG&E’s potential participation.

Pilot G – Combustion Sensors and Controls.  Continued to research and evaluate technologies; developed working paper on emerging technology opportunities in combustion sensors and controls; interviewed lead developers of selected combustion sensors and controls to assess their state of commercial readiness; updated powerpoint presentation; and requested additional information from suppliers for select sectors.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

- All approved pilot programs have commenced and are producing information.

- Scan for additional emerging technologies continuing.

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- Continue to conduct market surveys, technology demonstrations and pilot projects.

- Continue to secure partners and subcontractors.

- Continue to develop work plans for additional proposed technologies.

- Develop & launch market awareness building program, including presence on the Portfolio’s sister program's website (the California Sustainability Alliance).

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts

- None

- Changes to contractors and contractor responsibilities, if any

- ASW Engineering, a DBE firm, was hired to assist in evaluating energy efficiency potential of pilot emerging technologies and to prepare detailed workpapers documenting findings and recommendations.

- LUCITA, a DBE creative marketing consultant, was hired to design the Portfolio section of the Alliance website and to assist with marketing and outreach activities.

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any, provided in February 1, 2006 concept paper.

- None