| Program Name: | Multi Family Energy Efficiency Retrofit Program |
| --- | --- |
| Program Number: | SCG3510 |
| Quarter: | First Quarter 2008 |

- Program description:

The Southern California Gas Company (SoCal Gas) Multi Family Energy Efficiency Retrofit (MFEER) Program is a statewide program that targets property owners and managers of multifamily residential dwellings, homeowner’s associations, and mobile home park associations.  The program encourages property owners and managers to install qualifying energy efficiency products in common areas for residential apartments, mobile home parks and condominium complexes.  The program is designed for flexibility; it offers agreed upon statewide measures for coordinated implementation, but is designed to easily adapt to market changes, including adding new measures that may emerge as cost effective opportunities in the SoCalGas local service area.

- Administrative activities:

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.

In addition, program staff:

- Continued ongoing communication with Processing and Inspection group to ensure correct application of 2008 program procedures.

- Continued participation in weekly Statewide IOU Multifamily Rebate Team conference calls.

- Attended monthly Residential Customer Programs Staff Meetings.

- Coordinated maintenance and updates of SoCalGas’ 2008 Multifamily Rebate webpage.

- Coordinated updates of SoCalGas’ 2008 Multifamily Rebate information to Flex Your Power.

- Continued participation with the 3rd Party Proposal review and scoring for Water Heater and Multifamily Programs.

- Attended multiple 2009-2011 EE Program Planning Workshops; emphasis on program design, marketing and implementation strategies

- Attended 4 day Customer Relationship Management Business Scenario Training.

- Attended Director’s Quarterly Dialogue Session, ERC, Downey.

- Attended 2 Day Training- Whole House Performance with Energy Star.

- Major emphasis placed on preparing, editing and coordinating efforts for 2009-2011 Residential Business Plan and Program Implementation Plans.

- Attended Regulatory Kickoff Meeting

- Marketing activities:

- Applications may be downloaded via the web site or requested via SoCalGas’ Residential Marketing Department, or Program Manager.

- Provided SoCalGas Public Affairs Managers the updated Residential Customer Programs’ presentation, specifically designed for public events.

- Received valuable Residential Programs survey results from EcoNorthwest; working to incorporate strategic recommendations into program design for 2009-2011 PY.

- Attended Commercial Program’s Vendor Mixer to cross promote Multifamily Rebate Program to participating vendors.

- Maintained high visibility and promotion of SoCalGas Residential Rebate Programs (RCP) at tradeshows and public events in service territory.  RCPs was promoted at 10 business related events (over 6300 attendees), as well as 19 events specifically focused on residential outreach (over 1.5 million attendees).

- Information and Outreach coordinators continued to promote Multifamily Rebate Program at all residential public events and tradeshows in service territory (specific Multifamily events outlined below):

- 03/1208:  Participated in the Apartment Owners Association of Orange County: “Step up to the Plate ” Tradeshow, Costa Mesa, CA

  - Distributed multifamily applications, tri-fold program description brochures and Multifamily Fact Sheet during the tradeshow.

- Direct implementation activities:

- Multifamily EE Rebate applications and brochures were delivered to customers in SoCalGas service territory via tradeshow and outreach participation during first quarter.

- Ongoing random inspections of installed rebate measures as required per program specifications.

- Continued Pre-Inspections for SoCalGas Multifamily Rebate Program, with an emphasis on conducting 100% Pre-inspections on Controller devices and 25% of all other measures.

- Participated in the Statewide Contractors Meeting to assist, train and ensure contractors complete appropriate documentation when preparing rebate forms.

- Met with Tankless Water Heater companies to discuss pilot program for multifamily applications~ worked with engineering group to discuss potential pilot.

- Successfully facilitated program participation with representative of Irvine Apartment Communities; resulted in major EE appliance upgrade to multiple property locations.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

YTD for the end of the first quarter 2008 approximately one-third of the incentive goal for 2006-2008 has been paid and the program has achieved less than one third of therm goal for the three year period.  Currently, the program is falling short of expectations.

- Worked with Corporate Communications in first quarter to refresh marketing materials and launch Multifamily Direct Mail Marketing Campaign in 2nd Quarter 2008, in order to increase program participation.

- Received final results of the EM&V Study on Controllers for Boilers and Central Water Heaters (conducted by KEMA, Services Inc.).  Study indicated that the realization rate for controllers reduced therm savings by as much as75%.  These findings negatively impacted program participation.  Further steps are being addressed to salvage this measure’s viability.

- Program achievements (non-resource programs only):

N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

- Fulfillment on the Multi Family Energy Efficiency Starter kits has been delayed due to internal processing requirements.  Work papers to substantiate therm savings in the Multi Family sector have been requested from engineering and are expected in second quarter 2008.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

- Plans to promote MF Rebate Program by participating in upcoming tradeshows:

05/20/08:  Apartment Owners Association Tradeshow

- Changes to staffing and staff responsibilities, if any:

Continued to employ a “Temporary” Data Entry Clerk to assist with the program administration.

- Changes to contracts:

None.

- Changes to contractors and contractor responsibilities, if any:

None.

- Number of customer complaints received:

- Revisions to program theory and logic model, if any:

None.