| Program Name: | PACE Energy Efficiency Ethnic Outreach Program |
| --- | --- |
| Program Number: | SCG3531 |
| Quarter: | First Quarter 2008 |

- Program description

- PACE’s Energy Efficiency Ethnic Outreach Program will promote Southern California Gas Company’s energy efficiency programs in ethnic minority communities and customers with historically low participation rates in The Gas Company programs.  Specifically, the three categories of customers covered by this contract include:  Individual Residential Users; Multifamily Owners/Managers; and Small Businesses owned, operated or catering to the targeted ethnic minorities.

- Administrative activities

    - PACE submitted its fourth quarter and annual reports to The Gas Company on February 8 and February 11, respectively, as well as a short report on the Korean foodservice seminar, news clippings (February 13) and a list/inventory of collateral materials (in language) used to promote energy efficiency programs (February 13).

- PACE discussed with The Gas Company:

  - Refinements to revisions and realignment of PACE’s contract’s scope of works. The Gas Company program manager informed PACE the revised contract has been submitted to Supply Management for review on January 28, 2008.

- Status of the following in meetings held February 15, March 12 and 17  2008:

        - Contract’s scope of work amendments;

        - Upcoming Vietnamese foodservice seminar scheduled for May 1, 2008;

        - Proposed topics for second round of foodservice seminars;

        - SMART system issues and suggestions;

        - Program evaluation inquiries from EcoNorthWest and Opinion Dynamics;

        - Renewal of contract for 2009-2011 program cycle

          - The Gas Company encouraged PACE to develop seminars with other organizations and explore use of its other training facilities.

          - Since The Gas Company does not have a Vietnamese-speaking presenter, PACE marketing specialist will conduct foodservice seminar on May 1, with support from ERC staff.

- PACE sought bids among qualified vendors about training its Assessment/Evaluation Specialist on the Goldmine database software and selected Team Autonation.  Training was scheduled on April 1 and 9, 2008.

- PACE reviewed applications and conducted interviews of qualified applicants for the position of Marketing Specialist for the Vietnamese community and offered the position to the best-qualified candidate on January 15.  Applicant started part time on January 16 and began full time on January 28, 2008.

- Energy Efficiency Contractor Collateral Data Request:

    - PACE submitted data requested by Opinion Dynamics to The Gas Company on January 4, 2008.  PACE provided additional information requested by The Gas Company on January 14 and 16, 2008.

- Marketing activities

- The Gas Company-provided materials:

Showerhead/Aerator Confirmation brochure

- The Gas Company provided the English/Spanish version to Agnew Tech II on January 7, 2008 and PACE coordinated and reviewed the translations prior to submission to The Gas Company for approval: Vietnamese (February 5), Chinese and Korean (February 29).

- PACE ordered 2,000 copies of the English/Spanish version in January 2008.

- The Gas Company approved the translations into Chinese, Korean and Vietnamese on March 6, 2008.

- PACE ordered 1,600 copies of each brochure on March 7, 2008 from Golden State Printing.  Printed copies were received on March 17, 2008.

Foodservice seminar materials

  - Spanish foodservice seminar

    - The Gas Company approved the updated (English version) of the foodservice seminar flier on January 31, 2008; 750 copies were provided to PACE and this was distributed beginning February 1, 2008.

    - The Gas Company approved its translation into Spanish on February 6, 2008 and 500 copies were delivered to PACE for distribution beginning February 8, 2008.

      - Vietnamese foodservice seminar

- PACE submitted to The Gas Company the Vietnamese translation of the registration form on February 27, 2008; this was approved on the same day, but reproduction was held, pending the selection of the seminar presenter.

- The “Save the Date” card translation was re-submitted and approved by The Gas Company on March 20, 2008.

- PACE-generated materials:

- PowerPoint presentation for small business customers:

    - PACE submitted the Chinese, Korean, Spanish and Vietnamese translations to The Gas Company for review/approval on March 17.  The Gas Company approved the Chinese translation on March 20; the Vietnamese translation on March 27; the Korean translation on March 24 and the Spanish translation on March 31, 2008.

- Showerheads/aerator application forms

    - PACE submitted the updated/revised forms to The Gas Company on:

      - January 15 – English

      - January 16- Chinese

      - January 23 – Korean

      - February 1 -  Vietnamese

      - February 4 – Spanish

    - The Gas Company approved these on:

      - January 16- English

      - January 17 – Chinese

      - January 28 – Korean

      - February 5- Vietnamese

      - March 10 - Spanish

  - PACE advertisement

    - PACE placed the Chinese version of the ad in two publications: the Asian American Expo souvenir magazine (January 19-20) and the Taiwan Daily News (February 2-3 issue).

    - Copies of these publications were provided The Gas Company for file/reference.

- Press Releases/Articles/Media Coverage:

- The Gas Company approved the following PACE press releases:

- January 31, 2008- upcoming community events in February 2008 submitted on January 30, 2008

- January 31, 2008- seminar for Hispanic foodservice operators submitted in January 30, 2008

- March 28, 2008- upcoming events in April 2008 submitted on March 25, 2008

- March 28, 2008- Vietnamese foodservice seminar submitted on March 25, 2008

- PACE disseminated the approved press releases to three major/mainstream newspaper dailies (Los Angeles Times, The Whittier Daily News and San Gabriel Valley Tribune) and Channel 4 Community Events website bulletin board.

- LA TV 4 online bulletin board posted PACE’s upcoming events in February 2008.

- Whittier Daily News (Z Events.com) informed PACE it posted the announcement about the Hispanic foodservice seminar on its online community bulletin board.

- PACE provided The Gas Company a copy of the news clipping/proof of publication on Chinese Biz News dated March 1, 2008.

- PACE submitted to The Gas Company a list of topics to be developed for in-depth articles for PACE News! on February 12; the list of topics was approved on February 13, 2008.

- The Gas Company approved article, “PACE Energy Savings Projects Reaches Out to Diverse Community” on March 24, 2008.

- Website Updates:

- PACE continued to maintain and update the information about The Gas Company’s energy efficiency programs and Calendar of Events listing PACE’s outreach and community events schedule.

- Networking /Outreach Activities:

- PACE conducted networking activities with several organizations, associations or businesses to promote the energy savings programs of The Gas Company for the period January to March 2008 (see monthly reports, January to March for details).

- PACE set up booths at 20 community events for the period January to March 2008 (see monthly reports, January to March for details).

- During these events, PACE distributed faucet aerators, rebate application forms and other information about The Gas Company’s Energy Efficiency Programs to participants and other exhibitors.  PACE also assisted target participants in accomplishing the Home Energy and Water Efficiency Survey (paper and online).

- PACE made reservations to participate in 24 ethnic community events during the months of January to March 2008, as well as for the months of April and May 2008.

- PACE conducted outreach activities with 596 small businesses, 64 residential and 16 multi-family residential customers during the period January to March 2008 (see monthly reports for details).

      - PACE pre-registered 179 Hispanic foodservice operators to attend the seminar scheduled February 28, 2008.  Of these, 37 attended.  It was the first time the participants visited the Energy Resource Center and got acquainted with its facilities and services.

- PACE continued to research, gather information and create contact lists of the various targeted groups in the residential, multi-family and small business categories to promote the energy efficiency programs of The Gas Company.

- Direct implementation activities

- PACE outreached to 596 small business owners and/or operators, 64 residential and 16 multifamily residential customers.

- PACE set up booths at 20 community events, gatherings or meetings to promote the energy savings programs of The Gas Company (see monthly reports, January to March 2008, for details).

- PACE completed the following goals from the above outreach activities during this quarter:

- 526 paper-based survey completed;

- 1,133 online surveys completed;

- 2,513 Low-Flow Showerheads distributed

- 2,563 Single Family faucet aerator sets distributed;

- 2,594 residential customers contacted and provided information about available energy savings and rebate programs;

- 676 small businesses informed and given energy efficiency program and rebate information materials;

- Adjustments were made during this quarter after receiving approvals from The Gas Company for previous months’ activities: Online surveys= +10 (December 2007) and Residential contacts= +9.

# Translation:

# PACE translated into Chinese, Korean, Spanish and Vietnamese PowerPoint presentations (for small business customers), foodservice seminar materials and coordinated/reviewed translations of the Showerhead/Aerator confirmation brochures into Chinese, Korean and Vietnamese.

- Program performance/program status

Program is on target

Program is exceeding expectations

Program is falling short of expectations

- Program achievements (non-resource programs only):

- PACE completed the recruitment process for the position of Marketing Specialist for the Vietnamese community by hiring a qualified applicant on January 15, 2008.

- PACE continued with its outreach activities to fulfill goals of encouraging participation of target ethnicities:

- assisted 526 customers of The Gas Company to complete paper-based Home Energy and Water Efficiency surveys

- assisted 1,133 customers of The Gas Company to complete online Home Energy and Water Efficiency surveys

- distributed 2,513 low-flow showerheads and 2,563 faucet aerator sets to 2,594 single-family residential customers of The Gas Company

- exhibited in 20 community events

- disseminated energy efficiency and rebate information to 2,594 residential and 676 small business customers of The Gas Company

- PACE completed four press releases about the energy efficiency programs and disseminated these to three mainstream daily newspapers and two online sites (LA TV 4 and Whittier Daily News).

- PACE completed placement of an article about The Gas Company’s energy savings programs in The Chinese Biz, an ethnic daily newspaper specializing in Chinese business news and events on March 1, 2008.

- PACE placed full page advertisements in the Asian American Expo 2008 magazine (January 19, 2008) and the Taiwan Daily News (February 2-3, 2008 issue).

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- PACE received the formal approval of its contract’s revised scope of work on March 25, 2008. The revised scope of work included the:

- distribution of 7,000 low-flow showerheads to customers of The Gas Company during its various outreach activities

- increase in the number of faucet aerators from 5,000 to 13,000 for distribution to customers of The Gas Company

- decrease in the number of customers to be assisted in completing the online Home Energy and Water Efficiency Survey from 9,000 to 2,000

- decrease in the number of targeted number of residential customers outreached and signed up to the various energy efficiency programs from 60,000 to 15,000

- addition of targeted presentations to ten (10) Chinese, Korean, Spanish and Vietnamese social, educational, religious, trade, professional organizations or associations to promote the energy saving programs to their members

- realignment of the number of small businesses to be outreached concerning the energy efficiency programs for customers of The Gas Company from 6,100 to 4,833

- increase in the number of community events, to include hard-to-reach areas or communities, from 25 to 70

- develop a PowerPoint presentation to promote the rebate programs to small business customers of The Gas Company and translate this into Chinese, Korean, Spanish and Vietnamese

- increase efforts to place news articles about the energy efficiency programs in various mass media—print, broadcast and the internet—from 10 to 20

- increase program staff complement to include a marketing specialist focused on outreach to the Vietnamese community and other staff as may be needed

- translate various information and marketing materials into ethnic languages to promote greater understanding, appreciation and participation among the Chinese, Korean, Spanish and Vietnamese customers of The Gas Company

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- PACE will include the distribution of 7,000 low-flow showerheads to customers of The Gas Company

- PACE will increase the number of faucet aerators for distribution from 5,000 to 13,000 to customers of The Gas Company.

- PACE will increase its marketing/advertising efforts by writing press releases and placing at least 20 news articles in various ethnic mass media to increase awareness and participation of target ethnicities in the various energy efficiency programs of The Gas Company

- PACE will utilize PowerPoint presentations that lists and provides details about the energy efficiency programs for residential and small business customers of The Gas Company to assist in increasing their understanding of and participation in these programs;

- PACE will continue to build closer relationships with collaborators and other ethnic organizations by coordinating and participating in various activities such as workshops, meetings and networking sessions, as well as making presentations before their members to generate increased awareness and participation among the target ethnic groups;

- PACE will continue to participate in increased number (70 from 25) of local community events where target ethnic communities are expected to participate;

- PACE will translate energy efficiency program information into ethnic languages (Chinese, Korean, Spanish and Vietnamese) for various media outlets;

- PACE will continue to work with The Gas Company to obtain and develop necessary/available materials and create new marketing materials to support its outreach efforts to the targeted ethnic communities.

- Changes to staffing and staff responsibilities, if any

- PACE completed the recruitment process and filled the position of Marketing Specialist in January 2008.

- Changes to contracts

- PACE received a copy of the revised contract on March 25, 2008.

- Changes to contractors and contractor responsibilities, if any

- None

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

- None