| Program Name: | Laundry Coin-aaOp Program |
| --- | --- |
| Program Number: | SCG3540 |
| Quarter: | 1st Quarter 2008 |

- Program Description:

The primary goal of the program is to promote the installation of Energy Star equivalent standards for commercial-grade clothes washers to replace inefficient commercial clothes washer’s as served by gas or electric water heaters in high-usage Laundromats, institutions and multifamily facilities.

The energy savings will be achieved by providing appropriate rebates and education on overall energy and water savings to property managers and owners, equipment manufacturers and residential and small commercial leasing companies to facilitate the replacement and early retirement of existing leased or company owned equipment. Additional energy savings will be achieved concurrently by installing pipe wrap and lighting measures.  The program shall market and provide outreach approaches to bring multiple decision makers and stakeholders together to facilitate energy efficiency actions in the commercial washer industry. The primary decision makers and stakeholders this program will include the following types of customers:

- Owners or Leasers of commercial clothes washers at Laundromat, institutions and multi family property managers and owners;

- Commercial washer leasing companies; distributors and route operators;

- Commercial washer equipment manufacturers; and

- Water agencies, municipalities and companies serving SCG&SCE

- Administrative Activities

During the 1st quarter 2008, the Commercial Laundry Administrative Team continued their meetings with the companies who lease or finance commercial washers to the end-use customers. The route operators and distributors have advised that the purchase of Maytag by Whirlpool, may cause the introduction on new or different front load commercial washers. We are working with the manufacturers and CEE so that we are promptly aware when any changes may be implemented.

CLP team members continued to work with SCG to work out bugs in getting data successfully uploaded in the SMART data and invoicing system training. We have greatly appreciated the support of the utilities and the SMART team to collaborate on meeting to address these issues. While therm savings have often been uploaded successfully uploaded into SMART, we have not been advised if kWh savings have successfully been uploaded.

CLP team members met with SCG program managers during this period to review new program elements submitted to SCG and SCE in February. A presentation was made to SCG program managers of the current marketing tools and marketing plan. Steps to continue the CLP into program years 2009-11 were reviewed.

CLP team members also met with MWD water rebate program managers as part of our on going efforts to collaborate on joint water and energy rebate programs of commercial washers. We presented a recommendation from those who purchase the new commercial washers, that water rebates be paid directly to them (as are rebates from SCG and from SCE). MWD will consider this request. MWD noted that they have heard from a great many customers that the timing of energy rebates is lagging far behind payment of water rebates. Our team members committed to making a recommendation to SCG and to SCE that rebate checks will be advanced (prior to utility inspection and payment to the contractor). We have made this recommendation to SCG and to SCE and are awaiting approval.

- Marketing Activities

The Coin Laundry Team is continuing to work with and co-market with all the various Route Operators, Distributors and Water Agencies in a coordinated effort to boost the number of rebate applications and front-load conversions.  Our approach is to educate our trade allies about the importance of energy savings and the measures that can be taken in order to provide their customers these vital facts.  Consistent and persistent coordination is going to make the Coin Laundry Program a success and entice greater customer participation.

During the 1st. quarter, meetings were set up with Web, Innovative Laundry, PWS Laundries and Sterling Equipment.  These vendors are the key players on our top-15 vendor list.  We have attended Trade Shows with some of these vendors and have assisted them in providing their customers the information and education pertaining to front-loaders.  Postcards and other marketing materials have been created to help increase awareness about the rebates being offered as well as the energy savings that are involved.

We are continually working with the local water agencies.  Constant contact with key members of the major water authorities is vital, and allows us to share valuable ideas and information, which will result in increased customer participation.  Meetings have been initiated with local water agencies in an effort to make any necessary changes or implementations to allow the program to operate more efficiently.

The CLP Marketing Team continues to work with multifamily Property Managers and their Management Groups.  Association meetings are being attended as well to help educate several Property Owners and Management Groups at once. When we are not meeting with Route Operators and Distributors, we are visiting apartment complexes, Laundromats, hotels/motels and any other locations that have common laundry facilities.

The purpose for this localized marketing is to raise awareness to the property owners about the Coin Laundry Program and its benefits in hopes that their interest is stimulated enough to take the extra step and request front-loaders from their current Route Operator or purchase new qualified machines to replace existing old top-loaders.

With the Route Operators and Distributors pushing for the front-load business and the end user pulling to get front-loaders in their facility, we should expect our program to continue to bring in a sufficient number of rebate applications and increase the number of energy efficient front-load machines, which in the end will allow us to fulfill our contractual obligations.

- Direct Implementation Activities

During the 1st quarter a total of 605 gas-heated washers were installed and inspected. Other measures included: 171 pipe wrap units, 141 interior CFLs, 785 exterior CFLs, and 1706 T12 to T8 retrofits.

This activity provides SCG and SCE savings of 39,418 therms and 84,426 kWh of annual energy savings plus a peak load reduction of 19.57 kW. This represents a significant increase above the implementation activities during the 4th quarter 2007. A separate EXCEL report has been provided with this quarterly report which summarizes both quarterly and energy savings data for the Commercial Laundry Program.

- Program Performance/Program Status

PROGRAM IS MEETING EXPECTATIONS:

Explanation: Program goals were modified during 2007 to recognize the resistance by manufacturers to move away from top load commercial washers (and the attendant on-going discounting of top loaders to their customers). We have continued to work diligently with end-users (with the CLP cash flow modeling programs), to educate them on the financial benefits for making their next purchase (or lease) to be for a front load washer.

Our discussions with WEB during the 1st quarter identified a factor which can significantly increase the EUL (effective life of a washer for E-3 analysis). Specifically, over 200 washers were replaced with “rebuilt commercial washers” in recent weeks. This is a large increase in the number of “rebuilt or recycled washers and has caused a significant reduction in the number of applications for new washers during the 2nd quarter. If this continues, the E-3 analyses and work papers need be revised to reflect a much longer lifetime of commercial washers. However, such a change (while increasing TRC) is not the primary goal. It is possible that current financial markets have caused route operators and distributors to not replace washers with new equipment, but to focus on ways to cut capital expenditures. We will keep a close watch on this trend.

- Program Achievements

Perhaps equally important to making program goals during the 1st quarter, the following exhibit demonstrate the effect the CLP has had in transforming the conversion from top load, to front-load commercial washers as indicated in the year to year comparison below.

This program has been shown to be cost effective and to make a significant impact on the number of front-load washers being used today. This early process evaluation has enabled the benefits of the program to be directly communicated to the end-use customer. It has also enabled the CLP team to implement design changes during the program to better meet the needs of the utility and the end user.

One of the most important achievements of the Commercial Laundry Program has been the greatly expanded collaboration in joint water and energy saving programs which has been achieved through this program. MWD (and their many participating water agencies) have worked closely with our Team and with the gas and electric utilities to make the separate water and energy rebate process less cumbersome for the end user. This program is one of the very few joint water-energy efficiency programs currently operating in California today.

- Changes in program emphasis, if any, from previous quarter. (New program elements, less or more emphasis on a particular delivery source, program elements discontinued, measure discontinued, budget changes, etc.)

In response to requests from Laundromat customer of SCG and SCE last year, our Team developed 3 new program elements:

  - a solar-thermal program element to displace energy in Commercial Laundromats

  - a multi-load (large commercial washer) element for use in commercial Laundromats

  - a new construction element (in response to both end-users and an SCE consultant)

The Work papers and E-3 analyses were submitted to SCG and SCE during the 1st. quarter. The development of these new program elements has been aided by the early process evaluation which has confirmed which components of the program have the greatest potential for cost effectiveness and benefits to the utility customer.

- Discussion of near-term plans for the program over the coming months (marketing, outreach efforts that are expected to significantly increase participation in the program).

See “changes in program emphasis”, above

- Changes to staffing and staff responsibilities, if any.

No changes in staffing during the 1st. quarter.

- Changes to the contract, if any.

No changes during the 1st. quarter

- Changes to contractors and contractor responsibilities, if any.

None

- Number of customer complaints received.

None

- Revisions to program theory and logic model, if any

None