Community Energy Partnership:

Building on Success

Natural Gas Efficiency

In the Southern California Flagship Model

Confirmation Number ____

Partner Cities

Irvine	Corona

Santa Monica	 Cathedral City

Moreno Valley	San Bernardino			Palm Desert	Monrovia

Brea	Tustin

West Hollywood	Santa Clarita

Partner Utility: Southern California Gas

Facilitating Partner: The Energy Coalition

This proposal is accompanied by three complementary 2004-2005 Program Proposals, being submitted separately:

Community Energy Partnership – The Southern California Flagship Model

Community Energy Partnership – Northern California Model

Community Energy Partnership -- San Diego Pilot Program

Contact Information:

Ted Flanigan, Managing Director

The Energy Coalition, 1540 South Coast Highway, Suite 204

Laguna Beach, California 92651

tflanigan@energycoalition.org

(949) 497-5110

Table of Contents

Executive Summary	3

Section l. Program Overview	5

Program Concept

Program Rationale

Program Objectives

Special Section: The Utility Partnership	9

Section ll. Program Process	11

Program Implementation

Marketing Plan

Customer Enrollment

Materials

Payment of Incentives

Staff and Subcontractor Responsibilities

Work Plan and Timeline for Program Implementation

Section lll. Customer Description	20

Customer Description

Customer Eligibility

Customer Complaint Resolution

Geographic Area

Section lV. Measure and Activity Descriptions	24

Types of Community Activities

Savings Assumptions

Section V. Performance Goals	33

Section Vl. Evaluation Measurement and Verification	34

Section Vll. Qualifications	37

Section Vlll. Budget	40

Section lX. Summary	41

Section X. Attachments	43

Executive Summary

This proposal includes Natural Gas Efficiency in the Southern California Community Energy Partnership flagship program, now in the works for five years. This $1.2 million program addition provides a major new program dimension to the previously electricity-savings only approach, effectively dovetailing gas and electric efficiency services for the benefit of hard-to-reach customers. With crews already going into thousands of homes to provide Community Energy Tune-Ups that provide electric-saving measures, why not address gas efficiency measures at the same time? With thousands of students gaining an appreciation of electricity through the PEAK program, aren’t they primed for education of natural gas, its safe and efficient use as the “prince of the hydrocarbons?”

| Southern California |  |  |  |  |
| --- | --- | --- | --- | --- |
| Community Energy Partnership City Partners |  |  |  |  |
|  | City | County | Climate Zone | Population |
| Original Six Cities |  |  |  |  |
| 1 | Irvine | Orange | 8 | 142,000 |
| 2 | Santa Monica | Los Angeles | 8 | 125,000 |
| 3 | Moreno Valley | Riverside | 10 | 142,000 |
| 4 | Palm Desert | Riverside | 10 | 40,000 |
| 5 | Brea | Orange | 8 | 40,000 |
| 6 | West Hollywood | Los Angeles | 8 | 35,000 |
| Project Expansion Cities |  |  |  |  |
| 7 | Corona | Riverside | 10 | 138,000 |
| 8 | Cathedral City | Riverside | 10 | 43,000 |
| 9 | San Bernardino | San Bernardino | 10 | 185,000 |
| 10 | Monrovia | Los Angeles | 9 | 35,000 |
| 11 | Tustin | Orange | 8 | 60,000 |
| 12 | Santa Clarita | Los Angeles | 9 | 120,000 |
| Total |  |  |  | 1,105,000 |

This information program proposal for the inclusion of gas efficiency into the Community Energy Partnership expands the scope and benefits of exciting collaboration of Southern California cities and utilities committed to delivering short- and long-term energy efficiency savings in California facilitated by The Energy Coalition, a 20-year old non-profit with a strong track record of helping energy users get maximum value for their energy costs. The Partnership builds upon the strong foundation created by the Six Cities Energy Project. This proposal supports the extension of the project in the original six partner cities and its expansion to six additional cities. The proposal is submitted by The Energy Coalition and The Gas Company on behalf of the cities of Irvine, Santa Monica, Moreno Valley, Palm Desert, Brea, West Hollywood, Corona, Cathedral City, San Bernardino, Monrovia, Tustin, and Santa Clarita.

Building a Model Approach

This proposal is part of four complementary proposals that constitute the building blocks of a model for the Community Energy Partnership approach for the delivery of efficiency services throughout the State of California. The other proposals extend the current Six Cities to twelve cities in the SCE service territory, take the Partnership model north to six cities within the Pacific Gas & Electric service territory, and initiate a pilot of the model with two cities in San Diego County. Because of the results achieved by the Community Energy Partnership over the past five years of implementation experience, the partner utilities can rely on savings generated in the cities for their energy planning and resource procurement processes.

Tenets of the Community Energy Partnership

- Cities and their utilities work together to deliver customized efficiency programs in select neighborhood energy districts.

- “Hard-to-reach” communities of customers are targeted for highly valued services.

- The PEAK Student Energy Actions program is at the core of the community energy districts.

- Relationship marketing opens doors for existing utility programs to further improve their effectiveness.

- A resource efficiency ethic is created, renewed and supported in partner cities.

And the Southern California Partnership will deliver results to its citizens:

- Over 50,000 participants

- 16,000 PEAK students and their families

- 8,000 households; 600 businesses

With significant gas savings for participants and communities:

- Nearly 1,000,000 therms of net annual savings

- Nearly 5,000,000 therms of lifecycle savings

- Millions of therms of “indirect” savings through raised awareness

Responsibility:  Instead of making energy the responsibility of the State, or the utility, the Community Energy Partnership turns the tables and gives ultimate responsibility for energy use to the citizens -- in fact, to “hard-to-reach” and traditionally underserved energy users. Through student programs, household energy tune-ups in low and fixed income homes, neighborhood community energy rallies with dual pronged educational features as well as the sale of discounted efficient products. Through a host of local community organizing activities, the Partnership raises awareness and sustains a focus on the community’s energy use.

At the same time, the Community Energy Partnership relies on its city partners to lead by example, capitalizing on the numerous economic, environmental, and social benefits that energy efficiency provides to municipal facilities, schools, homes, and small businesses.

Credibility: The cities that come together are diverse and powerful. As the Six Cities Energy Project partners have already demonstrated, they are poised to take action and to use their connections to the communities they serve to build viable initiatives. More importantly, their collective program designs and planning – facilitated by The Energy Coalition – stimulate a robust set of activities that “raise the flag” about the value of smart energy management. Building on each city’s good standing in its community, the Community Energy Partnership delivers “hard” savings while creating a long-lasting movement towards responsible resource use.

The Model: The Community Energy Partnership is a model for reaching heretofore neglected power consumers, such as seniors on fixed incomes. It has been developed conceptually for ten years and in practice for five. The Energy Coalition established the Regional Energy Efficiency Initiative with the cities of Irvine and Santa Monica and Southern California Edison (1999-2001). In the next iteration of the model, these cities mentored four other cities (2002-2003). Now six cities are poised to mentor another six cities. The Coalition is also prepared to expand the model by developing a city cluster in Northern California and a pilot program in San Diego.

The Potential: The Community Energy Partnership backs this proposal with five years of experience delivering measurable results in partner cities. Hard-to-reach customers are reaping the benefits of the program, creating a win-win for the economy and environment. For utilities, doors are opening, and the Partnership is primed to build on program success to provide an effective channel for utility programs to the hard-to-reach. The partnership builds and then continually strengthens a bridge between city residents and their utilities. Meanwhile, households are “generating” hundreds of dollars of savings, schools are generating thousands, and the communities are experiencing savings in the millions. And the potential is huge when tapping these customer segments: 5,000 – 10,000 MW of capacity savings and billions of therms by the year 2010.

Section l. Program Overview

a. Program Concept

The Community Energy Partnership is a complementary delivery mechanism for energy efficiency that draws upon the strengths of a myriad of energy stakeholders to create a powerful synergy.  The partnership is multidimensional. On one hand it is between cities that are out to make a difference in the energy equation. Utilities can develop strong ties by working with active cities. It is about citizens and businesses working closely with community-based organizations to improve their financial condition. It is about dedicated school administrators, teachers, and students, working with their staffs and school districts to save precious resources. It is about hearing of a community event, and telling one’s neighbor. It is about creating Energy Champions in California cities.

The Community Energy Partnership

Statewide Model

The Southern California Flagship Program

Cluster #1: Six Cities

Cluster #2: Six Cities

The Northern California Partnership

Cluster #3: Six Cities

The San Diego Pilot Program

Cluster #4: Two Cities

The Community Energy Partnership model presented herein is nothing short of a movement. It involves people working together to foster responsible energy use and management in California cities. It involves leadership and tremendous levels of volunteerism.

* The Community Energy Partnership has been recognized with prestigious awards. In 2001, the Two Cities Energy Project was named a winner of the Governor's Environmental and Economic Leadership Award. In 2002, PEAK Student Energy Actions was awarded a 2002 Flex Your Power Award.

With five years of experience under its belt, The Energy Coalition has learned how to effectively work with cities and their serving utilities to engage the public in changing the face of California's energy equation. This proposal will support the expansion of the Community Energy Partnership model to twelve cities in Southern California with natural gas efficiency.

In every community, the Community Energy Partnership model’s approach is two-fold:

Raise Awareness: The Community Energy Partnership is rooted in education of hard-to-reach customer segments. Without an understanding of why efficiency makes sense, people will watch measures come and go. PEAK Student Energy Actions lessons, Energy Rallies with guest speakers, Quizzes and Fact Sheets distributed through Tune-Ups -- all provide persistent explanations of the benefits of efficiency. The ultimate goal is to change the way people and businesses view and use energy.

Target Participants

PEAK Students

PEAK Households

PEAK School Districts

Municipal Leaders

Mobile Home Residents

Apartment Dwellers

Community Event Participants

Homeowners in Multifamily Settings

Small Business Owners

Create Immediate Savings: The project also delivers a stream of immediate, "hard" savings through product distributions and installations. The aspect is particularly valued by low-income participants.

*  Two months after she'd completed an in-home Tune-Up in a rent-controlled building in Santa Monica, one of our contractors received a call.  "Gaby, before you came, my bill was $66," said the senior resident.  "And since the Tune-Up, it is only $46.  I just wanted to call and thank you."

b. Program Rationale

There is a strong rationale for expanding the Community Energy Partnership.

New Delivery Channel:  The Community Energy Partnership is a successful model approach for the delivery of efficiency services to hard-to-reach customers, presenting the State of California – as well as its four major investor-owned utilities – with a promising complement to current statewide efficiency programs.

Capacity Potential: The Community Energy Partnership model, ready to be tested in each major utility service territory in the State, also has huge ramifications to the State’s power system. If fully flexed on the electricity side, it has the potential to deliver 5,000 – 10,000 MW of capacity to the State from end-users heretofore largely disregarded as sources of “negawatts” or dispatchable capacity.

Running with the Ball! Currently all six cities in the project are eager to extend their initiatives. The cluster of cities is working well, the program designs are effective, the Coalition has built a solid track record of implementation experience and infrastructure but the success – albeit on track with project targets – is akin to the tip of the iceberg. Can it be replicated and maintain its high levels of enthusiasm and results? We are eager to prove that it can, and are joined by cities and citizens ready to “take the controls” of their current energy use and energy future.

Program Designation: Hardware / Incentive Program

1. The Community Energy Partnership is a hybrid model approach that incorporates both information and incentives to increase energy efficiency within California cities. Its primary focus is community organizing which is inherently an informational type of activity, but a unique feature of the program is that it couples organizing with potent efficiency demonstrations and other forms of community efficiency promotions.

2. The Commission requires that we present a recommendation as to the designation of the program as either a “hardware / incentive program,” or an “information program.” While we are uncomfortable with these distinctions, we herein classify the Community Energy Partnership as a “hardware / incentive program” because it was previously approved by the Commission under that designation. We also believe that the approach is generating real and sustainable savings.

3. We caution that the preliminary savings estimates presented in the narrative proposal and accompanying workbook are just that: They are preliminary savings estimates that have yet to be qualified as bona fide savings. The Energy Coalition’s current 2002-2003 third party initiative – the Six Cities Energy Project – was filed as a hardware/incentive program, but at this time its results have not been fully evaluated. In fact, given the nature of the program, the proof of savings that stem from behavioral change will not be forthcoming for a number of years.

c. Program Objectives

The Community Energy Partnership proposed has three main objectives:

Delivering Value in Partner Cities: The first program objective is to deliver real value to program participants and their cities. The project focuses on power consumers most in need, who tend to be the most disenfranchised by utility services. Many of these consumers don’t speak English; some are home-bound. At the city level, school districts and cities themselves are financially “against the wall” and thus get tremendous benefit from efficiency savings.

Sustaining Hard-Earned Successes: A second objective is to sustain hard-won program victories from the prior programs in Southern California. A knowledgeable program management team is in place at the Coalition, with unique experience in designing and launching community-based programs. The Partnership model’s foundation is firm and additional work can be done expeditiously and more cost-effectively.

Enhancing the Delivery Approach: The third objective is to enhance the program design and bring ever-greater benefit to the communities involved. In 2004-2005, the program will be enhanced by:

- Incorporating natural gas-savings measures.

- Featuring more sophisticated community outreach.

- Adding the promotion of existing statewide and local utility programs.

- Involving dedicated utility Energy Managers, as described below.

Special Section:  The Utility Partnership

This proposal presents a proven partnership of cities engaged with the Coalition. Now this highly effective partnership will be strengthened by close links with both electric and gas utilities that serve each city. The model will now find the optimal synergy between utility programs and the Community Energy Partnership third party initiative. And it represents an investment of resources and time by the partners. The Partnership is the beginning of an ongoing stewardship of natural resources, local and state economies, and the global environment.

The utility partnership model presented here accomplishes several objectives:

- The utility partnership will maximize societal benefit by helping residents and businesses in the partner cities take full advantage of utility services.

- Fully utilizing utility programs will avoid duplication, stretching program dollars and allowing The Energy Coalition to dig deeper with special offers in the partner cities.

- Cities will enhance their relationships with their utilities to create explicit dialogues between consumer needs and utility services.

- The utilities will get a first-hand opportunity to fully utilize this form of community organizing and complementary delivery mechanism.

Background

The Energy Coalition has a history of working in partnership with utilities, notably Southern California Edison but also with The Gas Company, PG&E, and LADWP. In fact, the Coalition was formed over 20 years ago to form “Energy Cooperatives” that effectively brought the capacity savings of large commercial and industrial customers to Edison. In 1999-2001, The Energy Coalition was the managing partner of the Two Cities Project, also known as the Regional Energy Efficiency Initiative (REEI), a working partnership with Edison and the cities of Irvine and Santa Monica. The Six Cities Energy Project is a third party initiative selected by the CPUC as a local cross-cutting program for 2002-2003 that has been contractually restricted in the ways that it may partner with Edison, limiting the synergies that will now be explored.

Working closely with the local utility provides the opportunity for a stronger, more comprehensive program. In this partnership, The Energy Coalition is pleased that all parties agree to adhere to the current working model and to maintain high degrees of flexibility and creativity. There is much work to do in the development and focus needed to bring the Partnership process to fruition. The Energy Coalition understands the need for changing perceptions of end-users and integrating community interest and initiatives with utility resources to forge a sustainable energy partnership that serves the end-user, the utility, and the State of California.

The Gas Company  2004-2005 Program Reference

Southern California Gas has included the Community Energy Partnership in its comprehensive 2004-2005 portfolio of gas energy efficiency program plans, highlighting the company’s commitment to the model approach and this proposal.

For the 2004-2005 program years, the Community Energy Partnership will take the best of both worlds. The Partnership will be managed by The Energy Coalition on behalf of the partner cities to assure that it fully maintains its program integrity or its flexibility to deliver results. The program will continue to be managed by the cities and the Coalition, while building in the synergy of utility programs. In this format, program dollars can be most judiciously applied to activities that standard utility offerings do not address.

Project Centers

The Community Energy Partnership is a hands-on approach to energy efficiency program delivery. We’ve learned that we need more, not less, staff regularly in the cities to build a program reputation to sustain enthusiasm and deliver ongoing results. To effectively organize communities, “real people, on the ground” have to be pushing for and planning events and program strategies. The 2004-2005 program features Project Centers that add personnel to the project on a per-city basis, and more importantly provide a local presence and become the physical manifestations of the Partnership.

A Project Center will be established for each six city cluster. These centers will keep the project management local and “in touch,” a key element of past program success. They also address the considerable logistics associated with the project management. Ideally, a project city will house the Project Center within its facilities. At each center there will partner staff offices, a conference room, and ample storage for project materials.

Project Energy Staff: At each of the Project Centers there will be a staff of four full-time equivalents that reflects the spirit and value of the Partnership. The core project management staff at the Center will be made up of Coalition, Edison, and Gas Company personnel, working shoulder-to-shoulder with city Team Leaders, their staff, and volunteers. The Centers, as well as all Partnership activities in the cities, will be supervised by senior management at The Energy Coalition.

Project Center Staff Composition

- Project Manager (full-time Coalition employee)

- Campaign Coordinator (full-time Coalition employee)

- Partnership Energy Manager (0.5 FTE Gas Company)

- Partnership Energy Manager (0.5 FTE Edison employee)

- Project Assistant (full-time Coalition employee)

Gas Company Dedicated Staff Position: To increase the project’s linkage to existing gas efficiency programs and services, a half time Gas Company professional will be dedicated to the project and to bring the full force of appropriate Gas Company incentives and services to the partner cities. His or her title will be Partnership Energy Manager. The other half of this dedicated Energy Manager’s time will be spent managing the efficiency activities associated with the San Diego Pilot Community Energy Partnership program.

A full-time Edison Energy Manager will split his or her time between the two centers. Each Energy Manager will also take back lessons learned from the Community Energy Partnership to the respective utilities to embellish statewide and local programs with key lessons learned from the Partnership.

Executive Guidance

Prior experience has demonstrated the value of having a project Executive Committee to provide guidance through quarterly meetings and as needed. The Executive Committee will be made up of officials from the cities, Edison, the Gas Company, and the Coalition. Committee members will set strategic direction, guide work plans and approve the budget based on forecasts of quarterly expenditures. The Executive Committee is yet another dimension of the partnership approach, this time featuring partnering at the policy level.

Section ll. Program Process

a. Program Implementation

The Community Energy Partnership works within communities to deliver a value of the need to sustain smart energy management in our partner cities and in the State. In the broadest terms, this is done by raising awareness, fostering trust, and creating networks of understanding of the win-win benefits that efficiency affords for communities’ collective best interests. The Coalition has repeatedly found that “hard-to-reach” citizens and businesses -- from students to seniors -- are far from reluctant to engage in community activities. Rather, when approached with respect and understanding, they are pleased to have a means to “plug in” and are eager to reap the benefits of energy efficiency.

Working with Cities

The Community Energy Partnership process features several principles.

Focusing on Energy Districts: The Community Energy Partnership is unique in its targeted delivery of energy efficiency services. It focuses its services in select geographical “Energy Districts.” Within each of these districts, a critical mass of activity takes place to raise program awareness and visibility.

Tailoring Initiatives to City Needs: In each city and energy district, the Community Energy Partnership captures unique needs and interests and builds a stream of customized programs. Like ripples from rocks falling in a pool of water, the consequences of these initial projects converge in a way never before experienced by the classically underserved utility customers.

*  During the planning process for an Energy Rally at The Groves, a mobile home park in Irvine, members of the committee reported concerns within the park about water quality and water use. The Energy Coalition promptly contacted colleagues at Irvine Ranch Water District to engage their participation in the Rally.

City Role in the Process:  Through a collaborative process of relevant stakeholders within the city, the Partnership first identifies potential projects and energy districts. Here the discussion is broad and unrestricted. What are each city’s objectives in energy management? How can the city’s energy plan be updated to reflect the current needs of its constituents? Which neighborhoods are in greatest need? Which have the greatest potential to save energy, to support the local economy, and to preserve the environment? How can the Community Energy Partnership help the city achieve these goals? What project, state, federal, and other resources can be tapped? What resources does The Gas Company bring to the table?

The Strategic Build-Out of Initiatives: A strategic plan is then developed for the delivery of services to target participants in each city. The approach flourishes with community input. And it is grounded in incremental and sequential developments. Whichever initiatives are begun must effectively set the stage for the next. And it is this multiplicative effect that provides the basis for the synergy of results that leads to high levels of participation and penetration. This build out of activity is at the root of the Community Energy Partnership process.

*  The City of Palm Desert assigned a new employee to serve as team leader for the Six Cities Energy Project. Within a month, the City had begun on its first energy plan. Within six months, the City's planned new Visitor's Information Center took center stage at a design charrette focused on efficiency and green building standards. Just last month, the Team Leader was invited to participate in a conference being held by a national retailer preparing to move to Palm Desert and wanting to train all its people in more energy-efficient building methods.

Leveraging Funds: The program process works to leverage funds. The Community Energy Partnership is a channel for utility services to the partner cities and their hardest to reach citizens. The Community Energy Partnership will also provide key linkages to Southern California Gas programs, Edison programs, water efficiency opportunities, and community development and small business services. Project funds are only expended where other funding is not available and are used to strategically raise awareness through demonstrations and outreach.

###### Community Involvement: Community education touches the community at all levels.  Program participants include:

###### Senior Centers

###### Apartment Complexes

###### Mobile Home Parks

###### Neighborhood Associations

###### Community Centers

###### Homeowners Associations

###### Parks and Recreation Departments

###### Community Libraries

School Classes and Sports Teams

Senior Retirement Communities

Fire and Police Departments

Small Business Groups

Chambers of Commerce

Boy and Girl Scouts

Service Clubs (Rotary, Kiwanis)

College Fraternities and Sororities

Private Businesses

Government Agencies

Like the partnership approach itself, the process of organizing communities to take greater responsibility for their energy use and management is also multidimensional. It involves building relationships with city governments, and with their constituents. It also necessarily involves bringing in all manner of relevant stakeholders into the process. For the program to succeed, it taps volunteers and the commitment of countless individuals to save energy and money and the environment. Partnership activities involve hundreds and thousands of individuals.

- Moreno Valley's Torchiere Trade-In drew an estimated 2,000 participants from the community. Most were there to trade in their lamps, but more than fifty people came as volunteers to support the activity. The City donated its parking lot and waste management services to deliver and pick up dumpsters. Police Explorers directed traffic. Parks and Rec volunteers set up tents. And staffing "the line" were city employees, young people from the Youth Opportunity Center, Girl Scouts and their Scout Master, church members, optimists, and a variety of boyfriends, girlfriends and family members -- all there because they believed it to be a worthwhile way to spend their Saturday.

Working within the Community

Community Organizing: Community education and organizing is the basis of the approach. The Community Energy Partnership focuses on educating entire communities so that they can take the controls of their own energy futures and craft sustainable paths for themselves and future generations.

Building Trust: The Community Energy Partnership model features repeated face-to-face interactions with citizens and their community leaders, coupled with the immediate gratification of short-term efficiency gains. This lays the foundation for long-term program sustainability. Through the Partnership, trust is built and leads to the development of a resource efficiency ethic that ultimately sustains efficiency gains.

PEAK at the Core: At the core of the Community Energy Partnership model is the PEAK Student Energy Actions program. No other project area is as profound; no other project focal point has the potential to create a “generational transformation of attitudes.” But there is no question of the enormity of the challenge of getting any program into a school district. It takes time, time, and more time.

PEAK is rooted in a comprehensive curriculum developed by The Energy Coalition, reinforced with special events such as contests, exchanges, summer programs, fundraisers, clubs, etc. PEAK students become empowered to save energy at home, at school, and in their communities. PEAK students gain a thorough understanding of the electricity story from power plant to end-use, and why smart energy management is critical to fostering a “healthy energy future.” Students also gain a special understanding of peak demand and its environmental, economic, and political dimensions. This proposal extends PEAK into the realm of natural gas use and management, creating an important linkage between electric and gas uses and efficiency services.

Delivering Bundles of Valued Services: The Community Energy Partnership approach has proven to be an appealing model from a participant standpoint not only for its energy programs, but because it bundles services that until this time have been disparate and thus sporadically utilized. Project participants are exposed to “the bigger picture” of local, state and global energy resources, and now they be presented with a variety of savings opportunities through electric and gas efficiency services.

b. The Marketing Plan

The Community Energy Partnership presented herein involves seven customer segments or what we call project participants, and two focal areas, notably “community promotions” and “municipal activities.” Each of these end-use areas and programmatic activities requires its own marketing strategy and execution. By their very nature, community education activities take a number of forms and are cross-cutting in nature, requiring custom articles for community newsletters, video productions, press releases and video news releases, e-mail communications, printed materials for distribution to participants… all manner of communications appropriate to each audience.

Campaign Coordinators: To accomplish the multifaceted marketing function, The Energy Coalition depends on the skills of Campaign Coordinators who are responsible for developing overall marketing plans as well as detailed activity plans for each activity. Naturally this is also done on a city-by-city basis. Experience to date has made it clear that community organizing is not an engineering function, nor an economic argument, but about effective communications skills.

* When The Energy Coalition planned an Energy Rally for residents of a Section 8 retirement home in Irvine, it became clear that many would not come because they spoke only Farsi, Chinese, or Russian. Working with management, the Campaign Coordinator found "Champions" from within the community who went to each of their friends with explanations in their own language. In addition, the Coalition sent out letters to adult children of residents, urging them to be sure their parents came to the meeting. As a result, every one of the residents was able to receive not only a free fan and free CFLs, but also was able to sign up for special low-income energy and social programs.

The City Platform: The most profound form of marketing is marketing with substance, and this is explicitly why the city partners become engaged in the Partnership: They see value in the project and are happy to present it to their constituents. The cities “market” the project on their web sites, in newsletters, through special mailings, on their city television stations, in city council meetings, and in many other ways. This city platform gives the project invaluable credibility.

* Partner city Moreno Valley has taken so enthusiastically to energy efficiency that it has created its own city program, PowerWise, complete with logo, website presence, and city TV spots. Similarly, Irvine created the Irvine Saves!

Relationship Marketing: Experience to date has also shown that the success of the project is largely based on “relationship marketing,” whereby program participants tell their friends, families and neighbors about the Partnership. “My brother-in-law lives a few houses away. Can he participate as well?” Participants in the Tune-Ups become Energy Champions and program advocates. City staff members become ambassadors throughout the cities, and PEAK students turn up in lots of venues championing the program and its mission of creating a “healthy energy future through smart energy management.”  Appropriate marketing specialty items -- T-shirts, window decals, stickers, frisbees, etc. -- reinforce program messages.

Media Opportunities: The Community Energy Partnership is a colorful story and presents countless media opportunities. Taking advantage of these – aggressively working the media through press releases and repeated contacts – serves to build the “buzz” about the program and to continually reinforce the project. For example, the PEAK Energy Adventure was featured in the Irvine World News; Community Efficiency Tune-Ups were recently featured in the Home section of the Riverside Press Enterprise as a unique Moreno Valley opportunity. The Coalition has learned that success to date in the six cities has been a function of persistence and diligent follow-up, coupled with healthy doses of coordinated publicity.

The Community Energy Partnership has evolved dramatically in the past five years, and is now poised for its most sophisticated implementation experience. For the 2004-2005 program years we plan significantly expanded marketing and outreach effort within the partner cities to further reinforce the meaning and presence of the Community Energy Partnership. Each city’s campaign will feature a combination of the following strategies:

- Promoting the message with targeted Energy Rallies with City Officials

- Accessing City TV and Public Access to reinforce the message and publicize community events

- Spreading program information through local and regional media (in multiple languages)

- Using PEAK students and schools to promote all project activities

- Running Student Forums on energy and the environment in local malls

- Using elected City Officials to facilitate Energy Town Halls

- Sending targeted direct mail to promote Energy Rallies and Tune-Ups

- Working with local organizations, from churches to Chambers of Commerce, to reach their members

- Fully tapping the City web sites to promote energy management

- Linking project partners with statewide energy initiatives at the local level

c. Customer Enrollment

Participants enroll in the program in a number of ways. For instance, at community promotions participants sign in and purchase discounted products. In other cases, such as the PEAK Student Energy Actions program, enrollment is through the school district itself. For the Tune-Ups, enrollment takes a more conventional marketing approach with leads qualified and then participants scheduled by the installation contractors participating in the program.

d. Materials

Efficiency measures (lamps, fixtures, aerators, etc.) used as part of the Tune-Up programs are presented in the Tune-Up Checklist attachment. Other program materials fall into several categories.

Student educational materials:

- PEAK Curriculum (lesson plans) -- provided for each teacher

- PEAK Software -- individual CD for each student

- PEAK supply kit -- for each classroom

- Take-home materials for parents

Educational materials for consumers and businesses:

- Household Tune-Up Checklist

- Household Efficiency Recommendations Fact Sheets

- Small Business Efficiency Tune-Up Checklist

- Small Business leave behind ("Big Ideas for Small Business")

- "What's Your Energy I.Q.?" --  Quiz for use at fairs and meetings

- "Quick Check: Rate Your Home on Energy Efficiency" -- for classes

Promotional material for events:

- Partnership brochure -- basic marketing tool

- Customized flyers -- for local mobile home parks, apartment complexes, etc.

- Ads -- for local and city newspapers

- Project banner

- Audio-visual materials for public meetings (slide show, posters, etc.)

- "Door hangers" for Community Efficiency Tune-Ups

- Stickers, imprinted pens, frisbees, etc.

Program management materials:

- IMPACT -- quarterly newsletter

- Quarterly status reports -- for each participating city

- Team Leaders Bulletins

- Powerpoint presentations -- for city and Coalition staff use

- Tune-Ups Database – to track installation details

- Press releases and press kits

- Website

e. Payment of Incentives

The Community Energy Partnership delivers customized products and services to its various audiences. Any "incentive" payments are not of the typical rebate variety.

| 1. PEAK Students | Schools are encouraged to run art contests, for which the Partnership provides appropriate recognition items and prizes. In some schools, parent-teacher organizations help sponsor fundraisers for their school programs. In this case, the Partnership provides efficient products at cost or at a discount. |
| --- | --- |
| 2. PEAK Households | Households receive no direct products or services but are incented by their PEAK students to find means of cutting power and gas bills and to be responsible citizens and parents. |
| 3. PEAK School Districts | $5,000 of Partnership funds is allocated for each school district for gas efficiency products or services. This could include technical assessments, marginal costs for higher-efficiency equipment, etc. This complements $20,000 per city provided to support electric efficiency. |
| 4. Municipal Activities | $5,000 of Partnership funds is allocated for each city to spend on Partnership-approved activities or products. This could include developing the city's energy plan, technical assessments, a design charrette, marginal costs for higher-efficiency equipment, etc. (Same $20,000 electric efficiency complement.) |
| 5. Community Promotions | Generally, educational materials and efficiency measures are provided to consumers at a significant discount, or at no cost. The Partnership may work with a specific organization to mount an energy efficiency promotion that serves as a fundraiser for the group. For city-wide events, the Partnership may pay for commercial advertising, booth rental space, etc. |
| 6. Mobile Home, Rental and Owner-Occupied Multi- Family complexes | Energy Rallies bring residents together to educate them and to kick-off in-home Community Efficiency Tune-Ups. In addition to the measures associated with the Tune-Up, the Partnership may provide advertising flyers and refreshments for residents attending the Rally. |
| 7. Small Businesses | In addition to Small Business Efficiency Tune-Ups, the Partnership will support community events and advertising to promote its Small Business "Energy Champions." |

f. Staff and Subcontractor Responsibilities

This unique project requires flexible staffing. Full-time Partnership staff is dedicated to comprehensive project management and to managing staff in the project centers. To sustain its cost-effectiveness, the Partnership hires subcontractors on behalf of the partner cities to address precise program needs that stem from the Partnership’s highly customized approach to community energy efficiency.

g. Work Plan and Timeline for Program Implementation

The program is managed by quarters. The basic work plan and timeline is as follows:

First Quarter 2004

- Coalition briefs City Councils

- Memoranda of Understanding signed by City Manager

- Convene first Team Leaders' meeting

- Hold kick-off program with statewide event

- Conduct meetings with school districts

- Develop Executive Committee; schedule first meeting

Second Quarter 2004

- Executive Committee meeting

- Select and visit Energy Districts

- Develop city-specific plans

- Hold individual city kick-off events

- Execute PEAK Student Energy Artwork contest

- Develop the EM&V Plan

- Select and train contractors for Tune-Ups

Third Quarter 2004

- Hold first city-wide Community Promotions

- Schedule special Energy District activities

- Market Community Efficiency Tune-Up programs

- Market Small Business Efficiency Tune-Ups

- PEAK Energy Adventure Summer program

Fourth Quarter 2004

- Executive Committee meeting

- Deliver Community Efficiency Tune-Ups

- Deliver Small Business Efficiency Tune-Ups

- Continue with city-wide events

- Hold PEAK teacher training in new districts

- Conduct mid-point project evaluation

First Quarter 2005

- Address City Councils with mid-course update

- Maintain momentum with neighborhood Tune-Ups

- Hold special events as appropriate

Second Quarter 2005

- Executive Committee meeting

- Plan broad-based public relations effort based on results to date

- Schedule phase two city-wide events

- Laud PEAK Artwork contest winners at City Councils

Third Quarter 2005

- Complete Tune-Up activities

- Ramp up city events for robust program close

- PEAK Energy Adventure Summer program

Fourth Quarter 2005

- Executive Committee meeting

- Statewide Conference on the Model: Lessons Learned

- Make plans to support on-going activities in the cities

- Complete evaluation activities

First Quarter 2006

- Final Evaluation Report

- Publicize results

- Debriefing with project partners

Section lll. Customer Description

a.  Customer Description

The Community Energy Partnership focuses on the following nine areas with target participation numbers presented:

Focal Point	Participation Targets

1. PEAK Students	16,000

2. PEAK Households	12,000

3. PEAK School Districts	8

4. Municipal Activities	12

5. Community Promotions	16,000

6. Mobile Homes	2,400

7. Rental Apartments	2,400

8. Owner-Occupied Apartments	2,400

9. Small Businesses	600

Total Project Participants	51,828

The total number of participants is approximately 5% of the aggregate population of the twelve cities. These participants become Energy Champions, multiplying the project’s effect throughout the cities involved. This speaks to the educational aspect of the program: In order to transform communities’ energy usages, and to make communities responsible for their energy consumption and energy future, participants must understand not just “how” to save energy, but “why” doing so has local, state, national, and even global ramifications.

1. PEAK Students: 16,000

The PEAK Student Energy Actions program will continue in the cities of Irvine, Palm Desert, and Santa Monica for the 2004-2005 program years. With the existing school districts currently on board, 6,000 students will be involved with PEAK over the two-year proposed program period. Assuming that PEAK is introduced in at least five additional cities during the program period, another 10,000 students will be exposed to the PEAK learning experience, for a total of 16,000 students.

2. PEAK Households: 12,000

The PEAK Student Energy Actions program teaches the cities’ youth an appreciation of how to manage energy consumption. Armed with this awareness and knowledge of how to take action, and simulations of their homes’ optimal energy use, PEAK students take the message home. And that’s where the action begins as PEAK Students become “household energy managers.” Evaluations of the PEAK program reveal tremendous savings effects in student households.

* Quote from Santa Monica PEAK teacher: "We wouldn't hope for a repeat, but one of our students' homes burned down. As the parents rebuilt, they turned their new home into a demonstration project for energy efficiency, with efficient fluorescent lighting throughout, energy-efficient appliances, low-e windows, etc. -- all thanks to inspiration and knowledge they had received from their child through our program."

For the 2004-2005 program years, the Community Energy Partnership will engage approximately 12,000 PEAK households. This participation is 75% of the number of PEAK students, reflecting the fact that often a household has more than one child in the program, and that some older students have already been through the program and thus their homes’ savings are not double counted. PEAK households, incidentally, cut across income brackets and represent an area where the Community Energy Partnership addresses single family homes.

3. PEAK School Districts: 8

During the 2004-2005 program years, The Energy Coalition will work with a total of 8 school districts to implement the PEAK Student Energy Actions program. This includes the three districts already on board and committed to PEAK.

3 School Districts with Ongoing Programs

District	Number of Schools Involved

Irvine Unified School District	24

Santa Monica Malibu Unified School District	6

Palm Desert Unified School District	4

2 School Districts Primed for Pilot Programs

District	Number of Schools Involved

Moreno Valley Unified School District	3

Brea Olinda Unified School District	--

3 New School Districts Yet To Be Identified

4. Municipal Activities: 12 Cities

To be effective in their communities, partner cities must be actively involved in getting their own houses in order. The Community Energy Partnership promotes a number of planning and management functions for the City itself to become a model energy consumer and a champion of smart energy management over time. The Community Energy Partnership requires its partner to be actively engaged in the smart energy management of its own facilities. Therefore, in terms of participation, all 12 partner cities will be involved.

5. Community Promotions: 16,000 Participants

Community organizing takes many forms and unexpected directions and involves all types of participants. To get students, households, and businesses “fired up” about the potentials for energy efficiency, the Community Energy Partnership hosts a variety of special events. Community Energy Rallies often use discounted product and face-to-face interaction on the benefits of efficiency. These promotions are generally held within the Energy Districts defined by the partner cities and serve to support participation in subsequent initiatives such as Community Efficiency Tune-Ups and Small Business Efficiency Tune-Ups.

* "Hard-to-reach” energy consumers tend to live in mobile homes, rental apartments and owner-occupied apartments. These consumers are identified by the respective cities and then become the focus of the Community Efficiency Tune-Ups. In turn, these customers become Energy Champions within their communities.

6. Mobile Homes: 2,400

The Community Energy Partnership has an impressive track record of working with mobile home communities. Often occupied by seniors on fixed incomes, these communities are specifically included in the Energy Districts by the partner cities and become focal points for Energy Rallies and Community Efficiency Tune-Ups.  Partnership activities are often specifically designed to bring low-income-qualified utility and social services into these communities.

7. Rental Apartments: 2,400

Rental apartments are fundamental to the Community Energy Partnership. They are often occupied by low-income consumers in need of lower utility bills as well as increased comfort and safety. The project brings Tune-Ups to this customer segment as well as Energy Rallies and other forms of special events. In many cases, programs must take into consideration those residents whose English language skills are limited.

8. Owner-Occupied Apartments: 2,400

Owner-occupied apartments in the select Energy Districts are also a target for the program. These owners are often among the most highly motivated to understand and make changes in their energy use, and they often use Community Energy Partnership resources as a springboard to other energy-saving activities. The project goal is to reach 2,400 such units in the 2004-2005 program years through Tune-Ups as well as Energy Rallies and other special events.

* In the city of Santa Monica, The Energy Coalition has appeared on stage and exchanged leads with another city-supported non-profit organization, Sustainable Works, whose 8-week-long self-help educational programs focus on a variety of conservation topics.

9. Small Businesses: 600

The Community Energy Partnership also focuses on local small businesses that often form the fabric of the community. Small Business Tune-Ups address lighting, air handling, and refrigeration efficiency opportunities head on – and now will also focus on space and water heating -- while checking into business owners’ unusual energy use and problem areas. Small Business Energy Champions will also serve as emissaries to colleagues and customers. During the 2004-2005 program years, the Community Energy Partnership will deliver 600 Small Business Efficiency Tune-Ups to small businesses in the twelve partner cities.

*  Small Business owners who participate in a Tune-Up become "Energy Champions." They receive a decal for their window and energy tips handouts for their customers, and appear before the city council or in city-wide advertising to promote energy awareness.

b. Customer Eligibility

Many Partnership activities -- Energy Rallies, Community Efficiency Tune-Ups -- are focused in discrete Energy Districts selected by the City. Other activities are specifically open to all residents of the City, such as Energy Fairs and discounted efficient product sales. Since the purpose of the program is to create widespread awareness, there is no intent or restriction to limit participation to low-income or otherwise income-qualified families, or to strict geographical limits. This position has allowed for marked increase in participation levels that in turn foster a successful project in the community.

c. Customer Complaint Resolution

The Community Energy Partnership works hard to sustain the best possible reputation, for without it, the program will fail. Fortunately, because the program is totally voluntary, and because most measures are offered or installed at little or no cost, complaints are rare. However, to maintain the highest quality of service, contractors working with the Partnership are selected and trained in all facets of installations -- and education -- that they provide. In addition, contractors are contractually required to support their work for one year through warranties. As an example, when citizens receive measures as part of a Partnership activity, they also receive the 800 number of the manufacturer or distributor.

*  Two weeks after the recent torchiere trade-in in Moreno Valley, the torchiere distributor arranged to return to the city hall parking lot where the trade-in had been held in order to resolve any problems people may have had with their lamps. This follow-up service was advertised to all participants.

*  No matter how well-prepared or well-intentioned the contractors, things can go wrong. After one mobile home Tune-Up in Brea, the air conditioner wouldn't turn on. On his own time and nickel, the contractor traced the problem to a faulty exterior cut-off switch and repaired it.

d.  Geographic Area

The Southern California Community Partnership extends to cities located within a one-two hour drive from Los Angeles. -- depending on traffic!

Section lV. Measure and Activity Descriptions

The Community Energy Partnership reflects the spirit of community organizing. It is about bringing people together who are empowered to make a difference and who are committed to creating a safe and healthy energy future. And the power of the model is nothing short of fantastic: By bundling electric and gas services together, households can realize hundreds of dollars of annual savings, schools can realize tens of thousands of dollars of savings, and cities can realize millions of dollars of savings that can be reinvested to strengthen their economies.

To realize these potentials, the Community Energy Partnership focuses tailored services on nine community segments to raise awareness and get measures installed. This section presents a sector-by-sector description of the types of gas savings measures that result and the assumptions that have been used to substantiate the performance goals presented. The following paragraphs also present assumed participation rates and energy savings values for each of the nine focal points of the Community Energy Partnership.

# 1. PEAK Students

A key objective of the Community Energy Partnership is to create sustainable savings by building an ethic and community responsibility within partner cities and with their utilities to the greatest degree possible. There is no more important channel for this to develop than through the PEAK Student Energy Actions program.

Measure descriptions: During the 2004-2005 program years the PEAK Student Energy Actions program will be augmented to include natural gas activities and measures and thus corresponding savings. In particular, four lessons will be added to the PEAK curriculum, the PEAK 4.0 Simulation Software will be enhanced to include gas, special teacher training will focus on natural gas efficiency, and a host of special “gas features” will be added to the program. These actions will serve to enrich the program dramatically, giving students a far broader appreciation of the two major forms of household energy use rather than the current focus on electricity.

- New Gas PEAK Student Energy Actions lesson plans

  - Introduction to natural gas

  - Natural gas safety

  - Global gas use and management

  - The “gas bridge” to a solar hydrogen economy

- The Addition of Gas to the PEAK 4.0 Simulation Software

  - Space heating; addresses household insulation, building shell

  - Water heating

- Teacher Training on Natural Gas

- Special “Gas Features” throughout the school year!

Participation Rates: All 16,000 PEAK students projected for the 2004-2005 school years will take part in the gas efficiency focus proposed herein. To accomplish this goal, the enhancements to the program will necessarily have to take a high priority in the overall project management so that students in the 2003-2004 school year are presented with the information. Note, however, that some students will be exposed to PEAK and these gas-savings lessons in the fall of the 2005-2006 school year.

Savings Assumptions: No direct savings are presented for PEAK students. Instead the savings accrue in PEAK Households and PEAK Schools.

# 2. PEAK Households

Measure Descriptions: PEAK students become household energy managers, taking PEAK’s ethic of resource efficiency home and to their families. Their actions are multiple and diverse but focused on space and water heating measures. By raising awareness within PEAK households through the kids, new furnaces become high-e and noted to neighbors and extended family, windows and doors can get that much tighter, and clothes dryers now have sophisticated moisture sensors.

Gas savings actions – which in many cases feature their child’s newly learned information on smart energy management – are taken by parents voluntarily. We assume that each household will invest $50 in some form of gas efficiency – be it behavioral or through the installation of a highly efficient appliance -- in the next five years as a result of PEAK. In many cases these actions will be supported by Gas Company rebates, and the Community Energy Partnership serves only as a catalyst. The following is a list of gas-saving measures that may accrue through this aspect of the Partnership:

Space Heating Savings Measures

- New high-efficiency furnaces

- Replace furnace filters

- Better household insulation

- Better windows, doors, and skylights

Water Heating Savings Measures

- Highly efficient clothes washers

- High-efficient dish washers

- High-efficiency water heater installation

- Water heater insulation

- Hot water pipe insulation

- Water temperature check for optimal efficiency

- Behavioral: Use CW and DW only when full

- Install new high performance showerheads

- Install water-efficient faucet aerators

Gas Safety Reminders/Checks

Participation Rates: Assume 12,000 PEAK Households

Savings Assumptions: The Community Energy Partnership assumes that as a result of student participation in the PEAK program, the average PEAK household will cut its natural gas use by 10% for five years. (A parallel average value is used for calculating PEAK household electricity savings.) Since the average Southern California household uses 470 therms of gas per year (Energy Information Administration, Household Energy Consumption and Expenditures, 1997), we assume average annual household savings of 60 therms. When applying the Commission’s assigned net-to-gross for gas savings measures, each PEAK household will provide a net annual gas savings of 48 therms. Given 12,000 PEAK households during the project period, the total annual gas savings will be 576,000 therms.

# 3. PEAK School Districts

# Each school district participating in the PEAK Student Energy Actions program will also benefit from energy savings stimulated by students’ actions along with those of their teachers and custodians as energy awareness is raised on campus. One private school that taught PEAK slashed its campus electricity bill by 30%; another school realized 15% savings despite considerable construction on campus. Now for the first time, the Community Energy Partnership will also focus on gas savings on campus. This will occur in unique ways as already demonstrated in Irvine, Santa Monica, and Palm Desert.

PEAK Student Actions on Campus: The Energy Coalition and its partner cities will work closely with PEAK schools in a number of ways, from policy guidance to engineering assistance. One of the most encouraging aspects of the partnership is the linkage between PEAK students and school facilities personnel. In Irvine this has been promulgated by the development of PEAK Clubs that are made up of students that go on patrol to find campus energy waste. Irvine Unified now has a goal – reinforced with large barometers of energy savings successes – in the foyers of each school, of saving 10% on campus! Adding gas to this powerful equation may be challenging, but will serve to integrate each school’s energy resource efficiency perspective and ethic.

Sample School District Opportunities

- Developing School District Energy Management Plans

- Supporting PEAK Student Energy Patrols

- Engineering Analyses of School Facilities

- Design Assistance for New Facilities

- Incentives for High Visibility Demonstration Project

- Incentives for Leading School Efforts

- Training for Students, Administrators, and Facility Operators

PEAK Policy Initiatives: The Community Energy Partnership will also work with school districts and their facilities staffs to eliminate the split incentive between school districts that pay the bills for all school campuses, and the individual schools that have therefore not had the means to track their consumption, nor the incentive to do so. The Partnership will work with willing districts to overcome this barrier to energy savings at school and in some cases will benchmark energy intensity and then track monthly consumption for significant variations that represent savings potentials.

Savings Assumptions: For the purposes of this proposal, we assume that each of the participating school districts will cut its overall gas use by an average of 5% for a five-year period. We assume that each large school district uses 200,000 therms per year; that small school districts use 50,000 therms per year. (Note that the baseline assumptions presented are averages with key district variables being pool heating, age of systems, special events that extend operating hours, and amounts of space and water heating. (In the 2002-2003 fiscal year, the Irvine Unified School District used approximately 200,000 therms worth approximately $125,000). Using the 5% value for the average-sized school district that consumes 125,000 therms of gas, the gross annual savings per district will be 6,250 therms, providing approximately $5,000 per year that can be reinvested on campus.

The 2004-2005 program will provide 5% savings for the eight participating school districts for a combined gross annual savings of 50,000 therms. Using the 0.8% net-to-gross value, the net annual savings will be 40,000 therms and 200,000 over five years.

School District Investment: It is assumed that each PEAK School District will match the Community Energy Partnership’s investment in its facilities during the five-year energy savings period. As input in the accompanying worksheet, the average school district investment is expected to be a minimum of $5,000.

# 4. Municipal Facilities

The Community Energy Partnership will work with municipal facilities to cut energy use throughout city government, notably in city halls, as well as community centers, libraries, police and fire stations, corporate yards, etc. For the 2004-2005 program years, the gas element in the Community Energy Partnership has earmarked $5,000 per city to focus on optimizing gas use in municipal facilities and to create a sound platform for community wide smart energy management. This will be accomplished in each city in a number of ways and customized in each instance:

Sample Municipal Facility Opportunities

- Initial Employee Awareness-Raising Activities

- Developing City Energy Management Plans

- Engineering Analyses of Municipal Facilities

- Design Assistance for New Facilities

- Incentives for High Visibility Demonstration Project

- Incentives for Facility Operators

- Supporting Energy Advisors in City Government

Savings Assumptions: For the purposes of this proposal and based on this focus, we assume that the Community Energy Partnership will stimulate average gas savings of 5% over a five-year period for municipal facilities. Like school districts, we designate “large” and “small” cities. For the six partner cities with populations over 100,000, we estimate annual gas consumption of 500,000 therms. For small cities, we assume annual consumption of 250,000 therms.  The average municipal gas use is 375,000 therms/year.

We assume that program participation results in gross savings of 5% of the average usage of 375,000 therms for an annual savings of 18,750 therms per city. Through municipal energy management, the Community Energy Partnership will create annual gas savings of approximately 225,000 therms in the twelve cities. Using the 0.8 net-to-gross value, this will result in 180,000 net annual therms for the cities combined.

Partner City Investment: It is assumed that each partner city will match the Community Energy Partnership’s investment in its facilities during the five-year energy savings period. As input in the accompanying worksheet, the average city partner investment is expected to be a minimum of $25,000.

# 5. Community Promotions

Community promotions take many forms and are intended to stimulate awareness and direct energy savings in the partner cities. For the 2004-2005 project, 16,000 participants will participate in community promotions. For the first time in the Partnership’s evolution, gas savings opportunities will be promoted to participants at each event. This might be as simple as directing participants to existing Gas Company appliance rebates, or as creative as promoting a high-efficiency gas clothes dryer as a raffle prize.

Savings Assumptions: We assume that half of the projected 16,000 Community Promotions participants will get some form of gas-savings value. And we assume that the savings for each of the 8,000 recipients will be “a therm a year” for five years. Therefore, the gross annual savings will be 8,000 therms; the net annual savings are 6,400 therms.

# 6. Mobile Homes

Measure Descriptions: Mobile homes that use gas will benefit from Community Efficiency Tune-Ups that provide gas efficiency through a three-step process: “check it out – fix on the go – and flag further savings opportunities.” This will include inspections of all gas appliances such as space heaters, water heaters (and their downstream appliances), gas clothes dryers, and gas stoves. Consumer information on gas efficiency and safety are added program benefits.

The following is a list of gas-saving measures that will be provided through the Community Energy Partnership. For each home – and as with the electric side of the program – specific measures will applicable to specific homes. Working with the head of household, the installation contractors determine the optimal gas-saving measures and recommendations for that particular home.

Community Efficiency Tune-Up Gas Saving Measures

Space Heating Gas Saving Measures

- Visual inspection of furnaces or AC systems with “gas packs”

- Visual inspection of other gas space heaters

- Recommend replacement?

- Install programmable thermostats

- Provide new furnace filters

- Install door and window weatherstripping, caulk, etc.

- Visual inspection of gas fireplaces

- Check for leaks

- Check burners for optimal burn

- Adjust flame height

Water Heating Gas Savings Measures

- Visual inspection of water heater

- Safety check of water heaters

- Temperature regulation

- Install insulating wraps

- Install pipe insulation

- Check for hot water leaks

- Install efficient showerheads

- Install efficient faucet aerators

Gas Clothes Dryers

- Visual inspect of unit

- Check for leaks

- Check vent safety

- Recommend high-e clothes dryers (moisture sensors, etc.)

- Consumer education on full loads, shorter drying time, etc

Gas Stoves

- Visual inspection of unit

- Check for leaks

- Check/relight pilot lights if present

- Check burners for efficient burn

Consumer Education

- Information on gas-efficient appliances and rebates

- Information on low-income gas company programs

- Information on emergency gas safety procedures

- Information on room versus whole house conditioning

- Rules of thumb education on benefits of efficient gas appliances

Participation Rates: 2,400 mobile homes, 100% will receive gas-savings measures of one kind or other. Among the most common gas-saving measures installed through the Tune-Ups will be high performance showerheads, faucet aerators, hot water heater wraps, and furnace filters. Significant gas and especially electricity savings are “generated” from the installation of programmable thermostats. (Their costs, of course, are shared with the parallel Edison-funded project.) These will be installed in select circumstances and in approximately one-third of all Tune-Ups.

Savings Assumptions: A typical mobile home in Southern California uses 400 therms per year. Through a per-home investment of $40 for gas-savings measures, a 5% annual savings for five years is assumed. This results in a per-household savings of 20 therms per year, and a net annual value of 16 therms per year. Given the 2,400 participants, this program will provide a net gas savings of 38,400 per year.

| Representative Tune-Up Gas Savings for Mobile Home (Climate Zone 10) |  |  |  |
| --- | --- | --- | --- |
| Measure | Annual Savings (therms) | Net Annual Savings (therms) | Footnote Number |
| Programmable Thermostat | 130 | 104 | 1 |
| Weatherstripping (front door) | 2 | 1.6 | 2 |
| Showerhead | 10 | 8 | 3 |
| Faucet Aerators (2 units) | 8 | 6.4 | 3 |
| Water Heater Blanket | 14 | 11.2 | 3 |
| Total | 164 | 131.2 | 4 |
| Sources: |  |  |  |
| 1. DEER Database, 2001 Study page 184, Single Family Measure Savings, Programmable Thermostat |  |  |  |
| 2. DEER Database, 2001 Study, Single Family Values, Low-Income Door Weatherstripping |  |  |  |
| 3. DEER Database, 2001 Study, page 304, Non-Conditioning, Gas Measures |  |  |  |
| 4. Note that projected average net savings are only 20 therms |  |  |  |

# 7. Rental Apartments

Rental apartments are also eligible for the gas-saving Tune-Up measures.

Participation Rates: 2,400 rental apartments, 100% will receive gas-savings measures of one kind or other. Among the most common gas-saving measures installed through the Tune-Ups will be high performance showerheads, faucet aerators, hot water heater wraps, and furnace filters. As with mobile homes, significant gas and especially electricity savings are “generated” from the installation of programmable thermostats. These will be installed in select circumstances and in approximately one-third of all Tune-Ups.

| Representative Tune-Up Gas Savings for Rental Apts (Climate Zone 8) |  |  |  |
| --- | --- | --- | --- |
| Measure | Annual Savings (therms) | Net Annual Savings (therms) | Footnote Number |
| Weatherstripping (front door) | 2 | 1.6 | 1 |
| Showerhead | 10 | 8 | 2 |
| Faucet Aerators (1 unit) | 8 | 6.4 | 2 |
| Hot water pipe wrap | 5 | 4 | 2 |
| Water Heater Blanket | 14 | 11.2 | 2 |
| Total | 39 | 31.2 | 3 |
| Sources: |  |  |  |
| 1. DEER Database, 2001 Study, Single Family Values, Low-Income Door Weatherstripping |  |  |  |
| 2. DEER Database, 2001 Study, page 304, Non-Conditioning, Gas Measures |  |  |  |
| 3. Note that projected average net savings are ony 20 therms |  |  |  |

Savings Assumptions: A typical rental apartment in Southern California uses 300 therms per year. Through a per-apartment investment of $40 for gas-savings measures, 5% annual savings for five years are assumed. This results in a per-household savings of 15 therms per year, and a net annual value of 12 therms per year. Given the 2,400 rental apartment participants, this program will provide a net gas savings of 28,800 per year.

# 8. Owner-Occupied Apartments

Owner occupied apartments selected by the partner cities are also eligible for the gas saving Tune-Up measures presented above.

Participation Rates: 2,400 owner-occupied apartments, 100% will receive gas-savings measures of one kind or other. Among the most common gas-saving measures installed through the Tune-Ups will be high performance showerheads, faucet aerators, hot water heater wraps, and furnace filters. Significant gas and especially electricity savings are “generated” from the installation of programmable thermostats. These will be installed in select circumstances and in approximately one-third of all Tune-Ups.

Savings Assumptions: A typical owner-occupied apartment in Southern California uses 400 therms per year. (Owner occupied apartments are assumed to have a 33% higher energy intensity that rental units.) Through a per-home investment of $40 for gas-savings measures, we assume a 5% annual savings for five years. This results in a per-household savings of 20 therms per year, and a net annual value of 16 therms per year. Given the 2,400 participants, this program will provide a net gas savings of 38,400 per year.

# 9. Small Businesses

Small businesses are also targeted through Tune-Ups, in this case the Small Business Efficiency Tune-Ups. The Tune-Ups are similar to household Tune-Ups, with select measures and recommendations tailored for each business. Note that the average per-business, gas-savings measure cost is $100. Therefore common measures will be visual inspections of all gas-using appliances and the installation of programmable thermostats.

Participation Rates: 600 small businesses, 100% participate in the gas-savings program in one way or other.

Savings Assumptions: Typical small business in Southern California uses 2,400 therms per year. Through a per-small business investment of $100 for gas-savings measures, a 5% annual savings for five years is assumed. This results in 120 therms of savings per year for businesses, and a net annual savings of 96 therms. With 600 program participants, this results in net annual gas savings of 57,600 therms.

Section V. Performance Goals

The Community Energy Partnership, like the predecessor Six Cities Energy Project, will generate a number of short and long-term benefits thanks to the hybrid program approach featuring direct installation of measures and education/information to raise awareness of smart energy management. One of the greatest benefits will be providing services to hard-to-reach customers that have not fully participated in programs before.

The 2004-2005 Natural Gas Efficiency in the Community Energy Partnership in the Southern California Edison service territory is projected to save 965,600 net therms of natural gas annually, and 4,828,000 therms during the lifecycle of the measures installed. Many indirect savings, for instance those generated as a result of a student’s participation in the PEAK Student Energy Actions program, will also accrue. The Partnership will also result in major electricity savings that are presented for the project in the parallel Southern California Flagship Program proposal.

Community awareness: The gas savings will be generated through: residential programs (targeted for senior housing, mobile home communities, hard-to-reach multifamily apartments, and low and moderate income owner-occupied apartments); small business works; PEAK home and school-based savings, and through municipal initiatives that help partner cities “get their own houses” in order. The following table summarizes the natural gas savings that will be generated by the types of participants presented and from the measures presented in the prior section:

| Southern California Community Energy Partnership |  |  |  |
| --- | --- | --- | --- |
| Natural Gas Savings |  |  |  |
| Participants | Units | Net Annual Savings (therms) | Net Lifecycle Savings (therms) |
| PEAK Students | 16,000 |  |  |
| PEAK Households | 12,000 | 576,000 | 2,880,000 |
| PEAK School Districts | 8 | 40,000 | 200,000 |
| Municipal Energy Mgmt | 12 | 180,000 | 900,000 |
| Community Promotions | 8,000 | 6,400 | 32,000 |
| Mobile Homes | 2,400 | 38,400 | 192,000 |
| Rental Apartments | 2,400 | 28,800 | 144,000 |
| Owner-Occupied Apts | 2,400 | 38,400 | 192,000 |
| Small Businesses | 600 | 57,600 | 288,000 |
| Totals | 43,820 | 965,600 | 4,828,000 |

Long-Term Savings: In addition, and not considered in this section of the proposal, savings will be generated from community awareness activities and long-term savings related to the program’s emphasis on charting their sustainable energy futures. While not quantified for this proposal, these long-term savings may be far more profound, and may far outstrip the short and mid-term savings presented here.

Section Vl. Program Evaluation, Measurement and Verification (EM&V)

The Community Efficiency Partnership will be subject to a dual process and impact evaluation for both electricity and gas-saving measures. What worked? What didn’t? How much energy and capacity is offset through short-term measures? How much through long-term attitudinal transformations? How about gas savings? This section of the proposal presents some background on evaluation of the Community Energy Partnership and then presents key elements of the full evaluation process.

Current Evaluation Experience: The Six Cities Energy Project – the predecessor program that was delivered in 2002-2003 – is currently being evaluated using a multifaceted approach within a budget of $100,000. Given the deliberate proximity of the evaluation firm, the budget amount has allowed for extensive field visits. It also allows for telephone sampling. But it is, naturally, limited in terms of direct metering. Perhaps this is appropriate as it is the process of community organizing and the spirit that is then built, that will be most important to evaluate. Once a project has a spirit, the spin-off and indirect savings benefits far outstrip conventional program approaches.

The Six Cities Energy Project is being evaluated in real time, and there is a final evaluation report that will be completed in spring of 2004. Thus far, the Coalition has been pleased with the evaluator’s work. To preserve the cost-effectiveness of the evaluation and to take advantage of its position “on the learning curve” for the Community Energy Partnership approach, The Energy Coalition recommends that its current evaluator – Aloha Systems of Irvine, California -- be retained for the 2004-2005 program years for evaluation of both electric and gas-saving measures. The second firm that is local and understands our program sufficiently, ASW Engineering of Tustin, has agreed to be listed herein.

Recommendation of Evaluators

#1 Aloha Systems, Irvine, California.

#2 ASW Engineering, Tustin, California

The Energy Coalition recommends that Aloha Systems of Irvine, California be retained as the Community Energy Partnership program evaluator for the 2004-2005 program years and its expanded work with natural gas efficiency. Aloha is currently evaluating the Six Cities Energy Project, is local, and understands the program, allowing the majority of evaluation funds to go into site visits and reasoned technical analyses. Our alternative is ASW Engineering of Tustin, a local firm familiar with the Community Energy Partnership process.

2004-2005 Evaluation Budget: The Gas Efficiency Measures in the Community Energy Partnership provides additional EM&V budget to address gas savings. This will complement the $300,000 electric measures evaluation budget for the project, and represents a sizable increase of EM&V funds when compared to the Six Cities Energy Project. While the number of cities has also doubled, this increased evaluation budget will be sufficient to gain a more sophisticated evaluation of the program. In addition, mid-term results from some initial six cities activities – like student household savings – will be forthcoming in the early months of the proposed Community Energy Partnership to provide further substantiation of the model and insight as to efficacy.

Key elements of the proposed evaluation approach:

1. Measuring levels of gas savings achieved

Measuring direct energy savings is the primary focus of the EM&V plan. In some situations this will be a straightforward assessment of gas savings achieved as a result of making physical changes to facilities, for example providing incentives for pool covers or upgraded pool pumping and heating systems. Traditional measurement and verification approaches to determine operating hours and demand reductions will be used. In other situations like community promotions, the measurement of gas savings will necessarily rely on less exact methodologies, such as analysis of self-reported data from participants.

There will be many situations in the Community Energy Partnership where the primary energy savings are behavioral in nature. Furthermore, these behavioral changes are spread out over a large number of participants. A prime example of this is the PEAK program, where the primary results in both homes and schools are either directly behavioral (such as more carefully controlling heating and air conditioning) or are physical results inspired by behavioral or attitudinal changes (such as a student convincing her parents to buy an Energy Star water heater). These benefits will be virtually impossible to measure directly in any cost-effective manner, so they will be developed using indirect assessment means.

2. Measuring cost-effectiveness

The gas savings numbers provided through the EM&V analysis will be usable as revised parameters for calculations of the standard cost-effectiveness tests. Combined with The Energy Coalition’s actual costs for implementing various aspects of the program, accurate ex-post cost-effectiveness calculations will be determinable not only for the project as a whole but for its individual components as well.  When compared with the ex-ante calculations used for the official determination of meeting project goals, these cost-effectiveness results derived from the EM&V data will facilitate an assessment of similar future projects.

3. Providing up-front market assessments and baseline analyses

For the Community Energy Partnership’s customer segments, developing baseline analyses is more behavioral than technical. For the most part, the technologies deployed through the program are straightforward and replace old technologies that are even more straightforward. For the purposes of this evaluation, the more telling baseline issue will be assessing prior awareness of the various technologies and behaviors taught through the components of the project. The evaluation will employ market-research-style awareness assessment to make this kind of assessment, and to see just how well the project penetrated the hard-to-reach customers.

The evaluation will also survey a limited number of non-participants who were eligible for the program. This will help determine both the baseline of awareness and usage of the various efficiency technologies. It will also enable a better estimate of the market transformation component of the program, and thereby assess the value of the program that exceeds the direct value of the physical equipment supplied. For example, some energy savings will be achieved in the close-knit communities even among those not initially participating.

4. Providing ongoing feedback and corrective guidance

For the Community Energy Partnership the evaluator will be local and in frequent communication with The Energy Coalition as facilitating partner. Furthermore, because the assessment of the value of the community organizing is subjective in nature, one or more evaluation staff will observe key project meetings and volunteer at important special events to gain a first-hand perspective on their value to the city and project. After these events the evaluator will report back to The Energy Coalition and the partner cities with assessments and suggestions for process and impact improvements to maximize community savings and to make the project more cost effective.

5. Measuring effectiveness indicators of specific programs

Several sectors are addressed by the Community Energy Partnership, each of which has significantly different indicators of effectiveness. The full EM&V plan will present specific methods to measure these various indicators to grasp this variety and assess its individual and overall effectiveness. Furthermore, the exact implementation details of the project are not fixed at its onset.  An integral part of the Partnership approach is to allow the cities and schools to work with the Coalition to develop a tailored program that best suits their needs. Therefore, the EM&V plan will evolve with the project, requiring significant levels of flexibility from evaluators.

6. Assessing the overall levels of performance and success of the program

The overall performance and success of the Community Energy Partnership will be based upon a number of components. The process and impact elements of the evaluations will present the engineering and behavioral information gathered and analyzed. It will also assess an array of additional program aspects – from press coverage to volunteer spirit! --to provide an accurate and clear picture of the value of the Partnership’s innovative, diverse, comprehensive, and interwoven approach to community energy efficiency.

The process evaluation will also present and analyze additional benefits of various components of the program, some which are not directly related to energy efficiency, but nonetheless are laudable uses of public funds that contribute to the overall benefits of society. For example, gas safety that will be incorporated into the Community Energy Partnership is a prime example of this. The evaluation will stop short of developing financial values for these ancillary or spin-off benefits, but they will be included as telling anecdotes in the discussion of the project’s overall performance.

* As part of an Energy Rally, community residents volunteered to assemble and deliver torchiere lamps to their shut-in neighbors. When volunteers arrived at one mobile home, they found only one operating light in the entire coach. With difficulty, the elderly Korean-American owner explained that she seldom went out and never went to events, "because I can't understand."  But she had been able to decipher the flyer with the torchiere and CFL trade-in information, and had submitted her request because the lamps would be delivered.

7. Assessing whether there is a continuing need for the program

Ultimately the most important question of the EM&V process is whether the program warrants continuation. By its nature, the Community Energy Partnership is likely to be either an ineffective means of enhancing our State’s energy efficiency, or it will demonstrate itself to be something worth repeating in virtually every community. The success of the previous Two Cities Project and Six Cities Energy Project implies the likelihood of the latter, but the more complex arrangements, increased project management duties, and additional diversity among the cities will provide greater insight and evidence for this expectation. As such, the final component of the valuation will be a clear judgment of whether the program needs to “go back to the drawing boards,” or whether it does indeed warrant continuation.

Section Vll. Qualifications

Partner Cities

This proposal represents twelve diverse Southern California cities with an aggregate population of a million people. The cities are banded together by The Energy Coalition and are committed to making a difference and being responsible for crafting a healthy and sustainable energy future. These cities’ commitments to the Community Energy Partnership extension and expansion are exhibited as the first attachment.

Team Leaders: As part of the Memorandum of Understanding signed by each city and The Energy Coalition, each city must designate a senior official to serve as the project Team Leader in his or her community. Cities have to dedicate staff time and other in-kind services (such as traffic support and use of City Hall) to the project. It is the cities' dedication to the project, and the successes that these Team Leaders have enabled in their cities that is the ultimate qualification for funding.

The Energy Coalition

The Energy Coalition is a 20-year old 501 c(4) non-profit organization based in Laguna Beach, California that has been developing the Community Energy Partnership model for ten years, and that now has five years of experience under its belt. Thanks to the partner six cities involved, the program was heralded for its success. In 2001, the Two Cities Energy Project – one of the Partnership’s predecessor projects -- was named a winner of the Governor's Environmental and Economic Leadership Award. The Energy Coalition was awarded a 2002 Flex Your Power Award for PEAK Student Energy Actions.

The Coalition is headed up by John B. Phillips and managed by Ted Flanigan. Virginia Nicols is our Campaign Coordinator; Sheila Bailey is our Financial Officer. Dorothy Terman is our senior PEAK consultant.

John Phillips has nearly 50 years of experience helping end-users optimize their energy use. He designed and managed energy systems for major facilities across the country, and later pioneered energy cooperatives of large users keen on learning from one and other to trim their costs and provide better services. For the past ten years, working at the senior energy policy level, Phillips has been advocating more effective means of delivering energy services to communities in California and Sweden.

Ted Flanigan has over 20 years experience designing and implementing efficiency programs. He has worked for two major utilities and consulted for over 100 utilities and energy services provides in over 30 countries. His work was recognized and funded by the John D. and Catherine T. MacArthur Foundation. As the Project Director, he will be responsible for all day-to-day managerial functions of the Community Energy Partnership. His resume is in the proposal attachments.

Virginia Nicols has over 20 years of experience with marketing concepts and engaging participants. For the Coalition, she has found creative means of stimulating record-high levels of participation in community events. Her skill is to relate the message to the audience, an invaluable attribute of the Community Energy Partnership.

Sheila Bailey has worked for The Energy Coalition for nearly 20 years and is responsible for the financial accountability of Edison ratepayers’ funds for the Community Energy Partnership. She has extensive experience with CPUC rules for program accounting and has been diligent in careful financial control to maximize program dollars that can be spent in the field.

Southern California Gas

SoCalGas has actively promoted and administered energy efficiency and energy conservation programs over the last several decades. In the last 10 years alone, customers who have taken advantage of its energy efficiency programs have saved more than 26.5 million therms of natural gas a year, or enough gas to serve 48,000 homes a year. These programs have been varied and widespread including residential, commercial, industrial, new construction, and low income. These programs represent the efforts of countless employees and consultants retained by the Company who are in the energy business and uniquely qualified to design, manage and administer these programs.

The underlying network that supports these efforts is best described by the “iceberg analogy”; from the surface what is observed are a variety of energy efficiency programs that incent the consumer to make energy-efficient choices when purchasing or retro-fitting equipment or refurbishing a home. What is not easily observed nor comprehended is what lies below the surface, a large work force of energy experts who have designed and modified a wide range of programs over the last twenty years and a marketing staff that as part of normal marketing efforts has utilized their existing network to promote energy efficiency to their clients.

As the Commission’s energy efficiency policy has changed over the years, SoCalGas has consistently and successfully adapted to change and responded with a portfolio of residential, nonresidential and new construction programs that meet the needs of its customers. As in the past, SoCalGas continues to demonstrate its flexibility and ingenuity in providing energy efficiency programs and remains committed to achieving higher energy efficiency and will continue to offer programs that benefit its customers.

PEAK Services

Five outstanding science teachers from Santa Monica, Irvine, and Newport Beach -- Joel Post, Linda Cady, Kathy Marvin, Laurie Hartstein, and James Gapp -- provide consulting services for PEAK, train “incoming” PEAK teachers, and develop new curriculum modules. Two PEAK teachers took the initiative to develop the summer PEAK Energy Adventure, a two-week summer science adventure that included field trips to power plants and energy patrols in the community. Four PEAK teachers have trained PEAK teachers in Sweden.

PEAK benefits greatly from the services of Dr. Dorothy Terman, the former math and sciences curriculum coordinator for Irvine Unified School District and now a multifaceted consultant whose duties range from gender equity issues (promoting science for girls) to PEAK. Dr. Terman is responsible for PEAK’s integration into existing curricula and communicating the value of PEAK’s applied teaching.

Technical Services

The Community Energy Partnership frequently draws upon the services of a number of engineering firms for technical services. Notably, ASW Engineering of Tustin has done extensive work over the years with municipal and school facilities. In addition, ASW has provided engineering consulting for PEAK and program designs. Henrikson Owens, and notably its principal – Richard Henrikson – has also been a key player for the Partnership, auditing school and municipal facilities and assisting in program design activities. Global Green USA – a non-profit based in the partner City of Santa Monica-- serves as a technical advisor to the Partnership and provided guidance to cities within the Six Cities Energy Project on green building practices and LEED certification.

Tune-Up Installation Services

Two exceptional installation contractors make the Community Efficiency Tune-Ups successful. Ace & Sons Construction, Inc. of Riverside, California, provides services to in-land project cities with its expertise in weatherization and HVAC systems. Catalina Ballast & Bulb Co. of El Monte provides services in more coastal project cities with its expertise in lighting retrofits. Both firms possess exceptional communication skills and a wealth of experience providing direct installation services in Southern California.

Section Vlll. Budget

The Community Energy Partnership’s Gas Company works presented in this proposal requires a budget of $1,223,000. It is matched by the electricity savings budget of $7.46 million. A breakdown of the budget is presented in the table below:

###### 2004-2005 Community Energy Partnership

###### Gas Savings Measures Program Budget

| Budget Items | 2004 | 2005 | Total |
| --- | --- | --- | --- |
| PEAK Student Energy Actions | $145,000 | $25,000 | $170,000 |
| PEAK Households |  |  |  |
| PEAK School Districts | $20,000 | $20,000 | $40,000 |
| Municipal Facilities | $30,000 | $30,000 | $60,000 |
| Community Promotions | $25,000 | $25,000 | $50,000 |
| Mobile Home Activities | $48,000 | $48,000 | $96,000 |
| Rental Apartment Activities | $48,000 | $48,000 | $96,000 |
| Owner-Occupied Apartment Activities | $48,000 | $48,000 | $96,000 |
| Small Business Activities | $60,000 | $60,000 | $120,000 |
| Marketing and Outreach | $10,000 | $10,000 | $20,000 |
| Coalition Staff | $100,000 | $100,000 | $200,000 |
| Dedicated Gas Company Professional | $37,500 | $37,500 | $75,000 |
| Overhead | $30,000 | $30,000 | $60,000 |
| Travel Costs | $15,000 | $15,000 | $30,000 |
| General Administrative | $25,000 | $25,000 | $50,000 |
| Program Tracking/Reporting | $10,000 | $10,000 | $20,000 |
| Impact Evaluation | $20,000 | $20,000 | $40,000 |
| Total | $671,500 | $551,500 | $1,223,000 |

Footnotes

- The PEAK budget will allow for the integration of natural gas management throughout the curriculum – where new lessons will be developed – and in the simulation software. Much of this integration will be accomplished in the first year. Some funds provide program support during its two-year implementation.

- PEAK Households make investments on their own.

- Each PEAK School Districts is supported with $5,000; note the $20,000 electricity match. We assume incentives applied over two-year period.

- Each city partner is targeted for $5,000 for its municipal facilities.

- Community promotions are low-cost with a per-participant average value of $3.13.

- Mobile homes, rental apartments, and owner-occupied apartments get Community Efficiency Tune-Ups. $40 spent on the average home for gas-savings measures.

- Small businesses get Tune-Ups as well with $100 on the table for gas saving measures.

- The Dedicated Gas Company professional will spend 50% of his or her time on Gas Company initiatives in the Southern California Edison service territory, and 50% supporting the San Diego pilot program.

Funding Flexibility: The Community Energy Partnership is unique in its flexibility. Not only can checks be cut fast, but if a certain set of anticipated activities appear unlikely to deliver results, the Partnership can withdraw funds and reapply them in another, more likely to succeed area. Inversely, wild success with one energy efficiency strategy can warrant an infusion of project funds. The Partnership also reserves the right to shift resources between participating cities based on progress or lack thereof. This is all done with the primary program objectives in mind, that is to stimulate awareness and activity that will lead to sustained savings for eager communities and the State. Rather than a “flash in the pan” approach that harvests the low-hanging fruit at the least possible cost, the Partnership seeks to garner savings in ways that they will be sustained over time.

Section lX: Summary

The Community Energy Partnership works in a unique way and in doing so has been able to reach energy consumers that are most in need of energy and dollar savings. The Partnership engages participants who have been largely cynical about their prospects of having an impact at the community or state level. The Partnership educates participants and organizes communities to fundamentally change the way people think about energy and other finite resources. The Community Energy Partnership that has now grown to twelve Southern California Edison cities, representing a million Californians, will build a responsible energy ethic to transform both markets and attitudes for integrated electricity and gas use.

The California Potential

When fully extended and expanded throughout the State of California, the Community Energy Partnership can deliver up to 10,000 MW of capacity, billions of therms of gas savings, and $15 billion in consumer electric and gas savings by 2010. The model approach is proving that "ordinary people" can be educated and inspired to reap the benefits of immediate action and become part of a process of creating a healthy energy future. Through collaboration stimulated by the cities and the strategic partnerships developed by The Energy Coalition, Community Energy Partnerships are a potent model and expression of community energy responsibility.

The Community Energy Partnership has gained the respect of each of California’s investor-owned utilities as well as the California Public Utilities Commission. This has been hard-earned, and speaks to the success of a robust set of activities in the partner cities that are at once providing immediate energy-savings benefits and building community responsibility for energy use through an energy ethic that has been heretofore missing. By partnering with utilities, the Partnership now will take another major step forward to becoming fully linked with utilities’ integrated resource plans and resource procurement plans, an essential evolution that builds a win-win-win situation between the people and their cities, the serving utilities, and the State of California.