South Bay Cities Council of Governments (SBCCOG)

In partnership with the Southern California Gas Company

PY2004/PY2005 Energy Efficiency Program Proposal

CPUC Proceeding Number R.01-08-028

Submitted to the California Public Utilities Commission

September 23, 2003

Email Submission Confirmation Number:

XXXXX

Title of the Proposed Program:

SOUTH BAY CITIES COUNCIL OF GOVERNMENTS (SBEERC)

ENERGY EFFICIENCY RESOURCE CENTER

Contact Person:

Jacki Bacharach

Executive Director

South Bay Cities Council of Governments

5033 Rockvalley Road

Rancho Palos Verdes, CA 90275

(310) 377-8987

jackibach@cox.net

Other programs proposed:

South Bay Energy Rewards Program.

(Printed copy of email confirmation with confirmation number attached)

Table of Contents

Section I.	Program Overview	3

A.	Program Concept	3

B.	Program Rationale	3

A.	Program Objectives	9

Section II.	Program Process	13

A.	Program Implementation	13

B.	Marketing Plan	16

C.	Customer Enrollment	16

D.	Materials	17

E.	Payment of Incentives	17

F.	Staff and Subcontractor Responsibilities	17

G.	Work Plan and Timeline for Program Implementation	17

Section III.	Customer Description	19

A.	Customer Description	19

B.	Customer Eligibility	19

C.	Customer Complaint Resolution	19

D.	Geographic Area	20

Section IV. Measure and Activity Descriptions	21

A.	Energy Savings Assumptions	21

B.	Deviations in Standard Cost-effectiveness Values –	21

C.	Rebate Amounts	21

D.	Activities Descriptions	21

Section V. Goals	21

Program Goals include the following:	21

Section VI. Program Evaluation, Measurement and Verification (EM&V)	21

Section VII. Qualifications	24

A.	Primary Implementer	24

B.	Subcontractors	25

C.	Resumes or Description of Experience	26

Section VIII. Budget	31

# Section I.	Program Overview

## A.	Program Concept

The South Bay Cities Council of Governments (SBCCOG), in partnership with Southern California Edison (SCE) and the Southern California Gas Co. (SCG) is pleased to submit this proposal in response to the Californian Public Utilities Commission (CPUC) Decision 03-08-067.  The South Bay Energy Efficiency Resource Center (SBEERC) will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs. To accomplish this, the SBCCOG will form an Energy Efficiency Resource Center (SBEERC), which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.  The SBEERC will help ensure that the region derives the greatest benefit from the estimated $16.5 M the region will contribute to the PGC-EE funds for 2004-2005.

The total 2004-2005 budget for the SBEERC Program is $793,488 to be funded by electric and gas public goods charges wherein $610,986 will come from the SCE PGC funds and $182,502 will come from the SCG PGC funds.  This is an “information” program and the partnership will be managed under utility-specific contracts with SBCCOG.

## B.	Program Rationale

The South Bay Regional Energy Efficiency Center seeks to build on the recent successful energy efficiency activities of the South Bay Cities Council of Governments (SBCCOG) in 2002-2003.

This program addresses many of the policies, criteria and priorities as set forth in D.03-08-067 and Section 381.

The Partnership Approach

The SBEERC proposes to build on the respective strengths of SCE/SCG and the SBCCOG  to overcome identified participation barriers, better serve local needs and hard-to-reach customers, increase participation in energy efficiency programs and thus to increase the overall long-term sustainability and value of energy efficiency programs to the member agencies and citizens in South Bay region.  This joint partnership is in keeping with the CPUC policy to develop meaningful partnerships between local governments and utilities in order to foster, among other goals, cost-effective programs. This partnership recognizes the respective strengths and capabilities of the primary partners – SCE, SCG and the SBCCOG  – as well as other stakeholders, including other energy efficiency providers, local business organizations, under the principle that by working together, the region can accomplish much more than if they worked independently.  The partnership will strive to maintain both SCE/SCG’s and the SBCCOG's desire to protect their respective individual interests, identities and respective future roles in delivering energy efficiency and other programs in the future.

The Program targets underserved or hard-to-reach customers

The SBCCOG region includes a number of hard-to-reach markets, including non-English speaking consumers, renters and small businesses.  This efficient and cost-effective program delivery strategy ensures that more customers, particularly the hard-to-reach customers of South Bay region, will be aware of and create a demand for energy efficiency services and programs, whether provided by the SBEERC, through SCE/SCG’s statewide programs, or other program providers.

This Program is Innovative

This Program utilizes an innovative approach to a joint partnership between a regional local government agency and utilities to tailor energy efficiency programs and/or delivery strategies to the local region’s needs in order to increase local awareness and utilization of the programs as well as improve overall cost effectiveness.

This Program Has Been Designed to Meet the Needs of the Region

By working with the SBCCOG, which is the recognized Council of Governments, the program will be implemented to best meet the needs of the region’s many stakeholders.

This Program is closely coordinated with other Program Implementers

Close coordination will be assured through a close working relationship between SBCCOG and SCE/SCG and other program providers to ensure no overlap between this program and those of other providers.  In particular, the program will coordinate closely with that of the South Bay Energy Rewards (SBER) Program that is being offered in the SBCCOG region as a follow-on to successful efforts during PY2002 and PY2003.  In addition, the program partners will go beyond this mandate to proactively look for opportunities to promote other CPUC-EE programs where these opportunities have yet to be identified  (e.g. new local programs that program implementers were not aware of that will become available after the writing of this  proposal).    Coordination with SCE/SCG includes promotion of the following programs: SPC, Express Efficiency, Non-Residential Audits, Savings-by-Design Programs, Appliance Recycling, Single Family Rebates, Multifamily Rebates, Home Energy Efficiency Surveys and California Energy Star New Home Construction.   In addition, coordination with marketing and outreach activities will occur with the administrators of the statewide Flex Your Power campaign to ensure that the greatest leverage is obtained by consistent messaging and timing of promotional efforts, and that the SBEERC does not duplicate creation of outreach and information resources that have already been funded.  The SBEERC could also provide greater program synergies by being utilized as a mechanism to promote other public-good energy programs, such as the Self-Generation Incentive Program and low income assistance programs.

This Program Will Overcome Significant Market Barriers

This Program is designed to address all of the market barriers identified in the Energy Efficiency Policy Manual (Version 2).  A summary of these barriers, as well as those identified locally, and how this program proposes to overcome those barriers, is found in Table 3 on the following pages.

| Table 3: Market Barriers/ Challenge and Corresponding Program Attributes Design to Address Them |
| --- |
| Market Barrier/ Challenge | Corresponding Program Attribute |
| Lack of Consumer Information /Availability of a local resource to assist entities with identifying and applying appropriate resources to their specific needs. SBCCOG efforts to date and subsequent focus groups have revealed that although energy information has reached South Bay region, the lack of a centralized and local clearinghouse for information on energy programs is very noticeable. | Program will address the lack of availability of consumer information by providing local area customers with a local source of energy efficiency information and resources. This program will focus particularly on the information and resources that promote the statewide and local programs. In addition, the program will tailor information and resources that are not widely available to its specific market segments important to the region. This strategy will accomplish a more targeted and comprehensive penetration achievable using SBCCOG’s established and growing communication channels aligned with SCE/SCG’s technical resources and rebate programs. SBEERC will also raise the visibility of the applications and benefits of energy efficiency products through several highly visible energy projects that highlight energy efficiency products and their benefits, such as the successful South Bay Energy Rewards Program (SBER) and those that are highlighted in the Energy Centers throughout the state and those that are recently proven in the statewide Emerging Technologies Program. |
| Need for assistance in implementing follow-through on opportunities that have been identified in the past. | Program will address this barrier by having local resources dedicated to ensuring that the resources and technical assistance necessary to ensure implementation of projects occurs. This is particularly important in programs like Savings-by-Design, where there is a high degree of interaction between project implementers (i.e. architects, engineers) and the program administrators to ensure plans are checked and turned around expeditiously (this has been cited as a major barrier in customer participation in this specific program). |
| Lack of availability of resources due to impact of current economic conditions. | Program addresses this by providing targeted resources (technical and financial) at a specific locale that is significantly impacted by the current economic downturn. |
| Cost-effectiveness, particularly in light of the need for local personnel resources that could be redundant to IOU functions | The program partners have worked toward maximizing the inherent strengths of the combination of local resources and those of SCE/SCG. This close coordination of the partners may take a few months to fully optimize, but the end result should be an overall higher cost effectiveness through the use of local resources where local resources are appropriate (e.g. day-to-day information, SBER and customer interaction), and SCE/SCG resources where most appropriate (e.g. technical resources and rebate processing). |
| Higher start-up expense/ Lack of Financing for energy efficiency improvements, most impacted by the current downturn in the economy and its impact on the region’s economic foundation. Public agencies whose budgets have been significantly tightened due to local and statewide revenue shortfalls are particularly impacted. | Program seeks to overcome the financing barriers through the use of existing (e.g. California Energy Commission Low Interest Loans) and new financing programs. The SBEERC will be investigating the formation of a project aggregation pool to achieve greater economies of scale and cost effectiveness and to potentially finance them through a SBEERC-led ESCO type contractual arrangements. |
| Barriers to the entry of new energy efficiency service providers. | This program will assist local companies with training, gaining easier access to customers, and other resources that should enable them to grow their businesses and capabilities. In addition, the program will introduce resources (e.g. case studies, tools, and best practices) that are more widely available in larger urban areas. Lastly, the program will foster greater consumer demand for local energy efficiency service products and providers by providing marketing and outreach for the SBER and statewide energy efficiency programs. The resulting demand created may encourage new service providers to set up shop or expand their current businesses into the energy efficiency arena. |
| Lack of availability of high efficiency products. | The Program will build on the existing strong relationships between the SBCCOG and local energy services providers and retail outlets to encourage them to offer the type of energy efficient equipment that qualifies for rebates under the statewide programs. In addition, SBCCOG will further foster the availability of energy efficient products by using its local business networks to make them aware of programs that offer rebates for energy efficient products and expanding the local demand for energy efficient equipment, thus encouraging local businesses to provide greater “shelf space” for these products. |
| Lack of a viable and competitive set of providers of energy efficiency services in the market. | This program will supplement the hands on SBER program by providing support to local contractors, suppliers and retail stores offering energy efficiency services by providing them with advertising and promotion support and creating a ready market in which to offer their services, along with a rebate and information infrastructure that fosters customer interest in energy efficiency services. |

Basis for Evaluation of this Program

This program is primarily an information program; therefore we recommend it be evaluated as an information program per the criteria description in D.03-08-067, p. 27.

## Program Objectives

The objectives of the South Bay Energy Efficiency Resource Center are to:

- Significantly increase the availability of information and education programs to all market segments in South Bay region to produce a marked increased participation in the installation of energy efficient equipment through various statewide programs that will deliver long term savings and peak demand reduction.

- Provide the South Bay region’s hard-to-reach customers with high quality information about energy use in their homes and facilities.

- Overcome the identified market barriers that are information-related and are described in Section C.

- Enable and encourage customers to make informed decisions to change energy use and practices.

- Significantly leverage the SBCCOG institutional strengths to gaining access to local resources and serve specific local needs combined with utility program resources to increase the overall cost-effectiveness of resources PGC-EE resources spent in South Bay region.

Implementation

The SBEERC is composed of a centrally-located facility that will provide a convenient central clearinghouse where residents, businesses and others can call or visit and gain access to valuable energy efficiency resources and referrals to local expertise.  The costs for this resource will be kept very low by using either the facilities of a SBCCOG  member agency, sharing space with a local strategic partner (e.g. the Regional Economic Development Agency), or  subleasing space in a suitable facility.   The SBEERC will also make its conferencing and training room facilities available to other program providers on an as available basis.

Training classes and seminars will be offered to design/build firms, engineers and architects working on commercial properties.  Topics of seminars and workshops will include Commercial and Industrial Lighting, HVAC for Commercial Facilities, building envelope designs, day lighting, Motors/Adjustable Speed Drives, Energy Efficient Refrigeration, Motors (Water Pumping Applications), Lighting Fundamentals,  Groundwater Wells & Pumps, Residential and Non-residential Title 24 Compliance, Residential HVAC Quality Installation, Compressors/Air Leak Certification, HVAC Sizing and Duct Design, and Energy Efficiency Strategies for Schools.

Primary Task and Milestones

The following will be accomplished as part of this program element:

- Completion of the formation of the Energy Efficiency Resource Center.

- Establish a SBEERC “customer hotline” and customer resolution tracking system.

- Develop a comprehensive training and seminar plan based on the specific needs of the region.

- Meet with SCE/SCG and other program implementer representatives (including the CEC, DOE) to assess available information and training materials that can be imported into the SBEERC.

- Identify those specific resources that would be needed to be developed to support the SBEERC events (e.g. collaterals, training courses, etc.).

- Launch the SBEERC with an opening event.

- Commence training schedule and conduct training and information sessions on a regular basis.

Goals

The goals of this program include:

- Conduct at least 4 training sessions for the public sector, 6 sessions for businesses, and at least 4 events for residential customers.

- Promote SBEERC resources and energy efficiency information at 12 community events or more.

- Respond to every customer inquiry within 48 hours.

- Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent).

Customer Description and Enrollment

The program targets all SCE/SCG electric or natural gas customers in the South Bay, with an emphasis on hard-to-reach audiences of low-income, seniors, renters and non-English speaking audiences of diverse ethnic backgrounds.

Enrollment for programs will be accomplished through various means, including email, phone and fax to the SBEERC.

Coordination with Other Entities

In order to minimize overlapping messages and to minimize costs, close coordination will be accomplished with all parties offering information and education components, including SCE/SCG, other non-IOU providers of education and information services, as well as the significant amount of resources available through the California Energy Commission and the Department of Energy.

Contractor Support

Contractor support will be provided for development of the SBEERC, development of the customer feedback system, SBEERC employee training, and development of a customer inquiry referral database, development of information and training programs, as well as materials design and printing.  The SBEERC will also call on various subject matter experts from utility and non-utility entities to provide instruction and/or consultation for seminars, displays, demonstrations, and printed information provided to customers.

Exhibits and Displays

The SBEERC will not commit a large amount of resources on “bricks and mortar” and sophisticated exhibits and displays, but will focus its resources on deploying relatively low cost, simple static displays that “take the message to the people.”  For example, the opportunities for retrofitting older homes will be highlighted in an eye-catching poster-sized display that will promote a respective program or upcoming seminars.  These displays will be constantly prominently displayed throughout the region at places where people frequent, like food stores, malls, hardware stores and retail outlets.  In some cases, the SBEERC may work with a vendor to showcase equipment and demonstrate technologies for specific applications that consumers can go see during normal working hours (e.g. high-efficiency lighting retrofit at a Kinko’s location, or seasonal displays of energy efficient equipment at hardware stores).  Although the SBEERC will be lightly staffed with personnel, they will have a comprehensive knowledge of where to go for any particular issue or question.  If an answer cannot be found in-house, the SBEERC will have a comprehensive database of contacts and resources to refer customers to.  Each customer that contacts the SBEERC will be provided a feedback card in 2 weeks to ensure that their needs were met and to request whether they need additional assistance taking the “next step.”  The primary means of customer contact will be in person, by phone, and by e-mail.

Both SCE/SCG and the SBEERC will share all inquiry information with the other to best coordinate follow-up actions to be taken, recognizing in some cases, interaction directly with SCE/SCG would be most efficient and appropriate (e.g. in the case where the decision to proceed has been made and the project is moving into the rebate stage).  In other instances customers may need extra attention that can be best provided by the local SBEERC staff resources to ensure that the project does not become a lost opportunity.

Materials

This program will produce co-branded (SBEERC/SCE/SCG) residential and non-residential fact sheets.  Direct mailings about the program may be sent to target audiences with general program information. The program will distribute SCE/SCG statewide materials (Express Efficiency, SBD, SPC, upstream HVAC and motors (if approved), schools, single and multi-family rebate programs, as well as conducting workshops and community events.

This program addresses many of the policies and priorities as set forth in D.03-08-067 and California Public Utilities Code Section 381.

The Partnership Approach

The SBEERC proposes to build on the respective strengths of SCE/SCG and the SBCCOG to overcome identified participation barriers, better serve local needs and hard-to-reach customers, increase participation in energy efficiency programs and thus to increase the overall long-term sustainability and value of energy efficiency programs to the member agencies and citizens on the South Bay Cities COG.  This partnership is intended to fulfill the desire of the CPUC to realize meaningful partnerships between local governments and utilities in order to foster, among other goals, cost-effective programs.  The partnership will strive to maintain both SCE/SCG’s and the SBCCOG's desire to protect their respective individual interests, identities and respective future roles in delivering energy efficiency and other programs in the future.

# Section II.	Program Process

## A.	Program Implementation

The proposed program has several elements, including:

- Local Energy Efficiency Resource Planning

- Establish Energy Efficiency Resource Center

The objectives, primary tasks, milestones, marketing, coordination and other specifics of each of these program elements are described in this section.

Local Energy Efficiency Resource Planning Element

This program element will complete an Energy Efficiency Plan for the region that can tie its current and future activities to a long-term strategy, as well as align them with the resource planning efforts of the IOUs.   The strong partnership with SCE/SCG in this effort will ensure that the appropriate information necessary to best assess and target energy efficiency activities is available.  For example, understanding penetration of energy efficiency measures across public, business and residential sectors on a city or regional basis will allow the partnership to best implement current programs to achieve the greatest results.  Understanding what audits have been completed in the past that have not been followed through to implementation would also significantly increase the potential for results in the PY2004/PY2005 Programs.  Lastly, identifying areas of the region that may be experiencing higher levels of growth allow the effort to target these areas for higher levels of energy efficiency outreach in order to defer capital upgrades and provide added reliability.

The South Bay Cities Council of Governments, through its committees, will ensure that the planning involves all relevant stakeholders of the region.  This “round table” approach to regional efficiency will ensure the greatest commitment by local stakeholders.

Primary Task and Milestones

The following task will be accomplished as part of this program element:

- Meet with appropriate SCE/SCG staff to evaluate available data, including:

  - Available information on past program participation by zip code, focusing on customers that have expressed interest, but not followed through on implementation.

  - Electricity and natural gas consumption and demand by NAICS code.

  - Major transmission and distribution feeders loading and projected growth to identify customer blocks with high electricity use and higher potential for energy savings.

- Conduct surveys and focus groups to :

  - Assess the degree to which energy efficiency program information has reached SBCCOG  member cities’ constituents

  - Identify specific barriers to energy projects and steps in the process that caused energy efficiency projects to either fail or not be considered.

  - Identify specific information, education and training needs for the community to incorporate into scheduling of actual information programs

Goals

Complete a targeted energy efficiency Action Plan for the SBCCOG region by January 2005.

Customer Description and Enrollment

Not applicable.

Marketing and Outreach

Once developed in draft form, the plan will be distribute broadly to SBCCOG region’s stakeholders for comment.

Coordination with Other Entities

The SBEERC staff and consultants will work closely with SCE/SCG and other local stakeholders to collect data for the plan and to complete it in a timely manner.

Contractor Support

The SBCCOG has retained the services of K. J. Kammerer & Associates for this particular element.  Mr. Kammerer was the primary author of the 20-year San Diego Regional Energy Infrastructure Study and the 2030 San Diego Regional Energy Strategy, and has been supporting the SBCCOG for several months so is well qualified to accomplish this task.

Establish Energy Efficiency Resource Center

Objectives

The Energy Resource Center and Information, Education and Training Element will implement a targeted information and education program in the SBCCOG region.  The primary component of this element is an Energy Resource Center, which is composed of a centrally-located facility, that will provide a  location where residents, businesses and others can call or visit and gain access to valuable resources and local expertise.  This Center is intended to augment, not duplicate the resources and capabilities that already exist in the investor-owned utilities resource centers (SCG’s ERC/ and SCE’s CTAC).  In addition, the close coordinated and resource sharing will occur with the IOUs with training events planned at the ERC and CTAC.  The SBEERC will provide the following resources:

- A comprehensive collection of information on all energy efficiency programs available to the community (as will as other programs, such as the Self-Generation Program).

- Knowledgeable staff to assist customers in matching this information to meet their needs.

- A user friendly kiosk for customers to research and gain access to the wealth of information available on the internet (this resource is particularly important for hard-to-reach customers that may not have ready access to internet resources).

- Training and seminars that will target various sectors that are deemed to have been underserved by the results of the surveys conducted in the regional customer surveys (discussed previously).  Close coordination with SCE/SCG and other program providers in the region will ensure that duplication of effort is avoided and the SBEERC enhances, and does not detract from the overall program offerings.

Primary Task and Milestones

- Completion of the Energy Efficiency Resource Center (by end of 1st Qtr 2004).

- Meeting with respective SCE/SCG and SBEERC staff to assess available information and training materials versus specific needs and identify those specific resources that would be needed to support the SBEERC (e.g. collaterals, training courses, etc.).  (by end of 2nd month).

- Procure energy efficiency resource library and tool lending library (by end of 1st quarter 2004).

- Energy Efficiency Resource Center open houses (ongoing)

- Commence training schedule and conduct training and information sessions on a regular basis (start in second quarter 2004).

Goals

Conduct 4 information/training sessions for the public sector, 12 sessions for the business sector, and at least 3 events for residential customers.

Customer Description and Enrollment

For the purposes of this program, customers will be defined as all residential, business and industry ratepayers in the SBCCOG region.  Enrollment will be accomplished through various means, including advertising through industry partners (e.g. Chambers of Commerce), an SBEERC newsletter delivered via direct email, as well as through local jurisdiction bill inserts (e.g. water bills).  Enrollment for training courses will be accomplished through email, phone and fax to the SBEERC offices.

Marketing and Outreach

Marketing and outreach for the education and information programs will be accomplished jointly by SBCCOG and SCE/SCG through mail inserts and newsletter articles with industry partners (e.g. Chambers of Commerce), an SBEERC newsletter delivered via direct email and through local jurisdiction bill inserts (e.g. water bills).  The SBEERC will also partner with organizations like the Regional Business Assistance Network (RBAN).  RBAN is a cooperative effort that leverages over 450 service providers throughout the Los Angeles County to provide quick and effective business assistance to companies.

Coordination with Other Entities

In order to minimize overlapping messages and to minimize costs, close coordination will be accomplished with SBER, SCE/SCG, other non-IOU providers of education and information services, as well as the significant amount of resources available through the California Energy Commission and the Department of Energy.

Contractor Support

Contractor support will be provided for overall coordination of information programs, as well as materials design and printing.

## B.	Marketing Plan

The SBEERC will use a wide range of methods to market the SBEERC services, including:

- Flyers used to market specific seminars to targeted markets;

- Inserts in member agency water bills;

- Descriptions of the technical centers, exhibits and demonstration capabilities are detailed on the Web site.

- A general information brochure that briefly describes all the services available at the SBEERC.

- SBER web site and community events

Promotion of education and information programs offered by the SBEERC will be accomplished through various means, including newspaper articles, ads, mail inserts, newsletter articles with industry partners (e.g. Chambers of Commerce), an SBEERC newsletter delivered via direct email and through local jurisdiction bill inserts (e.g. water bills).  Events will be listed on all local events calendars, including the SBER web site and that of the local SBCCOG cities.  Requests will be made to include this information on the web site of libraries, and various electronic media like the South Bay Economic Development Partnership’s Events & Notices page on their web site.  The SBEERC will also take a travel display of information on the road to community events.

A detailed marketing plan will be developed during the first 2 months of the program.

## C.	Customer Enrollment

The program targets all SCE/SCG electric or natural gas customers, with an emphasis on hard-to-reach audiences of low-income, seniors, renters and non-English speaking audiences of diverse ethnic backgrounds.

Enrollment for programs will be accomplished through various means, including email, phone and fax to the SBEERC.

## D.	Materials

This program will produce co-branded (SBCCOG/SCE/SCG) residential and non-residential fact sheets.  Direct mailings about the program may be sent to target audiences with general program information. The program will distribute SBER as well as SCE/SCG statewide materials (Express Efficiency, SBD, SPC, upstream HVAC and motors (if approved), schools, single and multi-family rebate programs, as well as conducting workshops and community events.

## E.	Payment of Incentives

As an information only program, there will be no incentives paid to customers.

## F.	Staff and Subcontractor Responsibilities

Table 4 describes the relative roles and responsibilities of SBCCOG and SCE/SCG staff and subcontractors.

| Table 4: Roles and Responsibilities |
| --- |
| Staff or Consultant | Role/Responsibility | Level of Effort |
| SBEERC Program Director | Overall coordination of SBEERC-SCE/SCG partnership | 1.0 FTE |
| SBEERC Project Manager | Day-to-day operations and project management activities | 1.0 FTE |
| SBEERC Administrative Assistant | Day-to-day administrative issues | 0.5 FTE |
| IOU Program Manager | Coordination with IOU resources and statewide programs | 0.3 FTE |
| Consultant- K.J. Kammerer & Associates | Technical assistance with overall program management and implementation | As needed to augment local resources |

## G.	Work Plan and Timeline for Program Implementation

Table 5 outlines the work plan and timeline for accomplishment of major program objectives.

# Section III.	Customer Description

## Customer Description

This program seeks to serve a wide range of customers in the SBCCOG region.

The market segments addressed by this program are indicated in the following table:

|  | Market Segment |
| --- | --- |
| Program Element | Agricultural | Commercial | Industrial | Government | Residential – multi-family | Residential – single-family | Institutional | Schools | New Construction |
| Energy Efficiency Resource Center |  | ( | ( | ( | ( | ( | ( | ( | ( |

## Customer Eligibility

Customers of both SCE and SCG will qualify to participate in this program targeted to those in the South Bay region.

## Customer Complaint Resolution

Customers will be provided information that clearly delineates the means by which they can file and resolve complaints on the program.  This process will include the following procedure:

If a customer has a question, concern or dispute that relates to the SBEERC program policies, rules or procedures, the customer will be encouraged to first contact the SBEERC Program Director (contact information to be provided).  The SBEERC Program Director will promptly evaluate the issue and seek to resolve the dispute consistent with program rules, policies and procedures (within 48 hours).

If the matter is not satisfactorily resolved, the party should contact the SBEERC Board representative (contact information to be provided).

If the party feels the matter has not been adequately resolved by the SBEERC, they should contact the Business Customer Center at SCE/SCG.

If the customer is still not satisfied, they will encouraged to contact Tim Drew from the Energy Division at the California Public Utilities Commission.

If a customer has a dispute relating to work performed by a licensed contractor, the program will refer the customer to the Contractor State Licensing Board.  If a customer has a dispute relating to work performed by a non-licensed contractor, the program will recommend that the customer work directly with the contractor to resolve the dispute.

## Geographic Area

This program targets SBCCOG member cities as shown in Figure 1.

The South Bay region covers an area of 161 square miles and contains fifteen cities plus portions of the City of Los Angeles and unincorporated portions of the County of Los Angeles. The region is bounded by the Los Angeles International Airport (LAX) and the Port of Los Angeles    .  Jurisdictions included in the South Bay are the cities of: Carson, El Segundo, Gardena, Hawthorne, Hermosa Beach, Inglewood, Lawndale, Lomita, Manhattan beach, Palos Verdes Estates, Rancho Palos Verdes, Redondo Beach, Rolling Hills, Rolling Hills Estates, and Torrance. The region also includes the 15th District of the City of Los Angeles (the LA Strip) and portions of unincorporated Los Angeles County.

The South Bay, as a region, is still heavily reliant on the aerospace and related industries.

# Section IV. Measure and Activity Descriptions

As an information only program, there are no measures to be implemented.

## Energy Savings Assumptions

As an information only program, no energy savings calculations are required.

## Deviations in Standard Cost-effectiveness Values –

Not applicable.

## Rebate Amounts

Not applicable.

## Activities Descriptions

Not applicable.

# Section V. Goals

# Program Goals include the following:

- Conduct at least 4 training sessions for the public sector, 6 sessions for businesses, and at least 4 events for residential customers.

- Promote SBCCOG resources and energy efficiency information at 20 community events or more.

- Respond to every customer inquiry within 48 hours.

- Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent).

- Develop and Regional Energy Efficiency Plan by June 2005.

# Section VI. Program Evaluation, Measurement and Verification (EM&V)

This EM&V plan is based on the Commission’s objectives as outlined in the Energy Efficiency Policy Manual (EE Policy Manual) and adheres to the guidelines in the International Performance Measurement and Verification Protocol (IPMVP).

The proposed evaluation of the program’s success will primarily be to provide measurable and quantifiable results in the form of achieved levels of energy and peak demand savings by the program.  The success of the program is also gauged by other program evaluation studies, such as process evaluation and market assessment and customer behavior analysis studies. Such studies provide (a) ongoing feedback and corrective guidance regarding program implementation and delivery to customers through program process evaluation, and (b) measured indicators of the program effectiveness through analysis of baseline conditions and customer’s satisfaction.

To comply with the objectives of the Commission for ongoing assessment and improvement of programs, the EM&V plan will also focus on process issues. The plan may also include 1) analysis of program accomplishments: 2) analysis of program design, delivery and implementation with recommendations for program enhancements; 3) an assessment of program targeting and customer satisfaction; 4) an analysis of incentive levels and options, if any, and 5) additional market assessment and evaluation as needed. More specifically, these activities may be done as follows:

Market Assessment and Customer Behavior Analyses:  Market saturation/potential studies from statewide studies currently underway will inform the market assessment and baseline analysis to assist with future program activities.  These activities assist with assessing customer awareness, behaviors and practices given their participation in the program.

Process Evaluations: These activities may include evaluations of program delivery in terms of timeliness and customer satisfaction.  The objectives of these activities will be to provide feedback to the program implementers on elements of the program that can be improved to enhance the program’s performance. Assessing performance of various delivery aspects of the program will help to identify specific, actionable servicing actions to make the program more effective, including statewide integration between the investor-owned utilities, and with other implementers of California programs, as appropriate to improve program delivery.

Budget and Potential EM&V Contractors:

The program will allocate approximated 5 percent of the contract amount to EM&V activities.

Potential EM&V Contractors

The abbreviated list of contractors proposed below can objectively evaluate program success and have performed work that includes impact evaluation, measurement and evaluation, measurement and verification, process evaluation, market assessment and verification of program accomplishments.  These are firms that have a proven track record of completing high quality, objective evaluations of energy efficiency programs either for the California investor-owned utilities or for other entities.  As stated earlier, this list is not inclusive of all the qualified evaluators who could objectively evaluate programs. The final list of evaluation consultants will be based on several factors including: future Commission decisions, the mix of approved programs and the experience of the evaluation consultants.

ADM Associates, Inc

Aloha Systems

Alternative Energy Systems Consulting (AESC)

Applied Management Sciences Group

Architectural Energy Corporation

ASW Engineering Management

Aspen Systems Corporation

EcoNorthwest

Energy & Environmental Economics

Energy Market Innovations

Equipoise Consulting

Freeman Sullivan

Frontier Associates

GDS Associates

Global Energy Partners

Heschong Mahone Group

ICF Consulting

Itron (RER)

KEMA-Xenergy, Inc.

KVDR Consulting

Megdal & Associates

Nextant

Opinion Dynamics

P.A. Consulting, Inc.

Quantec LLC

Quantum Consulting, Inc

Research into Action, Inc.

Ridge & Associates

RLW Analytics, Inc.

Robert Mowris & Associates

SBW Engineering

Science Applications International, Corp (SAIC)

# Section VII. Qualifications

## Primary Implementer

Table 5 summarizes the primary implementer and utility partners respective strengths.

| Table 5: Respective Program Partner Strengths and Contributions |
| --- |
| Quality or Strength | Program Partner Contribution to Partnership |
|  | SCE/SOCALGAS Staff and Resources (including consultants) | SBCCOG Staff and Resources (including consultants) |
| Close knowledge of customer data, including energy consumption, local demographics, building size, age, type, ownership, etc. | (((( (Note 1) | (( |
| Talented and committed staff | (((( | (((( |
| Experience in program design, operations, delivery and best practices | ((( | (( (Note 2) |
| Close relationship and communication channels with an extensive community-based network of resources and stakeholders | (( | ((( |
| Deep understanding of the unique local needs and challenges of customers in the SBCCOG territory, including program and policy objectives and preferred implementation strategies. | (( | (((( |
| Knowledge of the South Bay region’s unique needs, challenges, | (( | (((( |
| Comprehensive portfolio of energy programs targeting residential and business sectors. | ((( | ((( (SBER) |
| Existing program infrastructure for inspections, rebate processing, tracking and reporting. | ((( |  |
| Technical analysis capabilities including cost-effectiveness calculations, saturation and market potential studies and analysis of savings from various measures in different operating environments. | ((( | (( (Note 2) |
| Expertise in appropriate technology application and deployment. | ((( | ((( |
| Strong commitment of community leaders and local government institutions to energy efficiency through the charter of the SBCCOG |  | ((( |
| Training courses for city staff such as designers, plan reviewers and building inspectors as well as for contractors, building owners and operators and large customers, including hands-on training | ((( |  |
| Notes Particularly important will be data on electricity and gas consumption by customer SIC code; transmission and distribution pinch points, ability to identify customers with high electricity use and records of past program participation. Primarily through its retained expert consultants. |

## Subcontractors

K. J. Kammerer & Associates

- Mr. Kammerer led the development of the San Diego Regional Energy Office (SDREO).  Responsible for all aspects of energy policy, planning, development, startup, fundraising and administration of over $75M of public-good energy programs for the San Diego region- the third largest county in California and the sixth largest metropolitan area in the U.S. (1998 to 2003).

- Mr. Kammerer was the primary motivator and developer of the majority of programs now offered by the SDREO from 1998 through 2003.  These programs included the start-up of a highly successful San Diego Energy Technology and Training Center, a highly successful Cool Roofs Program that installed over 27 million square-feet of energy efficient roofs to customers throughout all of Southern California, and the highly successful San Diego Self Generation Program, which was designed to install over 8 MW of clean distributed generation per year.

- Mr. Kammerer led the reorganization of SDREO in 2001 after completing a comprehensive evaluation of various structures, including Joint Powers Authority and an independent public benefit, not-for-profit Corporation.  Led the transition from the San Diego State University Foundation to establish an independent public benefit, non-profit corporation, including application with the Secretary of the State, By-Laws, instituting financial controls and reporting, human resources, etc.  Most recently led the San Diego Regional Policy Advisory Council (REPAC) in the analysis of more formal options, strategic planning and the development of operational plans for the proposed government-led San Diego Regional Energy Authority (currently under consideration by the San Diego Association of Governments).  This effort included initiatives including, among other initiatives, more comprehensive administration of public-good funds, Community Choice Aggregation under AB 117, and development of renewable and other energy projects financed by the REA.

- Mr. Kammerer has a close working knowledge of the provisions of relevant legislation and regulatory proceedings including State of California Public Utilities Codes (Sections 381-384).  A party of record to all regulatory processes that are of interest to local governments and public agencies, particularly those that are related to the availability of public good energy funding (in particular, CPUC Rulemaking 01-08-028 and the recently proposed Order Instituting Rulemaking Regarding Implementation of Community Choice Aggregation under Assembly Bill (AB) 117 (Chapter 838, September 24, 2002).

- Mr. Kammerer was a key author, and led the completion of the San Diego Regional Energy Infrastructure Study, a comprehensive supply and demand analysis for the San Diego region during the 2000-2001 energy crisis.  In addition, was the primary author of the 2030 San Diego Regional Energy Strategy, adopted by SANDAG in June 2003.

- Mr. Kammerer has an excellent working knowledge of local government and Council of Governments processes through my experience with the close SDREO-SANDAG relationship from 1998 through 2003.  This effort included frequent direct interaction and communications with all levels including Supervisors, City Council members, Directors, and staff, to incorporate the needs of SANDAG and its member agencies into SDREO plans.

- Mr. Kammerer has active, close relationships with senior staff (and some Commissioners) of the California Energy Commission (CEC), the California Public Utilities Commission (CPUC), the California Power Authority (CPA), and the Department of Energy (DOE).

## Resumes or Description of Experience

Jacki Bacharach

Jacki Bacharach has her own business - Jacki Bacharach and Associates - which specializes in government and transportation policy and administration.   Her principal contract is with the South Bay Cities Council of Governments, a joint powers authority of 16 cities in the southwest portion of Los Angeles County, where she serves as the Executive Director.  Her duties include grant administration – including oversight responsibility for the South Bay Energy Reward program, policy development, city outreach, and working with state and regional agencies on behalf of the sub region.

Public service is important to Jacki.  She served as Mayor and Councilmember in the City of Rancho Palos Verdes for 14 years and as a Commissioner on the Los Angeles County Transportation Commission (a predecessor agency to the LACMTA) for 12 years.  On the Commission, she chaired the overall Planning Committee, the Rail Construction Committee and the Rail Planning Committee as well as serving a term as chair of the Commission itself.  She led the committees through the development of the overall rail plan for L.A. County as well as overseeing the construction of the Metro Blue and Green Lines.

Jacki was a charter member of the Alameda Corridor Transportation Authority dealing with landside access to the Ports of LA and Long Beach.  She served as the Founding Chair of the Southern California Regional Rail Authority - the five county agency that is operating the Metrolink commuter rail system.  Additionally, she was a Founding Vice Chair for the Los Angeles-San Diego Rail Corridor Agency overseeing and improving L.A.-San Diego Amtrak service and is again the Vice Chair representing LACMTA.  Additionally, for over 5 years she chaired Southern California Rideshare and served on the regional rideshare board for over 10 years.

She is currently the Acting Chair of the Senate Advisory Commission on Cost Control in State Government.   She also served on the State Commission on Local Governance for the 21st Century.   She is on the Board of Directors of Odyssey which is a non-profit organization promoting the benefits of alternative forms of transportation having just completed service as the co-chair.

She served as a member of the National Commission on Intermodal Transportation appointed by U.S. Secretary of Transportation Federico Peña as well as working with the Secretary as a member of President Clinton’s Transition Team Transportation Cluster Group.  In both of these positions, she was the only member from California.

Marilyn Lyon

- Contract position as South Bay Energy Rewards Program Coordinator.  Provided support and facilitation between the participating local governments and all the program activity as it affects the residents and businesses of 15 South Bay Cities and the coordination and support of various consultants working on the grant program. 2002-03.

- Chief political advisor to wife of gubernatorial candidate for the State of California.  Duties included scheduling, advance and assistance with the media. 2002

- Owner of Lyon & Associates a Public Relations and Marketing business since 1991.

- Mayor 1996 & 2001, City Council member for Rancho Palos Verdes 1993-2001.

- California State Governor’s Appointee to California Regional Water Quality Control Board for Los Angeles and Ventura Counties, quasi-judicial board serving as Vice-Chairman  1996-2000

- California State Governor’s Appointee to California Board of Professional Engineers and Land Surveyors.  Duties of Board included the testing, licensing and discipline of Professional Engineers.  1996-2001

- Board of Directors Boy Scouts of America, Pacifica (South Bay) District.  Public Relations Chairman.  2001-03

Southern California Gas Company

SoCalGas has actively promoted and administered energy efficiency and energy conservation programs over the last several decades.  In the last 10 years alone, customers who have taken advantage of its energy efficiency programs have saved more than 26.5 million therms of natural gas a year, or enough gas to serve 48,000 homes a year.  These programs have been varied and widespread including residential, commercial, industrial, new construction, and low income.  These programs represent the efforts of countless employees and consultants retained by the Company who are in the energy business and uniquely qualified to design, manage and administer these programs.  The underlying network that supports these efforts is best described by the “iceberg analogy”; from the surface what is observed are a variety of energy efficiency programs that incent the consumer to make energy efficient choices when purchasing or retro-fitting equipment or refurbishing a home.  What is not easily observed nor comprehended is what lies below the surface, a large work force of energy experts who have designed and modified a wide range of programs over the last twenty years and a marketing staff that as part of normal marketing efforts has utilized their existing network to promote energy efficiency to their clients.

As the Commission’s energy efficiency policy has changed over the years, SoCalGas has consistently and successfully adapted to change and responded with a portfolio of residential, nonresidential and new construction programs that meet the needs of its customers.  As in the past, SoCalGas continues to demonstrate its flexibility and ingenuity in providing energy efficiency programs and remains committed to achieving higher energy efficiency and will continue to offer programs that benefit its customers.

# Section VIII. Budget

| Budget Item | Budget |
| --- | --- |
| Administrative Costs | $132,024 |
| Marketing/Advertising/Outreach | $23,000 |
| Total Direct Implementation | $604,675 |
| EM&V | $33,789 |
| Potential Performance Award | $55,264 |
| Total Budget | $793,488 |

# Footnotes

The South Bay Cities Council of Governments (SBCCOG) includes the Cities of Carson, El Segundo, Gardena, Hawthorne, Hermosa Beach, Inglewood, Lawndale, Lomita, Manhattan Beach, Palos Verdes Estates, Rancho Palos Verdes, Redondo Beach, Rolling Hills Estates, Rolling Hills and Torrance.

INTERIM OPINION SOLICITING 2004-2005 ENERGY EFFICIENCY PROGRAM PROPOSALS AND ADDRESSING SCOPE OF PROCEEDING dated August 21, 2003.

The SBCCOG believes the SBEERC, once established, will help expand the region’s contribution to other elements of the State Energy Action Plan, including promotion of locally-based distributed generation, renewable resources and Low-Income Programs.

# Text boxes

Figure 1: Example of an SBEERC Poster Displays

Figure 1: Example of an SBEERC Poster Displays

Figure 1: Map of Geographic Area