Program Name:		Energy Efficiency Kiosk Program

Program Number:	SCG 3529

Month:			Second Quarter 2008

# Second Quarter 2008

Submitted by

Ferrell Van Raalten

Intergy Corporation

626-256-0526 ext 226 – tel

626-256-0525 – fax

ferrell.vanraalten@intergycorp.com

- Program description

The Energy Efficiency Kiosk Pilot program will implement and test a strategy, using kiosks in lending and retail institutions, to introduce energy efficiency into the buying habits of single-family homeowners located in the service territories of SoCalGas and SCE who are considering remodeling or retrofitting their homes.  The program’s overall activities are to install 20 kiosks at banks or lending institutions, as well as four static (non-kiosk) displays. The program will promote natural gas and electric energy efficiency upgrades through interactive kiosks. To increase the effectiveness of the kiosks, extensive marketing activities including give-away DVDs, a website, and community and industry promotion will be done.

- Administrative activities (describe)

- Developed draft copy of East West Bank English/Spanish Brochure

- Developed draft copy of East West Bank English/Mandarin Brochure

- Continued work on the East West Bank Kiosk Poster

- Began coordination of Cast Party

- Worked directly with Southern California Gas Company and Southern California Edison to obtain approvals on materials and plan events

- Coordinated speaker line up and prepped speakers for East West Bank event

- Printed additional survey cards

- Organized and held Kiosk Cast Party (invitations, event logistics and gifts)

- Developed and printed East West Bank Kiosk Posters (8)

- Processed surveys through SCE for the energy and water analyses.

- Processed gift cards to customers.

- Marketing activities (describe)

- Developed East West Bank Event Strategy

- Developed media lists for East West Bank event

- Coordinated event logistics with East West Bank

- Continued editing East West Bank Media Alert

- Continued editing East West Bank Press Release

- Finalized copy of East West Bank English/Spanish Brochure

- Finalized copy of East West Bank English/Mandarin Brochure

- Developed East West Bank Event Strategy and Event Flow

- Finalized media lists for East West Bank event

- Finalized and distributed East West Bank Media Alert

- Finalized and distributed East West Bank Press Release

- Conducted phone media outreach and secured media coverage

- Coordinated media interviews and compiled news coverage

- Managed/attended event with East West Bank

- Obtained approval, finalized, and printed East West Bank brochures – Spanish and Mandarin

- Gathered media clips from East West Bank event

- Coordinated efforts directly with East West Bank

- Began public relations planning with bank trade media

- Direct implementation activities (describe).

- Installed kiosks in the first set of (4) selected East West Bank locations:

  - San Gabriel

  - North El Monte

  - Alhambra Main

  - Rosemead

- Moved the (4) kiosks at the East West Bank to the second set of locations:

  - LA Chinatown

  - Industry-Azusa

  - Monterey Park-Ramona

  - Westminster

Summary of surveys returned/processed:

| Month | Incentive 1 | Incentive 2 | Incentive 3 | Totals |
| --- | --- | --- | --- | --- |
| February | 1 | 0 | 0 | 1 |
| March | 13 | 0 | 0 | 13 |
| April | 11 | 0 | 0 | 11 |
| May | 24 | 61 | 0 | 85 |
| June | 19 | 8 | 0 | 27 |
| Totals | 68 | 69 | 0 | 137 |

Deliverable 1: Signed agreements with hosting sites and begin other sub tasks.

Arrowhead Credit Union, with 27 branches, many of which are concentrated in the San Bernardino area has agreed to be the program’s primary hosting site. East West is a full-service commercial bank with over 50 locations in Southern California, and is also very enthusiastic about hosting kiosks for the program.

This deliverable is complete.

Deliverable 2: Develop marketing, public relations and outreach strategies and plan.

The marketing plan was developed, submitted and approved after a review with the program managers from SoCalGas and SCE.

This deliverable is complete.

Deliverable 3: Prepare and design marketing materials and collaterals: website, brochures, branding, program messages, point-of-sale displays, and posters. Prepare public relations media releases and create 1,000 DVDs.

The basic designs for the kiosks have been submitted, reviewed and approved and are being printed. Copies of the DVDs are completed and being shipped. All materials have been printed.

The draft of the website’s home page has been completed and approved. The backup pages have been completed and are being programmed into html prior to approval.

This deliverable is pending final approval.

Deliverable 4: Develop script and schedule of video production

Development of the script and production schedule for the video was completed and submitted to the SoCalGas/SCE program managers for review by the utilities communications and legal departments. Script has been approved. (Refer to narrative report for December, 2006 for details.)

This deliverable is complete.

Deliverable 5:  Production of video, including filming in English and Spanish, resulting in a rough cut.

Filming for the video is complete. We filmed our selected interviewees (see approved script for names of interviewees), plus spouses and children at ten different locations. Three interviews were conducted in Mandarin Chinese, three in Spanish and four in English.

This deliverable is complete.

Deliverable 6: Post-production and completion of video, including editing, animation and graphics.

All versions of the video—English, Spanish and Mandarin—have been approved. A meeting was held October 25 at SeePoint, the kiosk manufacturer, for final approval of the completed kiosk. Both SoCalGas and SCE have provided final approval for the video and kiosk.

This deliverable is complete.

Deliverable 7: Develop designs for kiosks

SeePoint Technology, a kiosk manufacturing company in Redondo Beach, will manufacture the program’s 20 kiosks. The kiosk design was approved.

This deliverable is complete.

Deliverable 8: Manufacturing and completion of 20 kiosks.

SeePoint Technology has manufactured the program’s 20 kiosks. The kiosks are prepared for uploading of video, and completion.

This deliverable is complete.

Deliverable 9 - Completed kiosk installation at all host sites.

Kiosks are installed at all of the selected Arrowhead Credit Union locations.  Kiosks are installed at the second set of (4) selected East West Bank locations.  These East West Bank locations will rotate every (6) weeks.  As of 8/15/08, kiosks will be installed at (6) selected East West Bank locations and (14) Arrowhead Credit Union locations.

Deliverable 10 - Train lending officers in kiosk use and DVD giveaway,

incentive application and tracking paperwork.

Arrowhead Credit Union lending officers have been trained in the kiosk processing and how the incentive program works.  East West Bank lending officers at the second set of (4) locations have been trained in the kiosk processing and how the incentive program works.

- Program performance/program status (describe)

(  Program is on target. The program has completed most of the development phase, including video production and kiosk manufacturing. The hosting sites have been selected; and a detailed marketing and public relations plan has been completed. Script and production schedules and budgets have been completed. Interviewees have been selected and the video has been filmed and post-production is done. The video has received final approval and is being translated into Spanish and Mandarin. Marketing pieces and collateral have been designed and are about to be printed. All elements have been reviewed and approved by the utilities.  Deliverables 1, 2, 3, 4, 5, 6, 7 and 8 are complete.  Deployment of kiosks and training of lending officers are repeated every (6) weeks at the East West Bank due to the rotation of locations of the (4) kiosks.  As of 8/15/08, kiosks will be rotated through (6) selected East West Bank locations and permanently at (14) Arrowhead Credit Union locations.

⁬ Program is exceeding expectations

⁬ Program is falling short of expectations

- Program achievements (non-resource programs only):

Kiosk development is complete.

- Deliverable 1--Hosting institution sites have been selected, memorandums of understanding have been signed.  This is complete.

- Deliverable 2--A detailed marketing and public relations plan.  This is complete.

- Deliverable 3: Prepare and design marketing materials and collaterals: website, brochures, branding, program messages, point-of-sale displays, and posters. Prepare public relations media releases and create 1,000 DVDs. Designs have been approved and printing has begun.  This is complete.

- Deliverable 4—Video script and production schedule.  Interviewees were selected, and questions for the interviewees.  This is complete.

- Deliverable 5—Rough-cut of video.  This is complete.

- Deliverable 6—Post-production and completion of video.  English, Spanish, and Mandarin versions.  This is complete.

- Deliverable 7—Development and design of kiosk.  This is complete.

- Deliverable 8: Manufacturing and completion of 20 kiosks. SeePoint Technology has completed the manufacturing of the program’s 20 kiosks.  This is complete.

- Deliverable 9 -- Completed kiosk installation at all host sites.  Kiosks are installed at the second set of (4) selected East West Bank locations.  These East West Bank locations will rotate every (6) weeks.  As of 8/15/08, kiosks will be installed at (6) selected East West Bank locations and (14) Arrowhead Credit Union locations.

- Deliverable 10 -- Train lending officers in kiosk use and DVD giveaway, incentive application and tracking paperwork.  Arrowhead Credit Union lending officers have been trained in the kiosk processing and how the incentive program works.  East West Bank lending officers at the second set of (4) locations have been trained in the kiosk processing and how the incentive program works.

- Changes in program emphasis, if any, from previous period (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

Activities expected in the next quarter include:

- Moving (2) kiosks from the Arrowhead Credit Union to the East West Bank.

- Move (1) kiosk from the Arrowhead Credit Union to the L.A. Co. Fair from 9/5-9/28.

- Rotate the (6) kiosks to the next set of (6) East West Bank locations:

  - Rowland Heights

  - Arcadia-Baldwin

  - Lincoln Heights

  - Montebello

  - Ontario

  - Irvine Jeffrey

- Changes to staffing and staff responsibilities, if any.

Program managers at both utilities have been changed.

- Changes to contracts, if any

None

- Changes to contractors and contractor responsibilities, if any

None

- Number of customer complaints received

None

- Revisions to program theory and logic model, if any

None