| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1493-04 |
| Month: | April 2005 |

- Program Status

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Apr-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $380,294 |  |  | $7,332 | 2% |  |  | $7,332 | 2% | $372,962 |
| Admin | $43,148 |  |  | $7,332 | 17% |  |  | $7,332 | 17% | $35,816 |
| Marketing | $5,290 |  |  |  |  |  |  |  |  | $5,290 |
| DI | $314,546 |  |  |  |  |  |  |  |  | $314,546 |
| EM&V | $17,310 |  |  |  |  |  |  |  |  | $17,310 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.  Expenditures include some of SCE expenses.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Apr-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 141,772 |  |  |  |  |  |  |  |  | 141,772 |
| Lifecyc Therms | 2,126,586 |  |  |  |  |  |  |  |  | 2,126,586 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

  - Activities/Accomplishments

    - Administrative -

None to report

    - Marketing -

Prepared and released e-fliers regarding May Wastewater Training event. (Attachment A)

VCREA staff continued discussions and met again with representatives of VCEDA to develop opportunities for the partnership to promote energy efficiencies at their annual Business Opportunities Conference planned for October 14, 2005.  VCERC partners will have opportunity to provide speakers and participate in regional energy discussions with local business leaders.

The BEST program is now fully active in the four VCREA member cities; the VCREA office has been called for further information, and as a result, callers have been advised of services and trainings available through the VCERC and other programs offered by SCE and SoCalGas.

VCREA chair, Brian Brennan participated in the 4th Annual Municipal Green Building Conference and Expo, April 21, co-hosted by Southern California Gas Company.  Mr. Brennan was included in a panel discussion that covered the work of public agencies in developing green and energy efficient policies. (Attachment B)

The TrashFlash Newsletter, produced by Harrison Industry, will again include information on the VCERC in their summer publication.  (Attachment C)

VCERC was invited to present an overview of trainings and programs to the Thousand Oaks Business Roundtable April 12.  Approximately 30 local business leaders were in attendance and several contacts have resulted from the presentation.  Businesses are interested in more information on summer energy efficiency programs offered by SCE and SoCalGas.

    - Direct Implementation –

Training

- April 14, 2005 Residential Training – Presented by David Inger to Ventura City employees and attended by 27 employees as a “brown bag” event. (Attachment D)

Community Events Participation

- VCERC participated in the April 9 Earth Day event in Thousand Oaks with a table top display shared with several other local building groups.  Approximately 6000 participants attended the all-day event.

- VCERC was represented at the April 16 training for Tres Contados Girl Scout Adult Leaders.  The VCREA provide energy efficiency information and CFL’s to the 125 adult leaders.  As a result of this event, the ERC will be used for future resources and the energy efficiency message will be shared with the youth and their families as residential customers.

- VCERC participated the in the April 17 Ojai Earth Day at Ojai Valley School with a tabletop display.  Approximately 2500 participated in the day-long event that included other community organizations, schools and families.

- VCERC participated in the April 26th Ventura County Science Fair and Expo with a table top display and gave a project award to a student with an outstanding energy efficient light project.  He was awarded a $25 savings bond, and a small collection of ERC materials for his efforts.

- VCERC participated the in the April 26 National AgGrowKnowledge Convention, providing a speaker at two of the sessions, with 40 in attendance at each session for a total of approximately 80 participants.  Participants were community college leaders, elected trustees and teachers from across the county and the VCERC was featured as an opportunity to connect the subject of energy and the importance of efficient technology to the educational community.

A summary of plans and accomplishments for all training and community events are include in the Program Spreadsheet. (Attachment E)

Projects and Incentives

VCREA welcomed Ventura Regional Sanitation District as a new public agency to the board and will now have another agency connection for new energy efficiency projects.  An initial on-site meeting provided VCREA staff with first-hand look at several potential energy efficiency retro-fit projects.

VCREA staff continued to work closely with the cities of Oxnard and Thousand Oaks in developing project documentation requested by the cities for projects identified.

A monthly update of the identified energy efficiency retrofit projects to date is included as Master Project List. (Attachment F)

Plans and Policy

VCREA staff attended a meeting with Planning Directors from the Tri-Counties (VTA, SB, SLO) to initiate contacts for energy planning efforts, expanded training markets and provide general introduction for the local energy efficiency efforts.

VCREA staff have been requested to meet in May with representatives of the League of Women Voters to discuss energy plans and policies for local public agencies as well as programs that serve the general public.

      - Audits, Site Surveys and Partnerships –

Audit of the Hill Canyon wastewater treatment facility was completed this month.  The report is being prepared at this time.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

- On March 24, VCREA staff met with representatives of the public agencies to provide an update and coordination on projects and incentives.  Discussion focused on expanding energy efficiency opportunities for the newest agency members, providing for training and support to operating staff, and securing commitments to go forward with projects for which an incentive has been reserved.

- The City of Ventura is underway with its first project:  the installation of VFD’s on three 100-hp pumps on one of the water booster pump stations.  On March 30, 2005, the California Energy Commission approved the City’s low-interest loan application for all of the projects identified by VCREA.  Construction on the first of these projects will begin in May.

- The City of Thousand Oaks has begun its first project:  an exterior lighting retrofit at the Municipal Services Center.

- The City of Oxnard has two projects underway: a lighting project at the Del Norte Regional Recycling and Transfer Station, and a city-wide traffic signal and street sign lighting efficiency project.

- The County of Ventura has completed one project this month:  a lighting retrofit at Todd Rd. Jail, Santa Paula.  Two additional projects are underway:  VFD retrofit on a 350-ton chiller at Todd Rd. Jail, and a major HVAC upgrade 646 County Square Dr., Ventura.

- A monthly update of the identified energy efficiency retrofit projects to date is included as Master Project List.

      - Calculated and Actual Payment Reconciliation - None

      - EM&V

No activity this month.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

VCREA participated in various meetings, coordinative phone calls and e-mail exchanges with SCE and SCG to discuss incentive issues and program proposals for 2006-08.

KEMA’s BEST program has been well received and as a result, has created exposure to other utility energy efficiency programs and may be expanded in the months ahead as additional funds are leveraged and available.

VCREA staff participated in a second round of discussions with Navigant Consulting to determine opportunities for energy efficiency planning through the CALeep program that would leverage and tie energy efficiency with green building and as a result, expand capabilities for the Partnership to implement new construction energy efficiency in the region.

VCREA participated in the Los Angeles County SCE/SCG partnership event April 20 that included about 125 public agency staff and officials to discuss opportunities to leverage and replicate successful partnerships.

- Changes to Subcontractors or Staffing

None

- Additional Items

Supporting Documentation

- Marketing Materials

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| Table E - Training Documentation |
| --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees | Training |
|  |  |  | Type | Number | Date | Location |
| Residential “Brown Bag” Training |  |  | Residential | 27 | 4/14/05 | Ventura |

- Trade Show and Public Events

| Table F.1 - Trade Show and Public Events |
| --- |
| Event Description | Event |  |
|  | Location | Date |
| Conejo Valley Earth Day | Thousand Oaks | 4/9/05 |
| Tres Contados Girl Scout Adult Leadership | Ventura | 4/16/05 |
| Ojai Earth Day | Ojai | 4/17/05 |
| Ventura County Science Fair and Expo | Ventura | 4/26/05 |
| National AgGrowKnowledge Convention | Ventura | 4/26/05 |

| Table F.1 - Trade Show and Public Events |
| --- |
| Event Description | Event |  |
|  | Location | Date |
| Conejo Valley Earth Day | Thousand Oaks | 4/9/05 |
| Tres Contados Girl Scout Adult Leadership | Ventura | 4/16/05 |
| Ojai Earth Day | Ojai | 4/17/05 |
| Ventura County Science Fair and Expo | Ventura | 4/26/05 |
| National AgGrowKnowledge Convention | Ventura | 4/26/05 |