| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential Energy Audit |
| IOU Service Area: | SCG |
| Program Number: | 1465-04 |
| Program Type: | IOU Statewide Program |
| Month | May - 05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $2,018,136 | $24,550 | 1% | $983,563 | 49% |  |  | $983,563 | 49% | $1,034,573 |
| Admin | $380,862 | $9,906 | 3% | $217,732 | 57% |  |  | $217,732 | 57% | $163,130 |
| Marketing | $162,000 |  |  | $73,093 | 45% |  |  | $73,093 | 45% | $88,907 |
| DI | $1,322,274 | $14,644 | 1% | $692,738 | 52% |  |  | $692,738 | 52% | $629,536 |
| EM&V | $153,000 |  |  |  |  |  |  |  |  | $153,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | May-05 | % of Goals |  | Cumulative |  | % of Goals |  | Committed |  | % of Goals |  | Cumulative & Committed |  | % of Goals |  | Goals Minus Cumulative |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HTR Goal | 640 | 15 |  | 2% |  | 842 |  | 132% |  | 0 |  | 0% |  | 842 |  | 132% |  | +202 |
| Online Goal | 1,100 | 9 |  | 1% |  | 522 |  | 48% |  | 0 |  | 0% |  | 522 |  | 48% |  | 578 |
| Mail In | 1,700 | 227 |  | 13% |  | 8416 |  | 495% |  | 0 |  | 0% |  | 8416 |  | 495% |  | +6716 |
| Phone | 2,200 | 2 |  | 1% |  | 1051 |  | 48% |  | 0 |  | 0% |  | 1051 |  | 48% |  | 1149 |
| CD Rom | 600 | 0 |  | 0% |  | 308 |  | 51% |  | 0 |  | 0% |  | 308 |  | 51% |  | 292 |
| On site audit | 800 | 36 |  | 5% |  | 2016 |  | 252% |  | 0 |  | 0% |  | 2016 |  | 252% |  | +1216 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include continued refining of the customer participation and process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

    - Marketing

- As a result of a bill insert sent to small Commercial & Industrial customers, an additional 41 AMC movie ticket cards were mailed to qualifying customers for their participation in the on-line audit.

    - Direct Implementation

      - For Audits and Site Surveys  - see 1.1.3

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -  not applicable.

      - If total month’s rebates paid or direct install costs differ from total calculated in report workbook, provide discussion of difference. – not applicable.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

Per CPUC Decision 04-12-019, So Cal Gas filed a modified Program Implementation Plan (PIP) for this program on December 13, 2004.

- Coordination Activities
Coordination activities are detailed in the PIP.

- Changes to Subcontractors or Staffing

Additional contract workers were added to help process the mail-in audits.

- Additional Items 
None

Supporting Documentation

- Marketing Materials –

None this month

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation –

None this month.

- Trade Shows and Public Events –

None this month