| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1404-04 |
| Month: | May 2005 |

- Program Status

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | May-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $793,490 | $53 | 0% | $40,751 | 5% | $14,828 | 2% | $55,580 | 7% | $752,739 |
| Admin | $132,026 | $53 | 0% | $12,854 | 10% | $14,828 | 11% | $27,683 | 21% | $119,172 |
| Marketing | $23,000 |  |  | $2,023 | 9% |  |  | $2,023 | 9% | $20,977 |
| DI | $604,675 |  |  | $25,874 | 4% |  |  | $25,874 | 4% | $578,801 |
| EM&V | $33,789 |  |  |  |  |  |  |  |  | $33,789 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | May-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 1 | 25% | 5 | 100% | 0 | 0% | 5 | 125% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 0 | 8% | 6 | 50% | 0 | 0% | 6 | 50% | 6 |
| Conduct at least 4 events for residential customers. | 4 | 1 | 25% | 18 | 450% | 0 | 0% | 18 | 450% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 2 | 16% | 23 | 192% | 0 | 0% | 23 | 192% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 1 | n/a | 25 | n/a | 0 | n/a | 25 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

- Team signed lease and moved into new office facilities at 3868 Carson Street, Torrance.

- Team participated in meetings, conference calls and other communication with Partners regarding the existing program and planning for future program.

    - Marketing –

SBESC:

- Sent out first issue of e-newsletter in new format regarding the “Flex Your Power” event on May 19, 2005.

- Created article for Seasons Magazine, the City of Torrance Summer Publication.

- Completed arrangements for SBESC’s inclusion in a resource book developed by The Daily Breeze entitled “The Source” to be published in June.  Includes the Center’s half page ad.  See attachments.

- Full page ad appeared on Daily Breeze Graduation Special Edition published on June 9, 2005.

- Prepared and mailed 201 letters with special flyer to South Bay Hotels and motels promoting our June 22 energy efficiency training.

Updated website with new information and photographs of recent events.

    - Direct Implementation

- Training

- SBESC delivered energy efficiency workshops for residential customers during the reporting period as follows:

  - May 11 –Residential training at the Orchard Mobile Home Park in Lomita.  Leveraged non-utility direct install program with American Synergy.

  - May 25 - Public Agency training for South High School class of special education students and instructors who had assisted with volunteer hours for SBESC.

Follow-up for training event included thank you letters and participation certificates. Most of the attendees rated the event good to excellent.

Community Events

- May 4 – Los Angeles – SCAG General Assembly – Exhibited and Program Manager attended Energy Committee Meeting

- May 19 – El Segundo “Flex Your Power” Conference.  SBESC collaborated with Flex Your Power to coordinate this event at Raytheon Corporation.  A small business testimonial from one of the businesses that had received an energy audit by SBESC consultant was provided and SBESC Program Manager spoke. There were over 150 attendees

Energy Efficiency Action Plan

- The plan is currently being worked on and a first draft will be completed in time to be incorporated in current program.

      - Audits, Site Surveys and Partnerships - None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization – Not applicable

      - Calculated and Actual Payment Reconciliation - None

    - EM&V

Nothing this month.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

- SBCCOG is participating in the Navigant CaLEEP Pilot Program.  Navigant will complete energy efficiency planning for South Bay Cities.

- Changes to Subcontractors or Staffing
None

- Additional Items
None

Supporting Documentation

- Marketing Materials

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| ###### Table E.1 – Training Documentation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees |  | Training |  |
|  |  |  | Type | Number | Date | Location |
| Residential EE Training | Workshop | EE Info | Residents | 13 | 5/11/05 | Lomita |
| Public Sector | Workshop | Res EE info | Students and Teachers | Not available | 5/25/05 | Not available |

| Table E.2 – Training Events Held |  |  |
| --- | --- | --- |
| Event Description | Event |  |
|  | Location | Date |
| Residential EE Training | Lomita | 5/11/05 |
| Residential EE Training | Torrance | 5/25/05 |

- Trade Show and Public Events

| Table F.2 - Trade Show and Public Events, Planned |  |  |
| --- | --- | --- |
| Event Description | Event |  |
|  | Location | Date |
| Southwood Homeowners Association | Torrance | 6/6/05 |
| Knolls Mobile Home Park | Torrance | 6/8/05 |
| SK Mobile Home Park | Torrance | 6/21/05 |
| Hotel EE Training | Torrance | 6/22/05 |
| San Rafael Mobile Home Park | Torrance | 6/23/05 |
| Skyline Mobile Home Park | Torrance | 6/30/05 |