| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | Ventura County Regional Energy Alliance – PGC |
| Program Number: | 1493-04 |
| Month: | June 2005 |

- Program Status

The Ventura County Regional Energy Alliance (VCREA), in partnership with Southern California Edison (SCE) and the Southern California Gas Company (SCG) proposes to build on the VCREA progress to date to further develop its core capabilities, to complete the development of its Energy Resource Center capability, and to implement a targeted Public Sector Program for public agencies throughout the Ventura County region.  This effort will utilize the strengths of the VCREA and its utility partners to jointly overcome identified participation barriers, better serve local needs and hard-to-reach customers, and increase participation in energy efficiency programs.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jun-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $380,294 | $261 | 0% | $7,652 | 2% |  |  | $7,652 | 2% | $372,642 |
| Admin | $43,148 | $261 | 1% | $7,652 | 18% |  |  | $7,652 | 18% | $35,496 |
| Marketing | $5,290 |  |  |  |  |  |  |  |  | $5,290 |
| DI | $314,546 |  |  |  |  |  |  |  |  | $314,546 |
| EM&V | $17,310 |  |  |  |  |  |  |  |  | $17,310 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.  Expenditures include some of SCE expenses.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Energy Effects | Goals | Jun-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Lifecyc kWh |  |  | NA |  | NA |  | NA |  | NA |  |
| Annual Therms | 141,772 |  |  |  |  |  |  |  |  | 141,772 |
| Lifecyc Therms | 2,126,586 |  |  |  |  |  |  |  |  | 2,126,586 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goal | June-05 | % of Goal | Cumulative | % of Goals | Committed | % of Goal | Cumulative & Committed | % of Goal | Goal Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 0% | 3 | 75% | n/a | n/a | 3 | 75% | 1 |
| Conduct at least 6 sessions for businesses | 6 | 2 | 33% | 5 | 83% | n/a | n/a | 5 | 83% | 1 |
| Conduct at least 4 events for residential customers. | 4 | 0 | 0% | 5 | 125% | n/a | n/a | 5 | 125% | -1 |
| Promote VCEEC resources and energy efficiency information at 20 community events or more. | 20 | 1 | 5% | 16 | 80% | n/a | n/a | 16 | 80% | 4 |
| Respond to every customer inquiry within 48 hours. |  | Met | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Good and Excellent | Met | Good and Excellent | met | n/a | n/a | Good and Excellent | Met |  |
| Reduce Energy Consumption in Major facilities of VCREA member agencies by 8 % | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |
| Reduce peak demand in major facilities of VCREA member agencies by 5% or more | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a |

  - Activities/Accomplishments

    - Administrative -

None to report

    - Marketing -

- Prepared and released e-fliers regarding July 7th Energy Efficiency Best Practices for Public Planning Policy Training event to be held in conjunction with local Planning Association. (Attachment A).

- Prepared the July/August edition of the Energy Leader Newsletter for distribution the first week of July.  (Attachment B)

- VCREA staff met again with representatives of Ventura County Economic Development Association (VCEDA) as part of their monthly meeting to develop details associated with the annual Business Opportunities Conference planned for October 14, 2005.  Representatives of the partnership will be present as speakers and participants.

- Local Rotary Clubs have invited the VCREA speak on the organization and the VCERC partnership programs.  A presentation was given June 8 to the Ventura Marina Rotary Club and another similar presentation will be given on July 13 to the Westlake/Thousand Oaks Rotary Club.

    - Direct Implementation –

Training

- June 7, 2005 Energy Efficiency Training for Non- Profits was conducted by David Inger and attended by 8 participants.    (Attachment C containing flyer, press release and outline)

- June 17, 2005 Energy Efficiency for Businesses was presented by Kurt Kammerer to 65 Moorpark Chamber of Commerce members and local business leaders.  A CFL and CD of training materials were distributed to all participants. (Attachment D)

Community Events Participation

- VCERC participated in the June 18 Piru Beautification Day held across the street from the Piru Depot.  A table top display of energy efficiency information (refrigerator rebates, summer information and home audit materials) was provided as well as compact fluorescent light bulbs to those participating in the clean-up.  Approximately 135 participants attended the half-day event. (Attachment E)

A summary of plans and accomplishments for all training and community events is include in the Program Spreadsheet. (Attachment F)

Projects and Incentives

VCREA staff continued to work closely with the various public agencies in managing the projects underway this month and including:

- The City of Ventura has issued a purchase order for lighting projects at City Hall, San Jon Maintenance Yard, Police & Fire Headquarters, and two parking structures.  Work is scheduled to begin the last week of June.

- The County of Ventura has completed the HVAC upgrade (high efficiency heat pumps) at County offices located at 646 County Square Drive, Ventura. The old units were approximately 23 years old.  (Attachment G)

- The County of Ventura has completed the lighting upgrade at the Ventura County Library, Simi Valley Branch.  The retrofit includes both interior and parking lot lighting.  (Attachment H)

- The County of Ventura has completed the second and final phase of a lighting upgrade at Todd Rd. Jail, Santa Paula.  The retrofitted areas included the Kitchen, Laundry, Classrooms and support areas.  (Attachment I)

A monthly update of the identified energy efficiency retrofit projects, costs, energy savings and incentives to date is included as Master Project List. (Attachment J)

Plans and Policy

VCREA coordination with public agency and private sector representatives of the Tri-Counties (VTA, SB, SLO) planning association led to further interest in energy efficiency planning efforts that will culminate in the July 7th training session described above.  The desired outcome of the session will be to provide participants and VCREA member agencies with policy guidelines and resources that will allow for local implementation of energy efficiency policies, and to showcase the energy resource center.

      - Audits, Site Surveys and Partnerships –

VCREA staff continued to work closely with the various public agencies in managing the projects underway this month:

- The City of Ventura has issued a purchase order for lighting projects at City Hall, San Jon Maintenance Yard, Police & Fire Headquarters and two parking structures.  Work is scheduled to begin the last week of June.

- The City of Oxnard has completed the lighting retrofit at the Del Norte Regional Recycling and Transfer Station.  (Attachment H)

- The City of Oxnard is continuing with its ongoing program to install LED’s in traffic lights.

- The County of Ventura has completed the installation of the variable frequency drive on the 360-ton central plant electric chiller at Todd Rd. Jail in Santa Paula.  (Attachment I)

- The County of Ventura has installed a 75-hp supply fan motor and a 15-hp return fan motor at the Hall of Administration.  The new premium efficiency (95%) “Super-E” motors replace units which were approximately 25 years old. (Attachment J)

- The County of Ventura has begun the lighting retrofit at the Simi Valley Library.

- The City of Thousand Oaks has approved the purchase order for the Municipal Service Center Parking Lot lighting retrofit.  Work is scheduled to commence the last week of June.

A monthly update of the identified energy efficiency retrofit projects, costs, energy savings and incentives to date is included as Master Project List. (Attachment K).

- VCREA staff continued to work closely with the cities of Oxnard and Thousand Oaks in developing project documentation requested by the cities for projects identified.

- VCREA staff has coordinated with a representative of the Tri-Counties (VTA, SB, SLO) planning association to initiate further contacts regarding energy planning efforts and schedule a training session in the summer months.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization –

A monthly update of the identified energy efficiency retrofit projects to date is included as Master Project List. (Attachment F).

      - Calculated and Actual Payment Reconciliation - None

      - EM&V

No activity this month.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

VCREA participated in various meetings, coordinative phone calls and e-mail exchanges with SCE and SCG to discuss incentive issues and up-dates intended for the Program Implementation Plan to support gas savings through the Living Wisely School Program for sixth graders.

A joint meeting of VCREA staff, the Navigant representative for the CALeep program as well as the consultants that will undertake the scope of work as administered through Navigant met on June 16 to kick-off the program which is intended to help leverage the growing regional interest in energy efficiency associated with new construction and “green” building design.

VCREA staff participated in a meeting in Los Angeles hosted by the Los Angeles County Partnership in follow-up to the April 20th event hosted with the utility partners.  Representatives of the various utility partnerships introduced their work to each other and participated in general discussions of programs that are working and leveraging of resources to promote energy efficiency to the entire region.  In addition, an SCE representative presented an overview of the Demand Response Programs and solicited local government partner support for implementing these programs.

VCREA staff attended a two-day energy standards training presented by the California Association of Building Energy Consultants and held June 28 and 29 at the SoCalGas Energy Resource Center in Downey.

VCREA staff attended the June 15 joint meeting of the CPUC and CEC to hear the presentation on the Energy Action Plan and gain understanding of the particular role energy efficiency and demand response play in achieving the goals of the partnership.

- Changes to Subcontractors or Staffing

None

- Additional Items

Supporting Documentation

- Marketing Materials

Attached

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| Table E - Training Documentation |
| --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees | Training |
|  |  |  | Type | Number | Date | Location |
| Non-Profit Training |  |  | Business | 8 | 6/7/05 | Ventura |
| Business Training |  |  | Business | 65 | 6/17/05 | Moorpark |

- Trade Show and Public Events

| Table F.1 - Trade Show and Public Events for June |  |
| --- | --- |
| Event Description |  | Event |  |
|  | Participants | Location | Date |
| Piru Beautification and Clean-up Day | 135 | Piru | 6/18/05 |

| Table F.2 – Trade Show and Public Events, Planned for July |
| --- |
| Event Description | Event |  |
|  | Location | Date |