| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Crosscutting Education & Training |
| IOU Service Area: | SCG |
| Program Number: | 1258-04 |
| Program Type: | IOU Statewide Program |
| Month | September-05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Sep-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,672,314 | $130,119 | 4% | $3,052,145 | 83% |  |  | $3,052,145 | 83% | $620,169 |
| Admin | $731,664 | $46,584 | 6% | $728,537 | 100% |  |  | $728,537 | 100% | $3,127 |
| Marketing | $277,000 | $1,316 | 0% | $136,976 | 49% |  |  | $136,976 | 49% | $140,024 |
| DI | $2,574,650 | $82,218 | 3% | $2,186,633 | 85% |  |  | $2,186,633 | 85% | $388,017 |
| EM&V | $89,000 |  |  |  |  |  |  |  |  | $89,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder

| Performance Goal | Current Month’s Achievement | Cumulative Achievement | Remainder |
| --- | --- | --- | --- |
| 137 Seminars | 14 | 126 | 11 |
| 40 HTR Seminars | 10 | 99 | 0 |
| 35 Outreach Events | 2 | 31 | 4 |

| Equipment Demonstrations | # of Demonstrations | # of Attendees |
| --- | --- | --- |
| Food Service | 14 | 452 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include production and distribution of collateral, scheduling and holding classes and seminars, participating in community outreach events, planning for future classes and seminars, community and outreach events, managing of program budgets and expenditures and compiling data to prepare CPUC monthly reports.

Marketing

| Collateral | Description | Distribution | PDF File Name |
| --- | --- | --- | --- |
| Air Balance Intermediate/Advanced: Part I (Chatsworth/ERC) (flier) (#13837/39) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 950 produced 750 direct mail 200 manually | 13837 13839 flier.pdf |
| 2005 Non-Residential Title 24 Standards: Compliance & Beyond (e-mail) (#14128) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 4726 via e-mail | 14128 email.pdf |
| 2005 Non-Residential Title 24 Standards: Compliance & Beyond (flier) (#14128) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 250 produced 000 direct mail 250 manually | 14128 flier.pdf |
| Boiler Basics (flier) (#12907) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 350 produced 000 direct mail 350 manually | 12907 12905 flier.pdf |
| Air Balance Intermediate/Advanced: Part II (Chatsworth/ERC) (flier) (#13838/40) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 950 produced 750 direct mail 200 manually | 13838 13840 flier.pdf |
| Indoor Comfort News – IHACI Seminar Ad | Full-page advertisement in HVAC industry-focused monthly periodical, created to provide information on seminar content, time, date, location | Insert in publication | September ICN Ad.pdf |
| Boiler Water Treatment for Energy Efficiency (flier) (#12905) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 350 produced 000 direct mail 350 manually | 12907 12905 flier.pdf |
| Certified Permitting Professionals' Update (Title V) (flier) (#13823) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 945 produced 675 direct mail 270 manually | 13823 flier.pdf |
| DOE Multi-Seminar Flier (e-mail) (#14052) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 292 via e-mail | 14052 email.pdf |
| DOE Multi-Seminar Flier (flier) (#14052) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 350 produced 000 direct mail 350 manually | 14052 flier.pdf |
| Thermal Displacement Ventilation & Underfloor Air Distribution (e-mail) (#14131) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 4276 via e-mail | 14131 email.pdf |
| Thermal Displacement Ventilation & Underfloor Air Distribution (flier) (#14131) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 300 produced 000 direct mail 300 manually | 14131 flier.pdf |
| Native American Influences on American Cuisine (e-mail) (#12807) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2734 via e-mail | 12807 email.pdf |
| Native American Influences on American Cuisine (flier) (#12807) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 450 produced 000 direct mail 450 manually | 12807 flier.pdf |
| Food Safety Symposium (e-mail) (#12808) | Electronic-mail campaign created to provide information on seminar content, time, date, location and availability | 2734 via e-mail | 12808 email.pdf |
| Food Safety Symposium (flier) (#12808) | Single sheet flier created to provide information on seminar content, time, date, location, and availability | 400 produced 000 direct mail 400 manually | 12808 flier.pdf |

    - Direct Implementation

The following classes were offered to train and inform the market actors in energy efficient methods and technologies:

| Date | Class Description | Attendees |
| --- | --- | --- |
| 09/07/05 | # 12807 – FSEC Downey, CA Native American Influences on American Cuisine Learn how the traditional cuisine from the tribes of Native Americans has influenced table foods in various parts of the country. Foods indigenous to the Americas such as chocolate, potatoes, peppers, and squash will be discussed. Learn of their influence on cultures around the world, and in some cases how these foods sustained entire countries. Come and experience these foods as prepared by guest chef(s), demonstrating their skills using energy-efficient equipment. | 51 |
| 09/07/05 | # 13837 – Chatsworth, CA Air Balance - Intermediate/Advanced (Part 1) Once a system is installed, even if the right-sized ducts are used, the system must be balanced to provide optimum energy efficiency. Balancing also assures that the contractor is not to blame for why one room is comfortable and others are not. In Part I discover how even if there isn’t a “specified” air balance requirement, a self-check can help prevent complaints of “uneven” heating or cooling later. | 44 |
| 09/07/05 | # 14128 – ERC Downey, CA 2005 Non-Residential Title 24 Standards: Compliance & Beyond Learn about the new Title 24 standards scheduled for implementation October 1, 2005, and understand how to design buildings to achieve compliance. The event will detail new compliance requirements for 2005 and provide a well-balanced review of the standards as they apply to new construction and alterations. In addition, participants can gain insight on taking buildings beyond Title 24 compliance and qualifying for energy efficiency incentives offered by various California utilities. Co-sponsored by The Gas Company's Savings By Design program. | 146 |
| 09/08/05 | # 12907 – ERC Downey, CA Boiler Basics Owners and operators of boilers will receive an explanation of boiler controls, interlocks safeties and combustion air requirements. They will also learn techniques that may help improve boiler and distribution system efficiencies as well as energy efficiency. Air quality and boiler operation guidelines will also be discussed | 38 |
| 09/08/05 | # 13838 – Chatsworth, CA Air Balance - Intermediate/Advanced - (Part 2) Note: Attendance of Part 1 is a prerequisite for attending Part 2 Once a system is installed, even if the right-sized ducts are used, the system must be balanced to provide optimum energy efficiency. Part II is an excellent opportunity to incorporate all of the knowledge you have acquired in the other Air Balance classes, with a full night focused on measuring, adjusting and balancing airflow. | 42 |
| 09/13/05 | # 13839 – ERC Downey, CA Air Balance - Intermediate/Advanced (Part 1) Once a system is installed, even if the right-sized ducts are used, the system must be balanced to provide optimum energy efficiency. Balancing also assures that the contractor is not to blame for why one room is comfortable and others are not. In Part I discover how even if there isn’t a “specified” air balance requirement, a self-check can help prevent complaints of “uneven” heating or cooling later. | 57 |
| 09/14/05 | # 13840 – ERC Downey, CA Air Balance - Intermediate/Advanced - (Part 2) Note: Attendance of Part 1 is a prerequisite for attending Part 2 Once a system is installed, even if the right-sized ducts are used, the system must be balanced to provide optimum energy efficiency. Part II is an excellent opportunity to incorporate all of the knowledge you have acquired in the other Air Balance classes, with a full night focused on measuring, adjusting and balancing airflow. | 47 |
| 09/14/05 | # 12808 – FSEC Downey, CA Food Safety Symposium Safety concerns in handling and preparing food are of particular importance to foodservice professionals everywhere. This seminar will focus on food safety and will feature experts from the Los Angeles County Department of Health and other food safety professionals. Visit with these experts and experience some of the latest products and energy-efficient applications available for food sanitation and safety today. | 23 |
| 09/15/05 | # 12905 – ERC Downey, CA Boiler Water Treatment for Energy Efficiency This seminar goes hand-in-hand with the "Understanding Boiler Basics" seminar. Owners and operators of boilers will learn how the correct treatment of water can increase operating energy efficiency. Learn how chemical costs can be reduced. Find out how to protect your boiler from corrosion, scale and biological fouling. | 43 |
| 09/15/05 | # 13823 – ERC Downey, CA Certified Permitting Professionals' Update Certified permitting professionals know how challenging it is to keep up with a constant flow of regulatory changes affecting permits. This seminar will address the latest changes, present the best options for dealing with them and provide the most effective computerized tools for the job. Participate in a thorough review of emission quantification, quantification effects, BACT, typical permit conditions, regulatory requirements & Title V compliance with a focus on energy-efficient combustion equipment. | 34 |
| 09/27/05 | # 14189 – Mira Loma, CA Hands-on Duct Testing As a proactive response to the needs of HVAC professionals, The Gas Company and IHACI are offering hands-on seminars to teach contractors, installers and service technicians how to self-test their work prior to third-party verification for energy-efficient change-outs. These comprehensive one-night classes will include an overview of rules and regulations for residential and nonresidential HVAC system change-outs, hands-on duct leakage test demonstrations, and relevant information on how to locate a HERS rater, what forms must be completed for the building department, and more. | 33 |
| 09/28/05 | # 14190 – Long Beach, CA Hands-on Duct Testing As a proactive response to the needs of HVAC professionals, The Gas Company and IHACI are offering hands-on seminars to teach contractors, installers and service technicians how to self-test their work prior to third-party verification for energy-efficient change-outs. These comprehensive one-night classes will include an overview of rules and regulations for residential and nonresidential HVAC system change-outs, hands-on duct leakage test demonstrations, and relevant information on how to locate a HERS rater, what forms must be completed for the building department, and more. | 37 |
| 09/29/05 | # 14052 – ERC Downey, CA DOE Steam Assessment This Department of Energy one-day course covers the operation of typical steam systems and discusses methods of system efficiency improvements. The training helps industrial and institutional plant personnel - energy managers, steam system supervisors, engineers and equipment operators - identify opportunities to improve steam system performance. The training is co-sponsored by The Department of Energy, the California Energy Commission and The Gas Company. | 15 |
| 09/29/05 | # 14131– ERC Downey, CA Thermal Displacement Ventilation and Underfloor Air Distribution Learn how to design aesthetically pleasing buildings that harness natural thermal forces for improved indoor air quality, occupant comfort, energy efficiency and operating savings. This course provides architects and engineers with a graphic, compelling case for thermal displacement ventilations and underfloor air distribution technologies in contrast to conventional mechanical ventilation systems, which typically consume more energy and circulate contaminants longer. Discover the estimated energy savings possible with good thermal displacement design. | 35 |

Outreach Events:

| Date | Organization | Event Description |
| --- | --- | --- |
| 09/13/05 | US Green Bldg Council Orange County Chapter | Promoted energy efficiency seminars and distributed calendars for upcoming seminars. |
| 09/21/05 | Bakersfield Housing Authority Grant Meeting | Presented a Residential/Multi Family Appliance combustion efficiency overview and discussed rebates and incentives. |
| 09/23/05- 09/24/05 | National Association of Foodservice Equipment Manufacturers (“NAFEM”) | jointly sponsored a booth with SoCalGas, SoCalEdison, PG&E and SDG&E at NAFEM’s bi-annual convention held, this year, at the Anaheim Convention Center. A principal focus of the booth’s message was the importance of using energy efficient equipment and practices in commercial food service operations. |
| 09/29/05 | Los Angeles County Fair | Sponsored a cooking booth at this year’s L.A. County Fair. Their demo stressed use of energy-efficient equipment. |

      - Audits and Site Surveys  -

- Not applicable to this program

      - Direct Installations, Rebates, Equipment Maintenance and Optimization  -

- Not applicable to this program

      - Spending Variance

No applicable to this program.

      - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
Revised program proposal and workbook filed on April 12, 2004 per the CPUC decision.

- Coordination Activities
Seminars and workshops focusing on commercial and residential new construction co-sponsored with SCG’s “Savings By Design” commercial new construction incentive program, Residential New Construction, and Building Operators Certification (BOC) program. Supporting the development of training and education of the UC/CSU/IOU Partnership program, South Bay Cities Council of Governments and the City of Ventura Resource Centers, and the California Energy Commission’s Best Practices education workshops.

- Changes to Subcontractors or Staffing
None.

- Additional Items 
None

Supporting Documentation

- Marketing Materials –

See 1.2.2

- Point of Purchase Program Documentation –

This program does not have point of purchase activities.

- Free Measure Distribution Documentation –

This program does not distribute free measures.

- Upstream Incentive Documentation –

This program is not an upstream incentive program.

- Training Documentation –

See 1.2.3

- Trade Shows and Public Events –

See 1.2.3