| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential New Construction California Energy Star New Homes |
| IOU Service Area: | SCG |
| Program Number: | 1244-04 |
| Program Type: | IOU Statewide Program |
| Month | November-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $3,988,606 | $309,809 | 8% | $1,709,867 | 43% |  |  | $1,709,867 | 43% | $2,278,739 |
| Admin | $357,000 | $16,804 | 5% | $139,047 | 39% |  |  | $139,047 | 39% | $217,953 |
| Marketing | $91,000 |  |  | $80,625 | 89% |  |  | $80,625 | 89% | $10,375 |
| DI | $3,412,000 | $293,005 | 9% | $1,490,195 | 44% |  |  | $1,490,195 | 44% | $1,921,805 |
| EM&V | $128,606 |  |  |  |  |  |  |  |  | $128,606 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder

| Energy Effects | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 4,595 | 600 | 13% | 2,755 | 60% |  |  | 2,755 | 60% | 1,839 |
| Annual kWh | 3,338,463 | 436,169 | 13% | 2,002,232 | 60% |  |  | 2,002,232 | 60% | 1,336,231 |
| Lifecyc kWh | 60,092,341 | 7,851,038 | 13% | 36,040,176 | 60% |  |  | 36,040,176 | 60% | 24,052,165 |
| Annual Therms | 271,352 | 37,282 | 14% | 183,767 | 68% |  |  | 183,767 | 68% | 87,585 |
| Lifecyc Therms | 4,884,336 | 671,069 | 14% | 3,307,810 | 68% |  |  | 3,307,810 | 68% | 1,576,526 |

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| MEASURE / ACTIVITY NAME | UNIT DEFINITION | FINANCIAL INCENTIVE PER UNIT | UNIT GOALS | TOTAL RECORDED UNITS |
| --- | --- | --- | --- | --- |
| Single Family Inland 15% Above AB970 | Home | $500.00 | 900 | 230 |
| Multifamily 15% Above AB970 | Home | $150.00 | 6,000 | 4827 |
| Single Family Coastal 15% Above AB970 | Home | $400.00 | 0 | 0 |
| Single Family Inland 20% Above AB970 | Home | $700.00 | 500 | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

This month, additional activities included

Program Managers attended meetings to review and understand CPUC reporting requirements for 2004.

    - Marketing

Marketing outreach continued via direct contact with builders, architects and energy analysts.

    - Direct Implementation

During October the following classes were offered to train and inform the market actors in energy efficient methods and technology.

- Advanced ACCA Manual J: Residential Load Calculation and Equipment Selection
The course reviews more advanced aspects of ACCA Manual J. Topics include calculating loads for two story homes and skylights, analysis of vaulted or cathedral ceilings, and continued training in the Wrightsoft software.
October 5, 2004, Four Points Hotel Sheraton, Fullerton, 8 attendess representing 6 firms.

- Introduction to ACCA Manual D: Residential Duct Design
This class focuses on designing residential duct systems according to ACCA Manual D specifications using the ACCA Manual D and duct calculator. The course covers determining the system static pressure and available static pressure, calculating the total equivalent length of duct runs and friction rate and the sizing of ducts. The course also demonstrates the Wrightsoft Manual D software program
October 6, 2004, Four Pointes Hotel Sheraton, Fullerton, 7 attendees representing 5 firms.

- Advanced ACCA Manual D
This course covers more advanced topics of duct design including utilizing the Wrightsoft ACCA computer software to perform calculations. Students utilize the computer lab to learn the software and perform group and individual exercises. The Introduction course is required for attendance.
October 14, 2004, National University Computer Center, San Bernardino, 5 attendees representing 3 firms.

- 2005 Energy Standards Update: High Performance Ducts
This course is oriented toward builders, HVAC contractors and engineers and reviews current and proposed changes to the Residential Energy Efficiency Standards. Class topics include: high performance glazing and radiant barrier roof sheathing, duct testing and the Home Energy Rating System (HERS) verification process. Hydronic systems are reviewed including sizing and installation, water heater sizing, cooling and heating coil sizing and air flow designs for heating and cooling.
October 15, 2004, Southern California Gas Company, Redlands, 3 attendees representing 2 firms.
October 20, 2004, Southern California Gas Company, Chatsworth, 54 attendees representing 27 firms.

- Combined Hydronic Systems
The focus of this course is on sizing combined hydronic systems. Topics that are covered include using the Gas Research Institute (GRI) guidelines for sizing and installing combination systems, water heating sizing for both domestic hot water and space heating, cooling and heating coil sizing guidelines and airflow recommendations for heating and cooling. A copy of the GRI report and guidelines is including in the training materials
October 20, 2004, Southern California Gas Company, Chatsworth, 3 attendees representing 3 firms.

- EnergyPro® Residential Building Energy Analysis
This course covers utilizing EnergyPro® to prepare Residential Title 24, Energy Code documentation. Topics include basic program operation and inputs, the Residential Wizard and changes to Title 24 Energy Code.
October 14, 2004, Energy Resource Center, Downey, 14 attendees representing 12 firms.

- MicroPas Residential Energy Compliance
This seminar is designed to provide detailed training on use of the California Energy Commission approved MicroPas program for use with the residential energy standards. Emphasis will be placed on energy code requirements and obtaining accurate compliance results as well as plan checking compliance.
October 20, 2004, Energy Resource Center, Downey, 7 attendees representing 6 firms.

- Static Pressure and Air Flow Testing
Participants in this class use a horizontal HVAC system to measure air flow, static pressure and amperage under various system configurations. System variables include filters, coils, variable size return ducts and leakage.
October 19, 2004, Southern California Gas Company, Chatsworth, 4 attendees representing 4 firms.

- High-Efficiency HVAC Troubleshooting
This course reviews basic terminology of HVAC systems and discusses the theory of heating efficiency and combustion, cooling efficiency, electrical and air movement. The sessions examines the importance of proper installation of HVAC equipment and minor troubleshooting techniques.
October 12, Energy Resource Center, Downey, 7 attendees representing 7 firms
October 13, 2004, Southern California Gas Company, Redlands, 8 attendees representing 7 firms.

- High-Performance Windows
This course reviews the lastest developments in high-performance window technology; including installation practices, standards and glazing technology.
October 1, 2004, Energy Resource Center, Downey, 5 attendees representing 5 firms.

      - Audits and Site Surveys

Not applicable.

      - Direct Installations, Rebates, Equipment Maintenance and Optimization

Not applicable.

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in  customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SDG&E  pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None.

- Customer Disputes 
None.

- Compliance Items 
None.

- Coordination Activities
Coordination activities are described in the PIP.

- Changes to Subcontractors or Staffing 
None.

- Additional Items

Workbook Tab 7 Updates

Tab 7 of the workbook has been updated to reflect subcontractor costs invoiced and paid during April and May 2004.

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
No new materials were distributed at training sessions in October.

- Trade Shows and Public Events – 
None this month.