| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Multifamily Energy Efficiency Rebates |
| IOU Service Area: | SCG |
| Program Number: | 1246-04 |
| Program Type: | IOU Statewide Program |
| Month | November-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $4,594,768 | $226,837 | 5% | $1,422,944 | 31% |  |  | $1,422,944 | 31% | $3,171,824 |
| Admin | $522,750 | $16,817 | 3% | $160,669 | 31% |  |  | $160,669 | 31% | $362,081 |
| Marketing | $455,360 |  |  | $49,242 | 11% |  |  | $49,242 | 11% | $406,118 |
| DI | $3,545,580 | $210,020 | 6% | $1,213,033 | 34% |  |  | $1,213,033 | 34% | $2,332,547 |
| EM&V | $71,078 |  |  |  |  |  |  |  |  | $71,078 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

| Energy Effects | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Coinc Peak kW | 791 |  |  | 85 | 11% |  |  | 85 | 11% | 706 |
| Annual kWh | 13,134,937 | 2,258,163 | 17% | 5,424,342 | 41% |  |  | 5,424,342 | 41% | 7,710,596 |
| Lifecyc kWh | 162,017,837 |  |  | 65,564,912 | 40% |  |  | 65,564,912 | 40% | 96,452,925 |
| Annual Therms | 1,881,059 |  |  | 674,888 | 36% |  |  | 674,888 | 36% | 1,206,171 |
| Lifecyc Therms | 21,274,006 |  |  | 7,887,486 | 37% |  |  | 7,887,486 | 37% | 13,386,519 |

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Nov-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Hard to Reach goal is that 29% of rebate applications come from HTR zip codes | 29% | 30% | 103% |  |  |  |  | 30% | 103% | 0 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

    - Regular monthly administrative activities include but are not limited to the following activities:  two calls with CA statewide Multifamily team to revise the customer application for 2005.  Internally developed talking points addressing year-end transition to address customer submitted applications.  Conducting year-end program budgets and expenditure review and reconciliation.

    - Marketing

    - Revised website to inform customers of recent changes regarding available rebates and funding.

    - Develop talking points for addressing questions from customers as to eligibility of 2004 installs linked to applications submitted in 2005.

    - Met with MF Advertisers regarding ad space in 2005.

    - Direct Implementation

      - For Audits and Site Surveys  - Not Applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization

- Total number of customers sites served, 370

- Summary of type and number of measures installed or repaired.

| Measure Type | Measure Qty |
| --- | --- |
| Appliances | 11 |
| Building Shell - Insulation | 10,255 |
| HVAC - Controls | 5,444 |
| Other | 48 |
| Water Heating - Systems | 57 |
| Water Heating - Controls | 5 |
| Grand Total | 15,820 |

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SoCalGas pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower;

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan for this program on December 13, 2004 per  Decision 04-12-019, issued on December 2, 2004.

- Coordination Activities 
In September statewide IOUs (SDG&E, PG&E, SCE, and SCG) continued regular communication to discuss program progress and share marketing approaches, promotional plans, and market participation.  The Utilities also continue to provide review, recommendation and approval of reservation procedures.  Other coordination Activities are detailed in the revised PIP

- Changes to Subcontractors or Staffing - 
None

- Additional Items - None

Supporting Documentation

- Marketing Materials – 
Full page ad placed with four Apartment publications

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation- 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
There were no training activities this month

- Trade Shows and Public Event