| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Residential Home Energy Efficiency Survey |
| IOU Service Area: | SCG |
| Program Number: | 1247-04 |
| Program Type: | IOU Statewide Program |
| Month | November-04 |

- Program Status

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Nov-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $628,000 | $19,824 | 3% | $175,592 | 28% |  |  | $175,592 | 28% | $452,408 |
| Admin | $158,752 | $4,259 | 3% | $51,976 | 33% |  |  | $51,976 | 33% | $106,776 |
| Marketing |  | $18,157 | NA | $22,711 | NA |  | NA | $22,711 | NA | -$22,711 |
| DI | $389,248 | -$2,592 | -1% | $100,905 | 26% |  |  | $100,905 | 26% | $288,343 |
| EM&V | $80,000 |  |  |  |  |  |  |  |  | $80,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable for this program.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative
Regular monthly administrative activities include but are not limited to the following activities:  continued re-fining of the customer participation process and program design, review of customer participation and market activity, coordination with other programs, survey vendor and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures

Continue to work with statewide vendor and translators to prepare in-languages survey for mailing.

    - Marketing –

- On line audit invitation is displayed on the SoCalGas Home Page.

- The English mail in survey was mailed to 14,757 targeted residential customers

    - Direct Implementation

      - For Audits and Site Surveys:

  - 23on line surveys were completed in November.

  - 89 SCG In-home audits  were completed in November.

  - 1,085 mail in surveys were completed in November.

- Aggregated number of audits/surveys completed, type of audit, and cost per audit.  (specify components of audit cost, such as auditor’s time, travel costs, cost to develop audit reports, etc.)

- Summary of type and number of energy efficiency measures recommended

- Estimated total demand and energy savings potential if recommended measures were to be implemented by customer – Not Applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  - Not Applicable

      - If total month’s rebates paid or direct install costs differ from total calculated in report workbook, provide discussion of difference – Not Applicable

    - EM&V

- Program Challenges 
 None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed an updated Program Implementation Plan for this program on April 12,  2004.

- Coordination Activities
Coordination Activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing -
None 
Additional Items 
None

Supporting Documentation

- Marketing Materials – 
None this month

- Point of Purchase Program Documentation – 
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
This program typically does not conduct training sessions.

- Trade Shows and Public Events – 
None this month