| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential Energy Audit |
| IOU Service Area: | SCG |
| Program Number: | 1465-04 |
| Program Type: | IOU Statewide Program |
| Month | December-04 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Dec-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $2,018,136 | $134,550 | 7% | $655,410 | 32% |  |  | $655,410 | 32% | $1,362,726 |
| Admin | $380,862 | -$222,442 | -58% | $113,505 | 30% |  |  | $113,505 | 30% | $267,357 |
| Marketing | $162,000 | -$27,436 | -17% | $61,570 | 38% |  |  | $61,570 | 38% | $100,430 |
| DI | $1,322,274 | $384,428 | 29% | $480,335 | 36% |  |  | $480,335 | 36% | $841,939 |
| EM&V | $153,000 |  |  |  |  |  |  |  |  | $153,000 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Dec-04 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| HTR Goal | 640 | 34 | 5% | 629 | 98% | 0 | 0% | 629 | 98% | 11 |
| Online Goal | 1,100 | 33 | 3% | 335 | 30% | 0 | 0% | 335 | 30% | 765 |
| Mail In | 1,700 | 1825 | 107% | 2364 | 139% | 0 | 0% | 2364 | 139% | -664 |
| Phone | 2,200 | 9 | 1% | 1034 | 47% | 0 | 0% | 1034 | 47% | 1166 |
| CD Rom | 600 | 0 | 0% | 307 | 51% | 0 | 0% | 307 | 51% | 593 |
| On site audit | 800 | 62 | 8% | 1682 | 210% | 0 | 0% | 1682 | 210% | -882 |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include continued refining of the customer participation and process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

    - Marketing

- The Winter Gas Letter, which featured a mail audit form, and was mailed in November continues to garner results.  While the expected return rate is 1% to 2%, through December, the rate is approaching 6%.

- A Bill Insert went out in December to all C&I customers.  The insert indicated the higher cost of gas this winter and presented the Energy Savings Finder as a method of attempting to reduce usage.  The insert was designed in conjunction with the CARE program for non-profit C&I customers.

    - Direct Implementation

      - For Audits and Site Surveys  - see 1.1.3

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -  not applicable.

      - If total month’s rebates paid or direct install costs differ from total calculated in report workbook, provide discussion of difference. – not applicable.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

Per CPUC Decision 04-12-019, So Cal Gas filed a modified Program Implementation Plan (PIP) for this program on December 13, 2004.

- Coordination Activities
Coordination activities are detailed in the PIP.

- Changes to Subcontractors or Staffing

Additional contract workers were added to help process the mail-in audits.

- Additional Items 
None

Supporting Documentation

- Marketing Materials –

Natural Gas Price Update: A Message to Our Business Customers bill insert – Message about gas prices and promoted energy efficiency programs including the audit program.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation –

None this month.

- Trade Shows and Public Events –

None this month.