| Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Name: | Statewide Nonresidential Building Operator Certification |
| IOU Service Area: | SCG |
| Program Number: | 1253-04 |
| Program Type: | IOU Statewide Program |
| Month | Jan - 05 |

- Program Status

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget  in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $392,550 | $11,565 | 3% | $88,369 | 23% |  |  | $88,369 | 23% | $304,181 |
| Admin | $200,050 | $5,579 | 3% | $64,972 | 32% |  |  | $64,972 | 32% | $135,078 |
| Marketing |  |  | NA |  | NA |  | NA |  | NA |  |
| DI | $131,000 | $5,986 | 5% | $23,397 | 18% |  |  | $23,397 | 18% | $107,603 |
| EM&V | $61,500 |  |  |  |  |  |  |  |  | $61,500 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Jan 05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Level 1 ‘04 | 1 course | 0 | 0 | 1 | 100% | 0 | 0 | 1 | 100% | 0 |
| Level 1 ‘04 | 20 students | +5 * | +25% | 27 | 135% | 0 | 0 | 27 | 135% | +7 |
| Level II ’05 * | 1 course | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Level II ’05 * | 12 students | 2 | 17% | 2 | 17% | 0 | 0 | 2 | 17% | -10 |

*These are the number of students registered.

Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Regular monthly administrative activities include but are not limited to the following activities: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

SoCalGas is offering BOC Level II classes for the first time instead of BOC Level I as originally planned. This change was recommended by National Energy Efficiency Council (NEEC) due to the need for Level II classes to accommodate students who completed Level I. Sufficient Level I classes in the vicinity of the ERC were being offered by SCE. No classes were held in January 2005.

    - Marketing

Information on BOC Level II Course scheduled to start on May 25, 2005, was mailed to previous BOC Level I students, and NEEC posted the class on their website. Informational meetings were held at CTAC in Irwindale and the Doubletree Hotel in Bakersfield.

    - Direct Implementation

      - For Audits and Site Surveys  - Not applicable

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  - Not applicable

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons:

(1) There may be a lag in customer rebate payments, particularly those approved for payments towards the end of the month, due to the processing of check payments;

(2) SDG&E pays an approved customer application either the prescribed rebates/incentives or the cost shown on the customer invoice, whichever is lower.

    - EM&V

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items 
SoCalGas filed updated Program Implementation Plans (PIP) for this program on February 2, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials – 
There were no new marketing materials this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation – 
This program does not distribute free measures.

- Upstream Incentive Documentation – 
This program is not an upstream incentive program.

- Training Documentation – 
There were no training activities this month.

- Trade Shows and Public Events – 
This program does not have trade shows or public events.