| Implementer Name: | Southern California Gas Co |
| --- | --- |
| Program Name: | Bakersfield/Kern Energy Watch 1350-04 |
| IOU Service Area: | SCG |
| Program Number: | 1230-04 |
| Program Type: | IOU Partnership Program |
| Month | October-04 |

- Program Status

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Oct-04 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $500,000 | $107 | 0% | $775 | 0% |  |  | $775 | 0% | $499,225 |
| Admin | $60,100 | $107 | 0% | $775 | 1% |  |  | $775 | 1% | $59,325 |
| Marketing | $439,900 |  |  |  |  |  |  |  |  | $439,900 |
| DI |  |  | NA |  | NA |  | NA |  | NA |  |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

Administrative activities related to standard program implementation included the monthly partnership coordination meeting of all partners in Bakersfield on October 28, 2004; telephone calls, e-mails and meetings between PG&E and Staples/Hutchinson (now Staples Marketing) and between PG&E and potential residential services vendors; telephone calls and e-mails at each utility to plan activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern, PG&E, and SCE to refine plans for municipal building retrofits; and between utilities to coordinate marketing activities.

    - Marketing

The Bakersfield & Kern County Energy Watch radio schedule, which began airing September 20 in the Bakersfield media market, continued through October. During October, the radio schedule generated 57 requests for residential surveys, approximately one-third of all requests. The other 131 requests resulted from direct marketing, realtor referrals, schools, and special events.

Staples Marketing employees from the Bakersfield office staffed Bakersfield & Kern County Energy Watch displays and distributed program literature at several venues in October:  Kern County Fair – October 1-3, Career Services Center presentation in Bakersfield -- October 14, Dust Bowl Festival in Lamont – October 16, and Bakersfield Fall Home Show on October 23 and 24.

    - Direct Implementation

Staff from the Energy Watch office in Bakersfield continues to make presentations to partner Realtor® firms.  Coupons offering free energy surveys are sent out to homebuyers and requests for homebuyer home energy surveys are scheduled by the Energy Watch office.

The Energy Watch Bakersfield office distributed approximately 5,000 residential energy survey coupons during October via onsite visits and mailings as part of the Realtor program.  In addition, 80 coupons were mailed to customers of Energy Watch partner S Realtors.  This work was done by a subcontractor and will not appear in the workbook until PG&E has paid the invoice for this work.

      - For Audits and Site Surveys  - Not applicable for SCG

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -  Not applicable for SCG.

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons: - Not applicable for SCG

    - EM&V -

EcoNorthwest, the consultant conducting the evaluations of seven of PG&E’s partnership programs received Energy Division approval to proceed with implementation of its evaluation plan on October 29, 2004.

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

PG&E, SCE and SoCal Gas filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP. In addition, all Energy Watch partners have provided Staples Marketing with supplies of informational materials regarding other energy efficiency programs to be handed out at special events scheduled to promote Energy Watch and statewide energy efficiency programs.

- Changes to Subcontractors or Staffing

As noted previously, Community Action Partnership of Kern decided that Bakersfield & Kern County Energy Watch survey activities did not fit with the organization’s mission and withdrew from the program.  Jess Bravo was hired as subcontractor to perform both residential (for the Realtor program) and non-residential surveys.

- Additional Items

None

Supporting Documentation

- Marketing Materials –

None this month.

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation –

Staples Marketing distributed 225 CFLs and installed 22 programmable thermostats.

- Upstream Incentive Documentation – 
This program does not have upstream incentive documentation.

- Training Documentation –

During the month of October there was one educational event scheduled for the Bakersfield/Kern Energy Watch Program on Grocery, Restaurant & Related Energy Efficiency.  In addition, there was a seminar held at AgTAC in Tulare which was promoted through the Energy Watch Program.  The following are highlights from those two events:

Grocery, Restaurant & Related Energy Efficiency  – The course showed business owners and operators how to reduce energy costs in their operations through a better understanding of lighting, refrigeration and HVAC operation,  The instructor emphasized practical, non-technical examples of no-cost, low-cost and key investment opportunities.  This session was held at Hodel’s Restaurant in Bakersfield on October 14, 2004 and was attended by 17 representatives of various businesses in the Bakersfield area.

Lighting the Electronic Office  – This workshop focused on the most effective methods of illuminating today’s electronically laden office workspace.  There was discussion of how to light offices to insure that all tasks are accomplished as effectively as possible.  Although the class was held at the Edison AgTAC Facility in Tulare, three of those attending were from businesses in Kern.

- Trade Shows and Public Events –

October 3:		Kern County Fair Booth

October 14:		Career Services Center presentation

October 23-24:		Bakersfield Fall Home Show

Weekly appearances at Wal-Mart and Lowe’s