| Implementer Name: | Southern California Gas Co |
| --- | --- |
| Program Name: | Bakersfield/Kern Energy Watch 1350-04 |
| IOU Service Area: | SCG |
| Program Number: | 1230-04 |
| Program Type: | IOU Partnership Program |
| Month | February-05 |

- Program Status

Pacific Gas and Electric Company (PG&E), Southern California Edison (SCE), Southern California Gas Company (SoCalGas), the City of Bakersfield (City), the County of Kern (County), and Staples/Hutchinson and Associates, Inc. (Staples/Hutchinson) entered into a partnership to reduce energy use by providing energy efficiency information and direct installation of energy efficient equipment to the City and County’s local community.

Specifically, this partnership will offer direct install services to hard-to-reach customers, home buyers, and small businesses; free energy audits to both residential and nonresidential hard-to-reach customers; marketing and outreach to encourage participation in statewide energy efficiency programs; municipal building energy efficiency retrofits; support for codes and standards enforcement; and local training seminars for residential contractors as well as design/build firms and engineers and architects working on commercial properties.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Feb-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $500,000 | $16 | 0% | $1,185 | 0% |  |  | $1,185 | 0% | $498,815 |
| Admin | $60,100 | $16 | 0% | $1,185 | 2% |  |  | $1,185 | 2% | $58,915 |
| Marketing | $439,900 |  |  |  |  |  |  |  |  | $439,900 |
| DI |  |  | NA |  | NA |  | NA |  | NA |  |
| EM&V |  |  | NA |  | NA |  | NA |  | NA |  |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note:  There may be line items in the expenditures on Tab 1A that have no corresponding budget amount (i.e. – Budget is zero).  These expenditures were not anticipated when the original budget was developed but must be reported as actual expenditures.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative

- Administrative activities related to standard program implementation included the monthly partnership coordination meeting of all partners in Bakersfield on February 17, 2005  in Bakersfield; telephone calls, e-mails and meetings between PG&E and Staples Marketing and between PG&E and potential residential services vendors; telephone calls and e-mails at each utility to plan 2005 activities; meetings, telephone calls and e-mails between the City of Bakersfield, County of Kern and PG&E and between the County of Kern and SCE to discuss progress in municipal building retrofits; and between utilities to coordinate marketing activities.

- On February 2, Staples Marketing provided Ray Kincy, manager of the Arvin Community Service District, with a draft letter for use with district customers. The letter invited customers to take advantage of the Energy Watch program, with the added incentive of a low-flow showerhead.  Plans to target market the Energy Watch program in the water utility districts of Arvin and Lamont are currently not feasible, because both districts are having problems with fluoridation. Alternatives for targeting other special markets are being discussed.

    - Marketing

- The Bakersfield & Kern County Energy Watch advertising schedule for February was concentrated in radio as follows:

| Dates Station | Feb.14-16 | Feb.21-23 | Feb.28-Mar.2 |
| --- | --- | --- | --- |
| KUZZ-FM | +++ | +++ | +++ |
| KKBB-FM | +++ | +++ | +++ |
| KERN-AM | +++ | +++ | +++ |
| KDFO-FM | +++ | +++ | +++ |
| Spanish Radio Group |  |  |  |
| LOBO-FM | +++ | +++ | +++ |
| KCHJ-AM | +++ | +++ | +++ |

Average number of commercials per day is 3.

- Bakersfield & Kern County Energy Watch staffed a booth at the Bakersfield Home & Garden Show, February 18-20 and participated in the KUZZ-FM promotion for the event.  The station was provided with 30-second copy to incorporate in some of its 60-second show promos.

- An approved article was provided for the Bakersfield Home & Garden Show guide and insert in the Bakersfield California.

- Throughout the month of February, Energy Watch office personnel staffed booths and distributed information at the following partner locations: Ranch Market, Kern Regional Center, Stock Lumber, Lowe’s on Rosedale, and Walmart.

Marketing/outreach efforts generated phone requests to the Energy Watch office for Home Energy Surveys:

| Source of Referral | Number of Calls February |
| --- | --- |
| Ranch Market | 56 |
| TV Commercial Schedule (earlier) | 37 |
| Lowe’s on Rosedale Highway | 114 |
| Stock Lumber | 64 |
| Radio Commercial Schedule | 54 |
| Walmart | 37 |
| Realtors | 8 |
| Kern Rergional Center | 33 |
| Employment Training Resource | 23 |
| Home & Garden Show | 261 |
|  | TOTAL 687 |

Staples Marketing provided the program administrator at PG&E with the draft copy for a new Energy Watch radio commercial. Requested edits have been made and the English-language script is being translated into Spanish.

    - Direct Implementation

While there were no courses specifically offered during February, the partnership was active in promoting the following Industrial Seminar:

- Technology Update, Feb 23, 2005 – This course presented attendees with a look at the latest technological improvements to end uses such as: HVAC, lighting, refrigeration, energy management systems and motors.  These improvements are designed to provide customers with the most energy efficient product to help control their energy use and cost.  The session was attended by 26 local business people and the course was received very well.  The seminar was held at Hodel’s Restaurant in Bakersfield and was a part of PG&E’s Industrial Seminar series.

- Again in March, no specific sessions are being offered as part of the Energy Watch Program, but we will again partner to support the marketing of a “Prime Movers” Industrial Seminar on March 16, 2005.

- Staff members from the Energy Watch office in Bakersfield continue to make presentations to partner Realtor® firms. Coupons offering free energy surveys are sent out to homebuyers and requests for homebuyer home energy surveys are scheduled by the Energy Watch office. In addition, staff is partnering with non-for-profit and profit businesses and organizations to distribute Energy Watch information to their employees.

      - For Audits and Site Surveys  - Not applicable for SCG

      - For Direct Installations, Rebates, Equipment Maintenance and Optimization  -  Not applicable for SCG.

      - Discrepancies between total month's rebates paid may differ from the total calculated in the workbook due to the following reasons: - Not applicable for SCG

    - EM&V -

EcoNorthwest, the consultant conducting the evaluations of seven of PG&E’s partnership programs received Energy Division approval to proceed with implementation of its evaluation plan on October 29, 2004. Survey design is proceeding and the revised EM&V project schedule has been reflected in tab 6 of PG&E’s workbook.

- Program Challenges 
None

- Customer Disputes 
None

- Compliance Items

PG&E, SCE and SoCal Gas filed revised Program Implementation Plans (PIP) and workbooks for this program on June 15, 2004.

- Coordination Activities

Coordination activities are detailed in the revised PIP. In addition, all Energy Watch partners have provided Staples Marketing with supplies of informational materials regarding other energy efficiency programs to be handed out at special events scheduled to promote Energy Watch and statewide energy efficiency programs.

- Changes to Subcontractors or Staffing

None

- Additional Items

None

Supporting Documentation

- Marketing Materials –

HVAC and Energy Auditing Class Announcements

- Point of Purchase Program Documentation –
This program does not have point of purchase activities.

- Free Measure Distribution Documentation –

This program does not have free measure distribution.

- Upstream Incentive Documentation – 
This program does not have upstream incentive documentation.

- Training Documentation –

None for SCG

- Trade Shows and Public Events –

| Brief description of the event | Location of the event | Date of event |
| --- | --- | --- |
| Display and Customer Outreach | Ranch Market in Bakersfield | February 2005 |
| Display and Customer Outreach | Kern Regional Center | February 2005 |
| Display and Customer Outreach | Stock Lumber, Bakersfield | February 2005 |
| Display and Customer Outreach | Lowe’s, Rosedale | February 2005 |