| Program Implementer Name: | Southern California Gas Company |
| --- | --- |
| Program Title: | South Bay Cities Energy Efficiency Resource Center – PGC |
| Program Number: | 1404-04 |
| Month: | January 2005 |

- Program Status

The South Bay Energy Efficiency Resource Center (SBEERC) is a partnership with the South Bay Cities Council of Governments (SBCCOG), Southern California Edison (SCE) and Southern California Gas Co. (SCG).  The South Bay Energy Efficiency Resource Center will expand on current regional energy efficiency activities through the development of a community-based resource for energy information, training and materials to assist the member agencies, businesses and citizens to best utilize the resources available to them through the wide variety of statewide and local energy efficiency programs.  To accomplish this, this partnership will form an Energy Efficiency Resource Center, which will serve the region’s constituents as the central clearinghouse for energy efficiency information and resources.  The SBEERC will establish a small, yet capable Resource Center that will significantly increase the availability of information and resources to the citizens of South Bay region.

  - Insert a table that shows the following:

    - Comparison of budget, current month’s expenditures, cumulative expenditures, commitments, and remaining budget in the four categories (admin, marketing, direct implementation, EM&V)

| Budget and Expenditures | Budget | Jan-05 | % of Bdgt | Cumulative | % of Bdgt | Committed | % of Bdgt | Cumulative & Committed | % of Bdgt | Unspent |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Total | $793,490 | -$3,639 | 0% | $40,683 | 5% | $14,828 | 2% | $55,512 | 7% | $752,807 |
| Admin | $132,026 | -$3,639 | -3% | $12,786 | 10% | $14,828 | 11% | $27,615 | 21% | $119,240 |
| Marketing | $23,000 |  |  | $2,023 | 9% |  |  | $2,023 | 9% | $20,977 |
| DI | $604,675 |  |  | $25,874 | 4% |  |  | $25,874 | 4% | $578,801 |
| EM&V | $33,789 |  |  |  |  |  |  |  |  | $33,789 |
| Financing |  |  | NA |  | NA |  | NA |  | NA |  |

Note – negative values, if any, reflect accounting adjustments made to correct errors/oversights made during previous reporting periods.

Due to a lag in the time between when the partnership expends funds and when SCG is invoiced for its share of those expenditures, the reported monthly expenditures of the partnership may differ from the expenditures recorded in SCG’s accounting system.

    - If applicable, comparison of energy savings goals, current month’s achievements, cumulative achievements, commitments and remainder.

Not applicable to this program.

    - If applicable, comparison of performance goals, current month’s achievements, cumulative achievements, commitments and remainder.

| Performance Goals | Goals | Jan-05 | % of Goals | Cumulative | % of Goals | Committed | % of Goals | Cumulative & Committed | % of Goals | Goals Minus Cumulative |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Conduct at least 4 training sessions for the public sector | 4 | 0 | 25% | 4 | 100% | 0 | % | 4 | 75% | 0 |
| Conduct at least 12 sessions for businesses | 12 | 2 | 0% | 4 | 34% | 0 | 0% | 4 | 34% | 8 |
| Conduct at least 4 events for residential customers. | 4 | 1 | 25% | 4 | 100% | 0 | 0% | 4 | 100% | 0 |
| Promote SBEERC resources and energy efficiency information at 12 community events or more. | 12 | 0 | 0% | 17 | 142% | 0 | 0% | 17 | 142% | 0 |
| Respond to every customer inquiry within 48 hours. |  | 4 | n/a | 19 | n/a | 0 | n/a | 19 | n/a |  |
| Achieve an 80 percent overall customer satisfaction level of Excellent (based on follow-up surveys) of (Evaluation Levels: Poor, Below Average, Average, Good, and Excellent). |  | Excellent | met | Excellent | met | Excellent | met | Excellent | met |  |

  - Describe program activities and accomplishments during the month for each of the following types of activities:

    - Administrative -

- SBESC continues to work with SBCCOG Board and Steering Committee as well as Utility Partners to keep the program on track.

    - Marketing -

SBESC:

- Updated the SBESC website with current information

- Marketed scheduled workshops through:

- Advertisement in The Daily Breeze Business Monday reaching 222,008 households.

- Advertisement in The Daily Breeze Out and About Section on another date reaching 222,008 households.

- Advertisement in Palos Verdes News reached 67,000 households.

- Flyer in Rancho Palos Verdes business license renewal letter.

- Flyer in the Palos Verdes Peninsula Chamber of Commerce Newsletter

- An e-mail blast to SBESC list of over 500 names gathered at community events.

- Distribution of flyers at two shopping centers in Palos Verdes.

#### Outreach Activities

SBESC continues to work with member cities, public officials and community organizations to secure assistance in disseminating energy efficiency information and co-sponsoring training events.  SBESC continues to handle walk-ins and telephone calls from the community and signing out resources from the lending library.  All calls to the center were responded to in less than twenty-four hours.

- Marilyn Lyon, SBESC Program Manager,  SCE’s Gene Rodrigues and Mayor Jim Dear of Carson Participated in the video taping of a cable show with Supervisor Yvonne Burke.  The show will run for four weeks in January and February in Inglewood, Carson, Hawthorne, and Gardena.

- SBESC participated in planning the South Bay Cities Council of Governments (SBCCOG) General Assembly event scheduled for February 24, 2005.

- Other outreach events include:

- Hawthorne Workforce Investment Board on January 20 (40 people)

- Torrance Workforce Investment Board on January 27 (40 people)

- Kiwanis Club Meeting on January 28 (30 people)

- Torrance Chamber of Commerce Lunch Networking on January 31 (32 people).

    - Direct Implementation

- A business energy efficiency workshop was held on January 18, 2005 at Rolling Hills Estates.  This workshop was co-sponsored by the Palos Verdes Peninsula Chamber of Commerce and was attended by seven people.  Attendees rated the workshop excellent.

- A Title 24 workshop for developers and architects was held at the Savings Center in Torrance on January 31, 2005.  Thirteen people attended the event and gave an overall rating of excellent.

- An energy efficiency training for residents was held on January 31, 2005 at Park Villa Mobile Home Estates in Carson.  This event was held in collaboration with American Synergy Corporation, (ASC) implementer of the Hard-to-Reach Mobile Home Program.  ASC staff was on hand to make appointments for services at the end of the workshop.  Attendees rated the workshop as excellent.

- Follow-up to attendees included mailing of thank you letters and certificates or participation

- The Energy Efficiency Action Plan is currently being rescoped.

      - Audits, Site Surveys and Partnerships - None

      - Direct Installations, Rebates, Equipment Maintenance and Optimization – Not applicable

      - Calculated and Actual Payment Reconciliation - None

    - EM&V

- Key contacts at member agencies were provided to the SBESC consultants.

- Program Challenges
None

- Customer Disputes
None

- Compliance Items
None

- Coordination Activities

- SBESC identified, through the mobile home outreach program, mobile homes that had no heat.  The matter was referred to SCG for action.

- The local SCE Hard-to-reach Small Business Direct Install Program has been identified for participation by South Bay small businesses.  The Multi-family torchiere exchange has also been identified for the South Bay.

- SBESC is also exploring opportunities to cooperate with ASW Engineering’s HTR business energy efficiency program.

- SBESC coordinated with Mayor Jim Dear of Carson regarding residential training for mobile home Parks in Carson.  These mobile homes benefit from SBESC residential energy efficiency training coupled with American Synergy Corporation’s Hard to Reach Mobile Home Program.

- Changes to Subcontractors or Staffing
None

- Additional Items
None

Supporting Documentation

- Marketing Materials

- Point of Purchase Program Documentation
None

- Free Measure Distribution Documentation
None

- Upstream Incentive Documentation
None

- Training Documentation

| Table E – Training Documentation |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Brief Description of Training | Delivery Method | Materials List | Attendees |  | Training |  |
|  |  |  | Type | Number | Date | Location |
| Business EE Training | Workshop | PP Presentation | Business | 7 | 1/18/05 | Rolling Hills |
| Title 24 | Workshop | Workbook, demos | Business | 13 | 1/31/05 | Torrance |
| Residential EE training | Workshop | EE information | Residents | 21 | 1/31/05 | Carson |
| Public Agency EE training | Workshop | EE Information, Slide presentation | Government | 11 | 12/14/04 | Torrance |

- Trade Show and Public Events

| ###### Table F.2 - Trade Show and Public Events, Planned |  |  |
| --- | --- | --- |
| Event Description | Event |  |
|  | Location | Date |
| 8 Residential EE workshops in collaboration with American Synergy at Mobile Home Parks | Carson | February 2 - 28 |
| SBCCOG General Assembly | PV Peninsula | February 24 |