| Program Name: | Multi Family Energy Efficiency Retrofit Program |
| --- | --- |
| Program Number: | SCG3510 |
| Quarter: | Third Quarter 2006 |

- Program description:

The Multi Family Energy Efficiency Retrofit (MFEER) Program is a statewide program that targets property owners and managers of multifamily residential dwellings, homeowner’s associations and mobile home park associations.  The program encourages property owners and managers to install qualifying energy efficiency products in common areas for residential apartments, mobile home parks and condominium complexes.  The program is designed for flexibility; it offers agreed upon statewide measures for coordinated implementation, but is designed to easily adapt to market changes, including adding new measures that may emerge as cost effective opportunities in the SoCalGas local service area.

- Administrative activities:

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.  In addition:

- Continued ongoing communication with Processing and Inspection group to ensure correct application of 2006 program procedures.

- Continued ongoing participation, and review of Scope of Work (SOW), Inter Utility Agreement (IUA), and marketing materials for joint 3rd Party Program with SCE, for Coin Op Laundry program.

- Continued participation in weekly Statewide IOU Multifamily Rebate Team conference calls.

- 7/19/06:  Met with On Bill Financing Program Manager for details of program and developed strategy for pending implementation.

- 8/16/06:  Attended SCG’s Customer Services Field Operations Peer Team Meeting to present information on the Residential Customer Programs, with an emphasis on Multifamily Rebate Program.

- 8/10/06:  Attended Customer Values and Mass Markets Strategic Plan meeting.

- 8/21/06:  Attended planning meeting for Energy Efficiency Tracking System (EETs) replacement, with the Customer Relationship Management (CRM) system.

- 9/13/06:  Updated English and Spanish version of the 2006 Multifamily Rebate Application as follows:
1.  Removed Coin-op Laundry measure from program offering, as 3rd Party Contractor was awarded administration of the Commercial Laundry Program.
2.  Added On Bill Financing verbiage to Terms and Conditions

- Printed revised 2006 Multifamily Rebate applications as necessary.

- Marketing activities:

- Applications may be downloaded via the web site or requested via SCG Residential Marketing Department, or Program Manager.

- 7/18/06:  Participated in the joint Utilities Panel Presentation with SCE and Inland Empire Water Districts at the Apartment Association of the Greater Inland Empire’s monthly meeting.

- 9/14/06:  Updated SoCalGas’ Multifamily Rebate webpage with revised applications in English and Spanish languages.

- 9/20/06:  Participated in the HUD Action Plan, “Energy Efficiency and Renewable Programs; Making a Difference”.  Coordinated joint presentation with SCE regarding the statewide Multifamily Rebate Programs.

- 9/21/06:  Participated in the Apartment Owners Association of California Million Dollar Tradeshow, Long Beach, CA. 
-Distributed multifamily applications and tri-fold program description brochures during the tradeshow.

- 9/26/06:  Participated in the Apartment Association of the Greater Inland Empire Annual Tradeshow, Ontario CA.
- Participated in joint Energy Efficiecy rebate program presentation with SCE
- Distributed multifamily applications and tri-fold program description brochures during tradeshow

- Collaborated with program manager for South Bay Energy Savings Center to design and implement joint Energy Efficiency Workshop with SCE, scheduled for 2/22/07.

- Direct implementation activities:

- Approximately 1000 applications and brochures were delivered to customers in SoCalGas service territory via tradeshow and outreach participation during third quarter.

- Ongoing random inspections of installed rebate measures as required per program specifications.

- 9/22/06:  Attended SCG’s Kickoff Meeting with Energy Efficiency Contractors; ‘Working Together for California’

- 9/27/06:  Attended ‘Powerful Presentations’ Training class

- 9/28/06:  Attended ‘SAP Accounting Basics’ Training class

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

552 requests for reservations have been received for 2006 Multifamily Rebate Program through September 30, 2006.  67% of the incentive goal has been reserved, committed or paid, and the program has achieved 66% of therm goal.  Currently, program is on target.

- Program achievements (non-resource programs only):

N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- Continued marketing strategy with emphasis on attending Apartment Association Tradeshows 1st , 2nd and 3rd quarters, and cultivating relationships in the industry.

- Continued to work with controller contractors to encourage installation of controls in older, pre 1970 multifamily buildings.

- Successfully networked with West Coast Regional Program Manager of HUD’s Energy Action Plan, and participated in outreach event to market SCG’s Multifamily Rebate Program to affordable housing retrofit projects.

- Coordinated the invitation for controller contractor to speak at the HUD Energy Action Workshop, and educate owners of affordable housing on the benefits of installing controllers on hot water delivery systems.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

Program Manager continued to provide internal training to SCG Customer Service Field Supervisors, in order to enhance employee knowledge of the Residential Energy Efficiency Programs.  

Program Manager attended Apartment Association meetings and Tradeshows, and developed critical key contacts.

Program Manager worked with Southern California Edison’s counterpart to conduct several joint Residential Energy Efficiency Presentations.

Utilize innovative approach to marketing strategy by participating in tradeshows outside traditional contacts (i.e. Apartment Associations):
--  IHACI Tradeshow
--  Builders Industry Tradeshow

- Changes to staffing and staff responsibilities, if any

Effective  September 2006, Marketing Advisor hired (MF responsible for    approximately 10% of salary)

- Changes to contracts,

None, Contact is Joy Yamagata

- Changes to contractors and contractor responsibilities, if any

N/A

- Number of customer complaints received

None

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.