| Program Name: | Natural Gas Cooling Replacement Program |
| --- | --- |
| Program Number: | SCG3538 |
| Quarter: | Third Quarter 2006 |

- Program description

Gas cooling units are installed in homes and small businesses throughout the SCG service territory.  These units are old and may fail soon, so customers are entering the market and may replace the units.  The market share for gas cooling has been on the decline over the years due to a variety of factors including rising gas rates, lower costs for the electric alternative product, high equipment prices for the gas units, limited product choice (few manufacturers) poor market strategy by the upstream players, and lack of quality assurance for the product and lack of qualified installers. This program will work to ensure the replacement of these old existing units and transition to new high efficiency gas AC equipment instead of alternative technologies.

- Administrative activities (describe)

Continued review of contract details and billing schedule. Created and changed invoice template to meet SCG guidelines. Refined input data categories for software based tracking systems.  Conducted multiple work sessions with software program team to create templates.  Defined basic program process flow chart and reviewed software scope with project team.  Attended SCG kick-off meeting for third party providers.  Met with SCG engineering regarding the development of savings and rebate levels.  SCG was comfortable with methodology and savings estimates.  Cypress is rerunning calculations using Engage program.  Met with SCG regarding adding on-bill-financing option to program for commercial projects.

- Marketing activities (describe)

Developed preliminary marketing plan and goals. Held meetings with contractor and manufacturers to position the program.

Conducted market planning both internal as Cypress team and external with market participants as follows:

# Manufacturers:

1) Identified manufacturers with potential qualifying equipment

2) Assisting manufacturers in getting equipment certified with CEC

3) Assisting manufacturers in developing a contractor training and certification program

4) Assisting manufacturers in establishing local distributors or manufacturer reps for product distribution, parts availability, and warranty issues

5) Set in motion further assistance to manufacturers in developing a warranty program

# Contractors:

- Identifying currently potentially qualified contractors

- Identifying potential contractors (Hydronics experience, etc.)

- Recruit participating contractors as needed

- Encourage to participate in manufacturer training and certification programs

- Use contractors to sell to customers – provide background info

- Incentive to contractors instead or customers as market requires

# Customers:

- Identify current customers with gas cooling units from

  - Manufacturers list

  - Distributors list

  - Contractors list

  - SoCal Gas customer lists – pending as SCG may have reservations about disclosing

  - SCG billing scans from rate or summer usage

- Establishing Web content, (what, why – benefits, key processes, look and feel)

- Enroll Customers – drafting application forms

# Marketing Material

- Developing marketing web piece describing advantages of gas cooling, available product, and details of program

- Developing list of qualified manufacturers and contractors (Manufacturer gets on list by getting product certified and offering contractor training and product warranty support.) (Contractor gets on list by getting certified through manufacturer training program)

- Developing on line and downloadable marketing brochure and application

- Met with three most active gas cooling contractors, Darrow Heating and Air Conditioning of North Hollywood, United Air Conditioning of Baldwin Park, and HH Air Conditioning of Palm Desert. Prospects of gas cooling units eligible for GCRP in near term (in next 6 to 12 months) are identified as the following:

HH – La Quinta Resort and Club, La Quinta, CA., three (3) Goettl 30-ton chillers.

Coincidental, Palm Desert, CA., three (3) Goettl 20-ton GHP.

SoCalGas,  Rate Payer’s Office, Palm Springs, CA., two Goettl 15-ton GHP.

Darrow – fifteen (15) Robur 5-ton chillers in various L A. and Orange County locations.

United A/C – five (5) Robur 5-ton chillers in various L. A. and Orange County locations.

Will contact other contractors in San Bernardino and Riverside counties for potential replacement units in the near future.

- Direct implementation activities (describe)

- Worked with specific manufacturers in getting their products certified by CEC.  Developed preliminary rebate and savings tables. Created basic outline of applications and reviewed process and software with customer service e center. Made 800# available to SCG website. Took several preliminary contractor applications.  Met with Blue Mountain Energy to review their Gas Cooling technology.

- Attended a GCRP kick off meeting and a subsequent meeting relating to the discussion of full-load ton hours for various climatic zones in SoCalGas service territories.

- Invited the representatives of Broad, Robur, Aisin, Tecochill, and Thermax to attend a seminar “2005 Non-Residential Title 24 Standards: Compliance, TDV & Beyond” held at SoCalGas ERC on August 3, 2006. SoCalGas and Cypress met with the attended representatives of manufacturers and presented the GCRP. The GCRP requirements were described to the manufacturers at the meeting.

- Broad, Robur and Aisin expressed strong interest to participate in GCRP. CT assisted the three manufacturers for the listing of their equipment with CEC. Currently, Broad and Robur (pending) were successfully gained the CEC listing. Aisin manufactures gas engine-driven heat pumps (GHP). The performance testing certification data of Aisin’s GHP are required by CEC. Aisin is working with CEC for the equipment listing. It may take longer time for the CEC listing. CT has approached other manufacturers for the CEC listings, but did not receive any positive responses.

- Developed a nomograph that related all the variables for GCRP rebate estimate. Once the COP (Old), COP (New), Full Load Hours, and Capacity in Tons are given, one can quickly obtain the rebate ($) estimate with the developed nomograph, which is attached with this activity report. An example is shown at the bottom of the nomograph. This Nomograph is a useful tool to train contractors or Cypress marketing staff to provide rebate estimate to customers at once. The nomograph can be used for estimating both a cooling and heating rebate amount.

- Program performance/program status (describe)

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain

Program is meeting the expectations of s first year ramp-up to set the stage for delivery of retro-fit units in ’07-’08. The essential market conditioning activities are well underway.

- Program achievements (non-resource programs only):

N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

Added specific climate zone savings categories and added savings calculations for different types of customer scenarios.  Based on market input, added contractors as rebate payees to stimulate contractor marketing efforts.  Eligible tonnage for program participation has been increased from 25 ton or less to 50 tons or less to accommodate the participation of a wider range of gas cooling technologies.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

Continue review of tracking data with software programmers and publish web template. Develop different rebate scenarios based on customer application and location. Continue market outreach and customer service center developments. Adding SCG On-Bill-Financing option for commercial customers.

- Changes to staffing and staff responsibilities, if any

None

- Changes to contracts, if any

Revised billing procedures based on SCG requests

- Changes to contractors and contractor responsibilities, if any

None

- Number of customer complaints received

None

- Revisions to program theory and logic model, if any

None

Basic: Replace old natural gas air conditioning (AC) units and transition to new high efficiency gas AC equipment within Company’s service territory.