| Program Name: | Multi Family Energy Efficiency Retrofit Program |
| --- | --- |
| Program Number: | SCG3510 |
| Quarter: | Fourth Quarter 2006 |

- Program description:

The Southern California Gas Company (SoCal Gas) Multi Family Energy Efficiency Retrofit (MFEER) Program is a statewide program that targets property owners and managers of multifamily residential dwellings, homeowner’s associations, and mobile home park associations.  The program encourages property owners and managers to install qualifying energy efficiency products in common areas for residential apartments, mobile home parks and condominium complexes.  The program is designed for flexibility; it offers agreed upon statewide measures for coordinated implementation, but is designed to easily adapt to market changes, including adding new measures that may emerge as cost effective opportunities in the SoCalGas local service area.

- Administrative activities:

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.  In addition, program staff:

- Continued ongoing communication with Processing and Inspection group to ensure correct application of 2006 program procedures.

- Continued participation in weekly Statewide IOU Multifamily Rebate Team conference calls.

- Attended bi-monthly Residential Customer Programs Staff Meetings.

- 10/9/06:  Attended Director’s Third Quarter Dialogue Session.

- 10/30/06 & 11/7/06: Attended Customer Feedback Performance Team meetings

- 11/21, 12/4, 12/5, 12/06, 12/13, 12/15/2006:  Attended Customer Relationship Management (CRM) Blueprint design workshops for Residential Energy Efficiency process.

- 12/14/06:  Attended Director’s Fourth Quarter Dialogue Session.

- Printed revised 2006 Multifamily Rebate applications as necessary.

- Marketing activities:

- Applications may be downloaded via the web site or requested via SoCalGas’ Residential Marketing Department, or Program Manager.

- 10/20/06:  HUD/LOMCO; Coordinated joint presentation with SCE regarding the statewide Multifamily Rebate Programs.

- 11/3/06:  Continued planning meetings with program manager of South Bay Energy Savings Center to design and implement joint EE Workshop with SCE; 4/19/07.

- 11/15/06:  Participated in the Institute of Heating & Air Conditioning Industries (IHACI) Tradeshow, Pasadena, CA.

  - Distributed multifamily applications and tri-fold program description brochures during the tradeshow.

- 11/16/06:  Participated in the Building Industry Show (BIS), Anaheim CA.

  - Multifamily applications and tri-fold program description brochures were distributed during tradeshow.

- 12/4/06 & 12/6/06:  Met with manufacturers representatives of tankless water heaters to discuss potential participation in 2007 residential EE rebate program.

- Direct implementation activities:

- Approximately 500 applications and brochures were delivered to customers in SoCalGas service territory via tradeshow and outreach participation during fourth quarter.

- Ongoing random inspections of installed rebate measures as required per program specifications.

- 10/18/06:  Attended Basic BW Tools Training class.

- 11/8/06:  Attended Cost Center Line Items Training class.

- 12/18/06: The CA SW IOU MF Rebate program team won Honorable Mention for the Association of Energy Services Professionals 2007 Awards in the Outstanding Achievement in Program Implementation/Design category.

- 12/26/06:  Provided email invitation to participants of Statewide Contractors Meeting scheduled for 1/22/07, Pacific Energy Center, San Francisco, CA.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

There were 719 requests for reservations received for 2006 Multifamily Rebate Program through December 31, 2006.  81% of the incentive goal has been reserved, committed or paid, and the program has achieved 77% of therm goal.  Currently, the program is on target.

- Program achievements (non-resource programs only):

N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- Continued marketing strategy with emphasis on attending Heating & Cooling, and Building Industry Tradeshows in fourth quarter,

- Continued to work with controller contractors to encourage installation of controls in older, pre 1970 multifamily buildings.

- Coordinated invitations for potential speakers for the Southbay Energy Savings Center workshop in 2007.  Proposed agenda will include:  Direct Assistance Program for joint utilities, Municipal Water Districts in the Southbay will deliver program information, and controller contractor will educate owners of multifamily buildings on the benefits of installing controllers on hot water delivery systems.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

- Program Manager worked with Southern California Edison’s counterpart to conduct joint Residential Energy Efficiency Presentation.

- Utilized innovative approach to marketing strategy by participating in tradeshows outside traditional contacts (e.g., Apartment Associations):

  - IHACI Tradeshow

  - Builders Industry Tradeshow

- Program Manager entered into discussions with a contractor regarding 2007 pilot program for installation of energy efficient showerheads and aerators in multifamily buildings.

- Changes to staffing and staff responsibilities, if any:

None

- Changes to contracts:

None

- Changes to contractors and contractor responsibilities, if any:

None

- Number of customer complaints received:

None

- Revisions to program theory and logic model, if any:

None