| Program Name: | SCG Local Business Energy Efficiency Program (BEEP) |
| --- | --- |
| Program Number: | SCG3513 |
| Quarter: | Fourth Quarter 2006 |

- Program description:

Southern California Gas Company’s (SoCalGas) Local Business Energy Efficiency Program (BEEP) targets all nonresidential customers, including commercial, industrial and agricultural customers.

- This program consists of five program elements:

  - Efficient Equipment Rebate Program (EER)

  - Process Equipment Replacement Program(PER)

  - Custom Process Improvement Program(CPI)

  - The “Grant Program”

  - The “Recognition Program”

BEEP is designed with multiple program elements to enable the creation of customized energy efficiency solutions for a wide range of customers.  Combining the five elements into one program also minimizes administrative costs and increases cross-element coordination since the same implementation staff delivers all five elements of this program.

- Administrative activities:

- Regular monthly administrative activities include but are not limited to the following: continued refining of the customer participation process and program design, review of customer participation and market activity, coordination with participating retailers, vendors, and manufacturers and other market participants, contract management, responding to customer inquiries and concerns, planning of future training events, and managing of program budgets and expenditures.

- SoCalGas provided introductory Commercial and Industrial (C&I) Demand Side Management (DSM) Energy Efficiency Program training sessions, including the Business Energy Efficiency Program (BEEP), for six (6) new C&I techs completing their formal training.

- Marketing activities

- SoCalGas attended 25 outreach events during fourth quarter 2006 at which BEEP, and other DSM collateral material, program information and applications were distributed. This brings the total of SoCalGas C&I outreach events to 92 during program year 2006.

- SCG distributed approximately 55,265 pieces of C&I energy efficiency collateral material, brochures, and applications at events, payment offices, and directly through its employees to customers during quarter, bringing the total to 122,053 through program year 2006.

- Direct implementation activities:

- SoCalGas’ BEEP coordinates its activities with its Account Executives and Commercial and Industrial Service Technicians so as to present Energy Efficiency program details to their customers during the course of their daily activities and interactions with SoCalGas’ customers.  SoCalGas’ Account Executives usually have an engineering background and have been tasked to meet the needs of their assigned customers with a focus on promoting rebate programs and to educate customers on energy efficiency matters.  The C&I Service Techs are fully trained in BEEP and are alert for opportunities to assist customers in upgrading their energy inefficient equipment to high efficiency equipment through BEEP during their interaction with the customers during daily service calls.

- SoCalGas continued development of a vendor program during fourth quarter 2006.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

With the completion of Phase 1 development of the new calculation tools along with the associated training during the second quarter, participation in the BEEP program saw 47% of the achieved energy savings produced in the third quarter and fourth quarter.  The acceleration of participating customers in the third quarter and fourth quarter is expected to carry over into the first quarter of 2007.  Currently there is a large quantity of therm savings in the committed mode, a large percentage of these should translate into closed projects for BEEP.

Participation in the Energy Efficiency Grant Program (EEGP) by non-core customers has increased, and several large therm savings projects will be realized in 2007 and 2008.  Due to the size of these projects, and the increased implementation time, many of this program’s therm savings results were not recorded during program year 2006.  Program year 2007 is forecasted to be a large producer of EEGP projects which will also help to meet projected BEEP savings levels by the second quarter or the third quarter of 2007.   These large projects, which include the project M&V phase built into the EEGP contract, require a longer time frame to complete.

Even though these programs are primarily designed for larger commercial and industrial customers, 26% of the incentives and 29% of the therm savings achieved in the BEEP program in program year 2006 went to customers formerly classified as Hard-to-Reach.

- Program achievements (non-resource programs only):

NA

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

None

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

Marketing and outreach efforts will continue as per program year 2006.

- Changes to staffing and staff responsibilities, if any:

None

- Changes to contracts:

None

- Changes to contractors and contractor responsibilities, if any:

None

- Number of customer complaints received:

None

- Revisions to program theory and logic model, if any:

None