| Program Name: | California Department of Corrections and Rehabilitation |
| --- | --- |
| Program Number: | SCG3519 |
| Quarter: | Fourth Quarter 2006 |

- Program Description:

Southern California Gas Company, The California Department of Corrections & Rehabilitation (CDCR) and the other three Investor Owned Utilities (IOUs) are collaborating on a new Energy Efficiency Partnership program to share energy efficiency best practices and to implement energy efficiency projects for immediate and long-term energy savings and peak demand reduction.

The Department of Corrections is a public institution and has recently merged with the California Youth Authority.  The new organization will be comprised of 34 adult facilities and 16 parole offices.  These facilities will have approximately 37,715,415 square feet of occupied space.  There will be an addition of 8 youth facilities with approximately 10 million square feet and 4 camp locations.   Through this transition, Southern California Gas Company and the other IOUs, will collaborate with CDCR to develop an implementation plan and schedule that will ensure timely implementation of identified projects and exceed program objectives.

- Administrative Activities:

- Master Agreement was fully executed by all parties on November 17, 2006.

- CDCR partners are collaborating with the State of California effort, coordinated through Department of General Service (DGS) partnership, to avoid any overlap in program activities and process.  CDCR will follow the requirements to secure project financing through GS$Mart.  The process requires the development of an engineering package with information evaluated through a life cycle cost analysis model to demonstrate the cost effectiveness of the projects. GS$Mart will fund the projects if they meet or exceed program funding criteria.

- CDCR management released an RFQ to solicit qualification from various vendors to support CDCR project implementation effort.  In Q4’06, CDCR was successful in creating a pool of qualified ESCOs, engineering management consultants, lighting and HVAC contractors.  As a result of this progress, the partnership is poised to commence implementation efforts in the first quarter of 2007.

- SCG will provide additional engineering assistance with second phase of project assessment.  These activities will provide information beyond the existing projects identified by previous site audits that were a few years old.  The engineering consultant will be in place by February of 2007.

- Marketing Activities:

- CDCR Facility Management Division has statewide oversight of all facilities.  This includes facilities in all four IOU service territories.  Periodic communications related to partnership implementation activities, especially training opportunities will be disseminated through a pre-established communication infra-structure.  Types of communication to include energy efficiency training information for Prison staff to encourage behavioral changes in conservation and to increase energy efficiency knowledge.

- Direct Implementation Activities:

- SCG collaborated with CDCR representatives to identify facilities that would require preliminary facility assessments.  The assessments will provide CDCR with existing measure information such as types, estimated quantity, energy savings and costs to implement.  CDCR will be able to use the analysis in their contracting discussions with the vendors as well as to support financing requests through GS$Mart.

- CDCR has identified 6 state facilities in SCE and SCG service territory for potential retrofit and retro-commissioning activities.  SCG will work with CDCR to further develop the projects for implementation.

CSP Los Angeles County

California Rehabilitation Center

California Correctional Institution

North Kern State Prison

Ironwood State Prison

California Institution for Women

- CDCR is working on acquiring contracts with ESCOs for each of the 6 sites (Phase One).  The ESCOs will perform the investigation and will provide a formal quote for each facility.  The quote will include (measure type, quantities, cost, kW, kWh, therm savings and project timeline.  This information will feed the application process and will help the IOUs to complete a project agreement and commit the project energy savings.

- Program Performance/Program Status:

( Program is on target

⁬ Program is exceeding expectations

⁬ Program is falling short of expectations

- Program Achievements (non-resource programs only):

- Not Applicable

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- None.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

- SCG will conduct audits in 1st Quarter 2007 to identify additional (Phase Two) projects.

- Changes to staffing and staff responsibilities, if any

- None

- Changes to contracts, if any

- None

- Changes to contractors and contractor responsibilities, if any

- Partners are in discussion on a potential solicitation for a program administration and management contractor/consultant.  This contractor/consultant will help the management team in the overall administration of the partnership program. The tasks will typically include meeting and workshop planning, administrative duties, and coordination of special activities including reporting of results to all the partners.  PG&E will be the lead IOU to initiate this effort.

- Number of customer complaints received

- None

- Revisions to program theory and logic model, if any

- None