| Program Name: | California Urban Water Council Program |
| --- | --- |
| Program Number: | SCG3526 |
| Quarter: | Third Quarter 2006 |

- Program description

This is the third phase of this direct-install incentive-based program that replaces high energy and water use pre-rinse spray valves with more efficient models at food service facilities: restaurants, cafeterias, institutional kitchens and food preparation companies.  There is no cost to the participants and water utilities throughout the state are contributing a portion of the funds for program implementation.  This program targets hard-to-reach food service operators.

- Administrative activities

For the fourth quarter of 2006 SCG focused on stabilizing the field operations and increasing production.   CUWCC contracted with Honeywell Inc. to market and install the spray valves.  Honeywell began field operations in July.

- Marketing activities (describe)

Marketing for this program is done through door-to-door solicitation.  Below are the number of sales visits conducted, valves installed and overall response rate.  The response rate continues to fall well below the expected rate.  This has caused a severe decrease in production.  The response rate is tracking at 27.5%, well below the previous phases’ rate of 50%.  This is due to two main factors saturation and no valve set up.  Many of the outlying communities that were not hit in previous phases that are being targeted in Phase 3 are older communities and most of the food service facilities in those areas do not have a valve set up.  This has reduced our response rate and impacted our ability to meet goal.

| Month | Number of Door-to-door Sales Visits | Number of Spray Valve Installations | Response Rate |
| --- | --- | --- | --- |
| October | 2434 | 683 | 28% |
| November | 1406 | 358 | 25% |
| December | 712 | 213 | 30% |
| Total | 4552 | 1254 | 27.5% |

.

- Direct implementation activities (describe)

Spray valves are installed after the site visit and with approval from the manager/owner.  Listed below are the installations per month.

| Month | Number of Spray Valve Installations |
| --- | --- |
| July | 683 |
| August | 358 |
| September | 213 |
| Total | 1254 |

- Program performance/program status (describe)

Program is on target

Program is exceeding expectations

Program is falling short of expectations

# Explain

# There are two reasons for production fall:

# The program started up several months later than expected.  We continue to track at the average monthly production from phase 1 and 2 during start up months.

# The program to date response rate is tracking at 20%, well below the previous phases’ rate of 50%.  This is due to two main factors: saturation and no spray valve set up.

# Saturation:  As would be expected saturation has increased since Phase 1 of the program.  It is becoming much harder to cost effectively outreach to food service facilities in a door-to-door style because on any given street many of the  sites have been done and therefore the field reps canvass area is not as concentrated.

# No Spray Valve Set Up: Many of the outlying communities that were not hit in previous phases that are being targeted in Phase 3 are older communities and most of the food service facilities in those areas do not have a valve set up.  This has reduced our response rate significantly.

- Program achievements (non-resource programs only):

NA

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

There are no changes to the program.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.)

The program’s end date was scheduled for December 31, 2006.  An extension is still being discussed.

- Changes to staffing and staff responsibilities, if any

There are no changes to staffing or staff responsibilities.

- Changes to contacts,

There are no changes to the contact.

- Changes to contractors and contractor responsibilities, if any

There are no changes to contractors or their responsibilities.

- Number of customer complaints received

No customer complaints were received.

- Revisions to program theory and logic model, if any

Provided in February 1, 2006 concept paper.

There are no changes to the theory and logic model.