| Program Name: | Multi Family Energy Efficiency Retrofit Program |
| --- | --- |
| Program Number: | SCG3510 |
| Quarter: | Second Quarter 2007 |

- Program description:

The Southern California Gas Company (SoCal Gas) Multi-Family Energy Efficiency Retrofit (MFEER) Program is a statewide program that targets property owners and managers of multifamily residential dwellings, homeowner’s associations, and mobile home park associations.  The program encourages property owners and managers to install qualifying energy efficiency products in common areas for residential apartments, mobile home parks and condominium complexes.  The program is designed for flexibility; it offers agreed upon statewide measures for coordinated implementation, but is designed to easily adapt to market changes, including adding new measures that may emerge as cost effective opportunities in the SoCalGas local service area.

- Administrative activities:

Routine monthly administration activities include but not limited to the following:  project tracking, review of prospective projects, coordination, contract management, responding to customer inquiries and concerns, planning for future marketing events, and managing of program budgets and expenditures were performed.  In addition, program staff:

- Continued ongoing communication with Processing and Inspection group to ensure correct application of 2007 program procedures.

- Continued participation in weekly Statewide IOU Multifamily Rebate Team conference calls.

- Attended bi-monthly Residential Customer Programs Staff Meetings.

- 04/03/07:  Attended Controller Study Kick off Meeting with representatives from SDG&E and KEMA

- 4/4/07 & 4/5/07:  Attended Introduction to Energy Efficiency Webinar.

- 04/09/07:  Attended Strategy Session with Honeywell regarding potential MF Audit Program.

- 4/10/07:  Attended Brainstorming session for 2009- 2011 Residential Customer Programs.

- 04/12/07:  Attended 2007 Municipal Green Building Conference

- 04/17/07:  Attended C/I EXPO

- 04/24/07:  Met with Processing Team- Procedural Update

- 04/25/07:  Met with representatives from Honeywell to discuss potential ‘Pilot Program’ for Multi-family properties.

- 04/26/07:  Met w/ representatives from Synergy and Bottom Line to discuss potential ‘Pilot Program’ for Multi-family properties.

- 05/08/07:  Attended Residential Program Process Evaluation meeting- completed interviews with EcoNorthwest

- 05/10/07:  Attended CRM Design walk-thru meeting

- 05/30/07:  Attended Best Practices Training Webcast

- 06/08/07:  Attended Director’s Annual Safety Stand Down

- 06/13/07:  Meeting with LA City Council representatives to discuss EE Rebate and Low Income Programs offered by SoCalGas.

- 06/22/07:  Attended Director’s Quarterly Dialog Session, ERC, Downey.

- 06/26/07:  Attended Public Advisory Group meeting, ERC, Downey.

- Marketing activities:

- Applications may be downloaded via the web site or requested via SoCalGas’ Residential Marketing Department, or Program Manager.

- 04/19/07:  Attended EE Workshop, hosted by the South Bay Energy Savings Center and provided joint EE presentation – SoCalGas & SoCalEdison’s MF EE Rebate Programs.

- 05/31/07:  Participated in the Apartment Owners Association “Million Dollar Tradeshow,” Long Beach, CA

  - Distributed multifamily applications and tri-fold program description brochures during the tradeshow.

  - Offered free EE Starter Kit promotion (Low Flow Showerheads and Aerator sets) to attendees.

- 06/09/07:  Participated in the Plumbing / Heating Contractors Convention (PHCC), Long Beach, CA

  - Distributed multifamily applications and tri-fold program description brochures during the tradeshow.

  - Offered free EE Starter Kit promotion (Low Flow Showerheads and Aerator sets) to attendees.

- 6/01/07:  Statewide IOU advertisement ran in Multifamily Trends Magazine

- Created new collateral to promote the MF Rebate Program and EE Starter Kit

  - Multifamily Fact Sheet –

  - Multifamily Thank you letter

  - Multifamily Sign up sheet & Tenant Roster

- 06/21/07:  Launched Direct Mail Campaign to GME (Master Metered accounts) to promote MF EE Rebate Program and Free EE Starter Kit to multifamily properties.

- Direct implementation activities:

- Multifamily EE Rebate applications and brochures were delivered to customers in SoCalGas service territory via tradeshow and outreach participation during second quarter.

- Promoted the EE Starter Kit and received 5566 requests for free Low Flow Showerheads and Aerators during AOA and PHCC Tradeshow events.

- Ongoing random inspections of installed rebate measures as required per program specifications.

- Continued pre-inspections for SoCalGas Multifamily Rebate Program, with an emphasis on conducting 100% Pre-inspections on Controller devices and 25% of all other measures.

- Created new MultifamilyRebates@SoCalGas.com email box for customers to request EE Starter Kits for multifamily properties.

- Program performance/program status:

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Explain:

Year-to-date, there have been 1049 requests for reservations received for 2006-2008 Multi-family Rebate Program through June 30, 2007.  36% of the incentive goal for 2006-2007 has been paid, and the program has achieved 33% of therm goal.  Currently, the program is falling short of expectations.

- Program achievements (non-resource programs only):

N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.).

- As previously mentioned in Q1 Narrative, MF was focused on launching a pilot program with contractors to install the EE Starter Kits.   Since then, Residential Customer Programs decided to implement a Direct Install program instead.   Significant work has been completed in second quarter and fulfillment will begin in Q3.  Large volume requests are expected and should account for increased therm savings.

- Secondary evaluation on boiler controller savings was requested (for SoCalGas and SDG&E) and will be conducted during second and third quarters 2007.  Reopened measure while awaiting final EM&V.

Effective April 20, 2007, requests for rebates on Boiler and Water Heater Controllers was granted for installations in all multi-family buildings after a brief suspension.

Provided email notification to contractors, internal contacts, and placed information on SoCalGas MF webpage.

- Instituted pre-inspections for 100% boiler controllers and 25% of all other measures in MF Program.

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

Will focus on opportunities to install Low Flow Showerheads and Aerators in Multifamily Properties:
1.  Will offer sign-ups for Free EE Starter Kits at all Residential Outreach Events. 
2.  Will conduct additional Direct Mail Campaign to all Master Metered Apartments Complexes with more than 75 units and offer Free EE Starter Kit and promote rebate program.

3.  Will offer Free EE Starter Kit on SoCalGas’ MF Webpage

4.  Preliminary plans to offer Free EE Starter Kit on Interactive Voice Response Unit for the Customer Call Center.

Plans to promote MF Rebate Program by participating in Upcoming Tradeshows:
09/20/07:  Apartment Owners Association Tradeshow

- Changes to staffing and staff responsibilities, if any:

A temporary Data Entry Clerk was added to the staff.

- Changes to contracts:

None

- Changes to contractors and contractor responsibilities, if any:

None

- Number of customer complaints received:

None

- Revisions to program theory and logic model, if any:

None