| Program Name: | CCC/IOU Energy Efficiency Partnership |
| --- | --- |
| Program Number: | SCG 3518 |
| Quarter: | Second Quarter 2007 |

- Program description

The California Community Colleges/Investor Owned Utility Energy Efficiency Partnership is a unique, statewide program to achieve immediate and long-term energy savings and peak demand reduction within California’s higher education system. The combined funding of nearly $29M for the 2006-08 program cycle will establish a permanent framework for sustainable, comprehensive energy management at Community College campuses served by California's four Investor Owned Utilities.

The 2006-2008 CCC/IOU Partnership was based on the experiences of the previous partnership cycle.  The management structure was modeled after the 2004-2005 UC/CSU Partnership.  However, the structure was flattened to facilitate the decision making process.   A Management Team was established to coordinate the Program and has been meeting on a regular basis for the year to plan and begin implementation of the 06-08 program.

- Administrative activities

- Continued to hold Partnership Management Team meetings every three weeks to conduct the business of the Partnership.  Held bi-weekly Project Team meetings to review and approve new project applications, monthly Outreach Team meetings to focus marketing efforts, and held nominal monthly Training and Education Team meetings to carry-out the program’s training activities.

- The Program web site was fully functional as of the Second Quarter of 2007 with all project data reconciled with IOU internal databases. Training and full rollout-out of the tracking web site to all Partnership stakeholders was completed in the 2nd Quarter.  A suite of standard reports was deployed to the Partnership members via the program website.  The Racetrack and Utility Status reports can be run from the website by anyone with a valid log on and allow users to review management level data for projects; schedule status, progress towards goals, and measure details are available through these standard reports.   Public “banner pages” were developed and deployed to provide a more user-friendly and informative “front-end” to the web site.  The public pages contain links to the project Tracking Tool and other elements of the Program.

- The Partnership was represented at the annual UC/CSU/CCC Sustainability Conference in Santa Barbara in June with Management Team members participating in conference sessions and in participating in Outreach activities.

- The Management Team discussed the need for coordination with other programs, including Savings by Design and Demand Response, to better serve the needs of the Community College customers.

- The Management Team participated in CPUC workshops being held for the planning of the 09-10-11 Energy Efficiency Program cycle to provide input to that process.  The Management Team also started preliminary planning activities for the 09-10-11 cycle.

- Marketing activities (describe)

- Enhanced Outreach, Marketing and Project Development efforts continued during the second quarter to focus on achieving savings goals.  A combined and coordinated effort by the IOU’s, the Foundation for California Community Colleges, the Community College Chancellor’s office, and representatives of the California Energy Commission planned and conducted a series of meetings with District top management staff to re-introduce the Program and explore additional project development opportunities.  This was followed by detailed engineering and auditing evaluation at campuses to develop new project applications.

- Direct implementation activities (describe)

- Through the end of the 2nd Quarter 2007, the Management Team approved projects based on Form 2 Applications from Districts.   All projects reviewed and approved by the Management Team had met IOU due-diligence review criteria based on CPUC filed plans.

- Project Agreements with Districts were executed for approved projects and project implementation activities continued.

- Continued the evolution of the Training & Education program in collaboration with the UC/CSU/IOU Partnership.  During the Second Quarter, the T&E Team worked with the California High Performance Schools (CHPS) program staff to finalize the customized Operations and Maintenance Training Program designed for presentation to Community College Maintenance and Facilities Staff.  This Web-based training will be conducted on two dates:  September 25th and October 3rd and will be available to all CCC Districts.

- A pilot-program was initiated to expand Monitoring Based Commissioning (MBCx) projects in the CCC footprint.  Program guidelines, standard work scope documents, and project application forms were adapted from the UC/CSU program and used with a select number of CCC campuses to evaluate project opportunities.  The expansion of MBCx in the CCC Partnership was one strategy used as part of the enhanced project development activities and is expected to produce significant savings for this program cycle and position campuses for projects in 2009-2011.   MBCx project applications received are under review by the Management Team during the 2nd Quarter.

- Program performance/program

Program is on target

Program is exceeding expectations

Program is falling short of expectations

Overall program performance is still on target for achieving goals over the three year cycle, but a shortfall in approved projects against the plan at this point in time in PG&E, SDG&E, and SCG territories required a renewed focus in those areas.  As discussed above, the Outreach plans and recent enhanced efforts have resulted in an influx of project approvals and significant gains in working toward achieving Program savings goals.

- Program achievements (non-resource programs only):

- N/A

- Changes in program emphasis, if any, from previous quarter (new program elements, less or more emphasis on a particular delivery strategy, program elements discontinued, measure discontinued, budget changes, etc.):

- None

- Discussion of near-term plans for program over the coming months (e.g., marketing and outreach efforts that are expected to significantly increase program participation, etc.):

- Continued review and approval of Project Applications  as they are submitted by Districts.

- Continue with enhanced Outreach Team efforts to identify additional Project Applications for submission and provide technical assistance to Districts/Campuses in need.

- Continue to develop a Training & Education plan coordinated with the UC/CSU Partnership.

- Continue with the development of MBCx pilot program for the Partnership in conjunction with UC/CSU/IOU Partnership.

- Monitor project progress and maintain Project Tracking Tool in Program web site in order to actually assess and forecast Program performance toward goals.

- Initiate preliminary planning efforts and identify potential projects that could apply to 09-10-11 program cycle.

- Changes to staffing and staff responsibilities, if any:

- No changes.

- Changes to contracts, if any:

- No changes.

- Changes to contractors and contractor responsibilities, if any:

- No changes.

- Number of customer complaints received:

- No complaints received.

- Revisions to program theory and logic model, if any:

- No changes.